## Cover Page
Petitioner's Exhibit No. 2
Public Attachment SAH-2 through SAH-9
CEI South
Cause No. 45612
FILED
September 10, 2021
INDIANA UTILITY
REGULATORY COMMISSION

## SAH-2
CEI South
Compliance Projects - Investment Summary
Compliance Projects | 2022 | 2023 | 2024 | 2025 | 2026 | 2022-2026
BS/CI Replacements | 18045042 | 20011733 | 13199987 | 3460048 | 0 | 54716810
Distribution Modernization | 8539815 | 10092693 | 13367728 | 20254845 | 18103781 | 70358862
Transmission Modernization | 11146899 | 16113272 | 14081678 | 17997414 | 22116143 | 81455406
Storage Modernization | 2979306 | 4067334 | 10152791 | 4221349 | 2426923 | 23847703
Compliance Total | 40711062 | 50285032 | 50802184 | 45933656 | 42646847 | 230378781

## SAH-3
CEI South
2022-2026 TDSIC Plan Investment Summary
TDSIC Projects | 2022 | 2023 | 2024 | 2025 | 2026 | 2022-2026
Targeted Economic Development | 200000 | 200000 | 200000 | 200000 | 200000 | 1000000
Rural Extension | 300000 | 300000 | 300000 | 300000 | 300000 | 1500000
System Improvement - Safety and Reliability | 1510539 | 13646438 | 10974689 | 1120209 | 11287660 | 38539535
Public Improvement | 4833130 | 3242894 | 333752 | 0 | 0 | 8409776
TDSIC Total | 6843669 | 17389332 | 11808441 | 1620209 | 11787660 | 49449311

## SAH-4 (Public)
CEI South
Transmission Modernization - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
SW6007-5057 | N/A | TBD | GAS QUALITY / CONDITIONING | SW | EVANSVILLE | Replace heater at Kasson Station - existing heater is obsolete. | 2022
SW6157-5056 | N/A | TBD | GAS QUALITY / CONDITIONING | SW | EDWARDSPORT | Install Carport at Duke Edwardsport Odorizer to eliminate heating threat to odorizer tank. | 2022
SW6159-5037 | N/A | TBD | GAS QUALITY / CONDITIONING | SW | EVANSVILLE | Install gas chromatograph at OBH to monitor gas quality from interstate pipeline | 2022
SW6007-3108 | N/A | TBD | PRESSURE TEST | SW | EVANSVILLE | Pressure test Kasson to Foot Doctor and remediate exposures | 2022
SW6007-5036 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | Replace HCA sections between Kasson and Virginia Rupper and install reg station at Virginia Rupper to reduce MAOP and move to distribution. | 2022
SW6159-4936 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | Phase 1 Replace various sections of 1950, 1953, 1954, 1965 and 1968 vintage pipe in SW6159 - 12" OBH to Oliver Storage Field due to seam defects. Total footage ± 51,005' . This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats | 2022
SW6123-4186 | N/A | TBD | GAS QUALITY / CONDITIONING | SW | MONROE CITY | H2S Removal Amine Plant | 2023
SW6078-4981 | N/A | TBD | PRESSURE TEST | SW | EVANSVILLE | Pressure test 12" Levee to Long Road. -Pressure test entire pipeline for MAOP verification and baseline assessment of HCA at Eagle Crest Blvd. | 2023
SW6159-4338 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | Replace existing 12" pipeline from approximately Measure 33395 to Measure 35589.44 due to seam defects. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats | 2023
SW6160-4984 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | SW6160 - 16" Highway 41 to Kasson Station - Cut out 7.9% dent: 38.020060, -87.53881 - Replace 1.5D 90º Bend: 38.021968, -87.538792 This will allow for In-Line Inspection. | 2023
SW6160-4985 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | SW6005 - 16" Kasson Station to Copperline Road Station - Cutout 4.8% Dent at Koressel Rd: 38.008454, -87.672397 This will allow for In-Line Inspection | 2023
5084 | N/A | TBD | GAS QUALITY / CONDITIONING | SW Storage | OLIVER | Install UltraSonic Metering at Oliver Storage Field to replace obsolete meters and provide enhanced reservoir inventory monitoring and control | 2024
5085 | N/A | TBD | GAS QUALITY / CONDITIONING | SW Storage | MIDWAY | Install Ultrasonic Metering at Midway Storage Field to replace obsolete meters and provide enhanced reservoir inventory monitoring and control | 2024
5088 | N/A | TBD | GAS QUALITY / CONDITIONING | SW Underground Gas Storage | MONROE CITY | Add piping at Monroe City Storage Field to connect 500' storage zone to dehydrator station | 2024
SW6159-4936 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | Phase 2 Replace various sections of 1950, 1953, 1954, 1965 and 1968 vintage pipe in SW6159 - 12" OBH to Oliver Storage Field due to seam defects. Total footage ± 51,005' . This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats | 2024
SW6900-3346 | N/A | TBD | VALVES / OPERATORS / REMOTE CNTRL | SW | MT VERNON | Oliver Storage field install compressor controls upgrade - existing controls obsolete | 2024
SW6900-3141 | N/A | TBD | EXPOSURES | SW | MT VERNON | Remediate exposures in Oliver Storage Field and replace pre-1960 pipe. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats | 2025
SW6076-5053 | N/A | TBD | GAS QUALITY / CONDITIONING | SW | CHRISNEY | Install Gas Chromatograph at MGT Chrisney Station to monitor gas quality | 2025
SW6700-3394 | N/A | TBD | GAS QUALITY / CONDITIONING | SW | MONROE CITY | Install gas chromatograph at Monroe City Storage Field to be able to monitor the quality of gas being delivered out of the storage field. | 2025
4871 | N/A | TBD | OBSOLETE EQUIPMENT | SW | BOONVILLE | Rebuild station #OC-191 (Oakland City TBS) to have primary and secondary runs with bypass and rebuild station #223 (Oakhill) and distribution piping to be able to adequately support station #OC-191 | 2025
5079 | N/A | TBD | OBSOLETE EQUIPMENT | SW | FORT BRANCH | Replace Snake Run odorizer due to obsolete equipment. | 2025
SW6159-4927 | N/A | TBD | OBSOLETE EQUIPMENT | SW | EVANSVILLE | Install relighters at various stations due to lighting issues. | 2025
SW6160-4926 | N/A | TBD | OBSOLETE EQUIPMENT | SW | EVANSVILLE | Install Bruest Pilot Heaters at various stations due to obsolete equipment | 2025
SW6156-3400 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SW | VIINCENNES | Install SCADA at River Road Station - This is where we regulate the Transmission pressure for the town of Vincennes it is located at River Rd and Perdue Rd. Per Greg Hoke | 2025
SW6076-3373 | N/A | TBD | PRIORITY PIPE | SW | NEWBURGH | The current AC mitigation near the intersection of Hwy. 66 and Lincoln Ave. in Newburgh needs to be upgraded to adequately protect the pipeline from external corrosion. | 2025
SW6159-4936 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | Phase 3 Replace various sections of 1950, 1953, 1954, 1965 and 1968 vintage pipe in SW6159 - 12" OBH to Oliver Storage Field due to seam defects. Total footage ± 51,005'. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats | 2025
SW6123-3393 | N/A | TBD | REGULATOR STATION | SW | MONROE CITY | Reconfigure/Replace heater and piping configuration to prevent controls freezing during high flow operation. | 2025
SW6123-3451 | N/A | TBD | REGULATOR STATION | SW | WASHINGTON | Retire Shouse Station due to being obsolete | 2025
SW6700-3404 | N/A | TBD | VALVES / OPERATORS / REMOTE CNTRL | SW | MONROE CITY | Install RCVs at MCSF Hub - Need actuator controller at HUB – Monroe City Storage Field (Ohio Valley Hub) to allow for remote operation of valves. | 2025
SW6700-4897 | N/A | TBD | VALVES / OPERATORS / REMOTE CNTRL | SW | MONROE CITY | Install 8-10 valves at Monroe City Storage Field to ensure safe isolation of well laterals for assessments, operation, and construction. | 2025
SW6700-4288 | N/A | TBD | EXPOSURES | SW | MONROE CITY | Remediate four (4) pipeline exposures within Monroe City Storage Field | 2026
SW6159-4936 | N/A | TBD | PRIORITY PIPE | SW | EVANSVILLE | Phase 4 Replace various sections of 1950, 1953, 1954, 1965 and 1968 vintage pipe in SW6159 - 12" OBH to Oliver Storage Field due to seam defects. Total footage ± 51,005' This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats | 2026

## SAH-5 (Public)
CEI South
Distribution Modernization - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
S-X-229.1 | 17637120 | 20585601050212 | EXPOSURES | SW | NEWBURGH | Indiana - South - Newburgh - N. Birch Dr. 8" HP STL exposure at dich located at 37.972996, -87.400232. Scope: SET 8" ANSI 300 bottom out stoppers at both sides of the ditch and lower 8" HP STL main 5'-10' below the bottom of creek Summary Install 50' of 8" steel main Retire 50' of 8" steel main Replace 0 services | 2022
TBD | N/A | 585450001 | INSIDE METERS | SW | MULTIPLE | SW INSIDE METERS - relocate inside meters to exterior of structure | 2022
S-X-2 | 17637080 | 20585401050217 | LEGACY PLASTIC | SW | EVANSVILLE | Evansville - W. Maryland St - 3" plastic main installed in 1971 via insertion. 2019 - Indiana - Evansville - W. Maryland St. W. Maryland St from N Sonntag to Harmony Way Scope: Replace 1,249' of 3" & 4" 1971 Vintage PE. Install 1,590' of 2" and 4" plastic main Retire 1,630' of 1-1/4", 2", 3" and 4" vintage plastic and bare steel main Replace 26 services | 2022
S-X-4741 | 17637040 | 20585401050213 | LEGACY PLASTIC | SW | EVANSVILLE | Replace approximately 5,755' of 2" PE, 1.25" PE, and 1.25" steel main along S. Villa between SR 66 and Lincoln, E. Chestnut between S. Villa and Vann, S. Dexter between S. Villa and Vann, and Oak between S. Villa and Vann in Evansville due to 1960's vintage plastic main that was installed via insertion. Install 5,957' of 2" plastic main Retire 5,763' of 1-1/4" and 2" vintage plastic main and bare steel main Replace 153 services | 2022
NA | TBD | 585450003 | LEGACY STEEL | SW | MULTIPLE | SW ISOLATED SERVICES - replaced isolated services | 2022
S-X-8 | 17637085 | 20585401050216 | LEGACY STEEL | SW | EVANSVILLE | Indiana - South - Evansville - Evansville - Fickas Rd Fickas Rd from Promise to Jeanette Euclid from Fickas to End of Euclid 3,000 of 2" X-Trube MP STL main (non-standard size) Summary Install 3,045' of 2" plastic main Retire 3,060' of 2" vintage plastic and steel main Replace 19 | 2022
S-X-11 | 17637091 | 20585601050210 | LEGACY STEEL | SW | EVANSVILLE | Indiana - South - Evansville - Evansville - Caren Dr. Caren Road from W Haven to Meadowlark Road Magnolia Road from W Haven to Caren Road Scope: Replace 1,200' of 2" X-trube MP STL main (non-standard size) with 2" MP PL main 38.003178, -87.638232 Summary Install 1,335' of 2" plastic main Retire 1,315' of 2" X-trube steel main Replace 23 services | 2022
S-X-39 | 17637093 | 20585401050218 | LEGACY STEEL | SW | EVANSVILLE | Indiana - South - Evansville - John Street John Street from Boeke to End Scope: Replace 280' of 1.25" xtrube 1955 vintage steel Olive Street from Boeke to End - Scope: Replace 280' of 1.25" xtrube 1955 vintage steel Ruston from Sycamore to Walnut - Scope: Replace 650' of 2" xtrube 1970 vintage steel Welworth from Walnut to Sycamore - Scope Replace 500' of 1.5" vintage plastic 1965 Walnut from Welworth to Vann - Scope Replace 200' of 1.5" vintage steel Vann from Sycamore to Walnut - Scope Replace 800' of 4" vintage steel Total - Replace 2,710' of X Trube vintage steel pipe Summary Install 2,895' of 2" and 4" plastic main Retire 2,590' of 1-1/4", 2" and 4" X-trube steel and vintage plastic main Replace 56 services | 2022
S-X-39.1 | 17637103 | 20585401050219 | LEGACY STEEL | SW | EVANSVILLE | 3,000 of 2" X-Trube MP STL main (non-standard size) | 2022
S-X-40.1 | 18179951 | 20585401050224 | LEGACY STEEL | SW | EVANSVILLE | MOD S-X-40.1 - Evansville, IN Indiana - South - Evansville - N 1st Ave & Meadowridge 1) Greenleaf from N 1st Ave to End: Replace 1,686' of 2" vintage 1959 steel - 43 SVC 2) Tremont from Greenleaf to Lexington: Replace 143' of 1.25" vintage steel - 2 SVC 3) Stratford from W Buena Vista to Park: Replace 1,235' of 4" vintage steel - 13 SVC 4) Lexington from N 1st to Stratford: Replace 1,300' of 2" vintage steel - 26 SVC 5) Kensington from Lexington to N Park: Replace 800' of 2" vintage steel - 22 SVC 6) Tremont from Lexington to N Park: Replace 1,000' of 2" vintage steel - 25 SVC 7 Longfield from Lexington to N Park - Replace 1,1128' of 2" STL - 33 SVC Total - 7,292 and SVC - 164 Summary Install 7,599' of 2" and 4" plastic main Retire 7,371' of 2" and 4" steel main Replace 165 services | 2022
S-X-40.2 | 18179954 | 20585401050225 | LEGACY STEEL | SW | EVANSVILLE | MOD S-X-40.2 - Evansville, IN Indiana - South - Evansville - N 1st Ave & Meadowridge 1) N Park Street from N 1st to Stratford - Replace 1,700' of 2" STL - 17 SVC 2) Commerce from N 1st to End - Replace 750' of 2" STL - 6 SVC 4) Longfield from N Park to Pemberton - Replace 780' of 2" STL - 21 5) Pemberton from Longfield to Stratford - Replace 700' of 2" STL - 20 SVC 6) Tremont from N Park to Kensington - Replace 700' of 2" STL - 20 SVC 7) Kensington from N Park to Pemberton - Replace 1,048' of 2" STL - 35 SVC 8) Stratford from N Park to Pemberton - Replace 1,226' of 2" STL - 35 SVC Total - 6,904 and SVC 154 Summary Install 5,945' of 2" and 4" plastic main Retire 6,205' of 2" steel main, ineffectively coated steel Replace 119 services | 2022
S-X-40.3 | 18179959 | 20585401050226 | LEGACY STEEL | SW | EVANSVILLE | MOD S-X-40.3- Evansville, IN Indiana - South - Evansville - N 1st Ave & Meadowridge 1) W Buena Vista from N 1st to Stratford - Replace 1,400' of 2" STL - 30 SVC 2) Sheridan from N 1st to Stratford - Replace 1,400' of 2" STL - 30 SVC 3) Colonial from N 1st to Stratford - Replace 1,300' of 2" STL - 18 SVC 4) Stratford from W Buenva VIsta to Colonial - Replace 600' of 2" STL - 5 SVC 5) Tremont from W Buena Vista to Colonial - Replace 700' of 2" STL - 2 SVC Total - 5700 and 85 Summary Install 4,443' of 2", 4" and 6" plastic main Retire 4,917' of 2"and 4" steel main Replace 65 services due to ineffectively coated pipe and corrosion issues | 2022
S-X-1688 | 16319393 | 18585501050215 | LEGACY STEEL | SW | WADESVILLE | Replace 15,000' of xtrube pipe (non-standard size) along Stierley S Road from School Lane to Westview Acres in Wadesville, IN. Summary Install 15,115' of 2" plastic main Retire 15,060' of 1-1/4", 2" and 4" steel and vintage plastic main Replace 20 services | 2022
S-X-4822 | 17637068 | 20585401050214 | LEGACY STEEL | SW | EVANSVILLE | Replace approximately 2,540' of MP 2" steel main on S. Taft Ave. between Covert Ave. and Pollack Ave. in Evansville due to leak and corrosion history. Install 2,380' of 2" plastic main Retire 3,150' of 1-1/4" and 2" steel main Replace 70 services | 2022
S-X-4881 | 17637076 | 20585401050215 | LEGACY STEEL | SW | EVANSVILLE | Replace approximately 2,100' of 2", 1-1/4", and 3/4" 1950's steel on W. Maryland and Varner in Evansville that comprises CP System 1731 due to consistently low CP reads and poor coating. Install 3,245' of 2" plastic main Retire 3,215' of 2" 1-1/4" and 2" steel main Replace 58 services | 2022
TBD | N/A | 585450002 | OBSOLETE EQUIPMENT | SW | MULTIPLE | SW OBSOLETE RISERS - replace obsolete service risers | 2022
S-XA-11877 | 18797488 | 21585501050221 | PRESSURE MONITORING/SCADA/RTU | SW | FORT BRANCH | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 3 ERXS | 2022
S-XA-11878 | 18799043 | 21585601050224 | PRESSURE MONITORING/SCADA/RTU | SW | BOONVILLE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) 5 ERXS | 2022
S-XA-11868 | 18768674 | TBD | REGULATOR STATION | SW | FRANKFORT | STATION NUMBER 311 Replace the Relief Blocking Valve at Reg. Station No. 60000292 - Fox Station - Frankfort - obsolete valve | 2022
S-XA-11869 | 18771527 | TBD | REGULATOR STATION | SW | LAFAYETTE | STATION NUMBER 319 Replace the Valves Nos. 59002167 and 59002171 at Reg. Station No. 59000870 - West TBS - Lafayette | 2022
S-XA-11870 | 18771623 | TBD | REGULATOR STATION | SW | EVANSVILLE | STATION NUMBER 325 DIMP Project ID 457 Area - 03.30.2021 - Vintage Plastic - Replace approx. 5,500' of 2" MP Plastic main between Owen St to the south, S 16th St to the east, N 2nd St to the west, Heath St to the north. Replace approx. 110 services. | 2022
S-XA-11871 | 18771698 | TBD | REGULATOR STATION | SW | HATFIELD | STATION NUMBER 304 DIMP Project ID 458 Area - 03.30.2021 - Vintage Plastic - Maps 59-245 & 59-265 Replace approx. 6,000' of 2" MP Plastic main at Kings Way Subdivision off of SR38E and at Pheasant Run Subdivision off of East Brady Lane. Replace approx. 140 services. | 2022
S-XA-11898 | 18352713 | 21585702050213 | REGULATOR STATION | SW | MONROE CITY | MONROE CITY-Install regulator station emergency inlet valve @ 300' SOUTHWEST OF THE INTERSECTION | 2022
S-XA-11899 | 18352711 | 21585502050216 | REGULATOR STATION | SW | PRINCETON | PRINCETON-Install regulator station emergency inlet valve SOUTH OF MULBERRY STREET & @ 200' EA | 2022
S-XA-11901 | 18352676 | 21585702050210 | REGULATOR STATION | SW | BICKNELL | BICKNELL-Install regulator station emergency inlet valve @200' NORTH OF THE INTERSECTION OF | 2022
S-XA-11903 | 18352634 | 21585602050219 | REGULATOR STATION | SW | NEWBURGH | NEWBURGH-Install regulator station emergency inlet valve @ 120' SOUTH OF LAKESIDE DRIVE & 40 | 2022
S-XA-11904 | 18352593 | 21585602050218 | REGULATOR STATION | SW | RICHLAND | RICHLAND-Install regulator station emergency inlet valve SOUTH OF HWY 66 - @ 100' EAST OF CPS | 2022
S-XA-11905 | 18352571 | 21585602050217 | REGULATOR STATION | SW | NEWBURGH | NEWBURGH-Install regulator station emergency inlet valve @ 30' NORTHEAST OF LAKESIDE DRIVE & | 2022
S-XA-11906 | 18352562 | 21585402050214 | REGULATOR STATION | SW | EVANSVILLE | EVANSVILLE-Install regulator station emergency inlet valve 7756 OLD BOONVILLE HWY - WEST OF OLD | 2022
S-XA-11907 | 18352548 | 21585502050214 | REGULATOR STATION | SW | WADESVILLE | WADESVILLE-Install regulator station emergency inlet valve EAST OF DONNER ROAD - @ 1000' SOUTH | 2022
S-XA-11908 | 18352369 | 21585402050213 | REGULATOR STATION | SW | EVANSVILLE | EVANSVILLE-Install regulator station emergency inlet valve SOUTH OF BLUE BELL ROAD - @ 900' WES | 2022
S-XA-12026 | 18352692 | 21585702050212 | REGULATOR STATION | SW | WESTPHALIA | WESTPHALIA-Install regulator station emergency inlet valve EAST OF THE INTERSECTION OF NORTH RA | 2022
S-XA-12027 | 18352652 | 21585502050215 | REGULATOR STATION | SW | PATOKA | PATOKA-Install regulator station emergency inlet valve NORTH SIDE OF FORD ROAD (CR 500 N) | 2022
S-X-231.1 | 18723776 | 21585501050214 | EXPOSURES | SW | PRINCETON | IN-Princeton-S. Dogwood Ln. MOD Project S-X-231.1 - Indiana - South - Fort Branch - Princeton - S. Dogwood Ln. Exposed 6" HP steel main in natural area east of 768 S. Dogwood Ln. in Princeton near 38.344159, -87.501771. Total 200' of 6" HP steel Install 200' of 6" HP steel main Retire 200' of 6" HP steel main Replace 0 SVC | 2023
S-X-232.1 | 18723779 | 21585501050215 | EXPOSURES | SW | PRINCETON | IN-Princeton-Deerhave going west MOD Project S-X-232.1 - Indiana - South - Fort Branch - Princeton - Deerhaven Estate Exposed 6" HP steel main on west side of Deerhave going west through natural area in Princeton in three locations near:38.344435, -87.516441, 38.344326, -87.516711, 38.344431, -87.516944 Install 400' of 6" HP steel main Retire 400' of 6" HP steel main Replace 0 SVC | 2023
S-X-233.1 | 18723805 | 21585401050222 | EXPOSURES | SW | EVANSVILLE | IN-Evansville-Darmstadt Rd. MOD Project S-X-233.1 - Indiana - South - Evansville - Evansville - Darmstadt Rd. 2" MP steel main installed over culvert on Darmstadt Rd. between Old Princeton Rd. and Nuebling Rd. in Evansville. There is a buildup of leaves and soil over the pipe, and the pipe is now exposed. Total 100' of 2" MP PL Install 200' of 2" plastic main Retire 200' of 2" steel main Replace 0 SVC | 2023
S-X-420.1 | 18580569 | 21585401050219 | EXPOSURES | SW | EVANSVILLE | IN-Evansville-NE corner of St Joe MOD Project S-X-420.1 - Evansville, IN 1. Exposure/Bridge Crossing at NE corner of St Joe Road and New Harmony. There is also a casing at this location that doesn't have a test station to monitor. Install 200' of 4" plastic main Retire 200' of 4" steel main Replace 0 | 2023
S-X-422.1 | 18589017 | 21585701050210 | EXPOSURES | SW | WASHINGTON | IN-Washington-Belle Terre Drive MOD Project S-X-422.1 - Washington, IN 1. 2" bare steel installed in 1969 on WO# 1616 is exposed at bridge crossing. Bridge is north of intersection of Belle Terre Drive and SR 257. Install 200' of 2" plastic main Retire 200' of 2" bare steel main Replace 0 SVC | 2023
TBD | N/A | 585450001 | INSIDE METERS | SW | MULTIPLE | SW INSIDE METERS - relocate inside meters to exterior of structure | 2023
S-X-424.1 | 18589026 | 21585501050212 | LEGACY PLASTIC | SW | MT VERNON | IN-Mt Vernon-Old Highway 62 MOD Project S-X-424.1 - Mt. Vernon, IN 1. Old Highway 62 - Pre-74 Plastic replacement. Identified as high risk with risk model. Install 2,283' of 2" plastic main Retire 2,283' of 2" vintage plastic main Replace 9 SVC | 2023
S-X-425.1 | 18589059 | 21585601050217 | LEGACY PLASTIC | SW | NEWBURGH | 1. IN-Newburg-Timber View Dr & Shadow Brook Dr MOD Project S-X-425.1 - Newburgh, IN 1. Timber View Dr & Shadow Brook Dr Install 2,465' of 2" plastic main Retire 2,465' of 2" vintage plastic main Replace 28 SVC | 2023
S-X-438.1 | 18726709 | 21585401050224 | LEGACY PLASTIC | SW | EVANSVILLE | IN-Evansville-Helmuth Rd. MOD Project S-X-438.1 - Evansville, IN 1. Helmuth Road from Edson to Hawthorne Install 581' of 2" plastic main Retire 581' of 2" vintage plastic main Replace 11 SVC | 2023
S-X-439.1 | 18726759 | 21585501050217 | LEGACY PLASTIC | SW | PRINCETON | IN-Princeton- McCarty Road from Darwin to George MOD Project S-X-439.1 - Princeton, IN 1. McCarty Road from Darwin to George Street Install 264' of 2" plastic main Retire 264' of 2" vintage plastic main Replace 2 SVC | 2023
S-X-426.1 | 18589090 | 21585601050218 | LEGACY PLASTIC | SW | NEWBURGH | IN- Newburgh-Jefferson from Posey to Darby MOD Project S-X-426.1 - Newburgh, IN 1. Jefferson from Posey to Darby Install 600' of 2" plastic main Retire 600' of 2" vintage plastic main Replace 6 SVC | 2023
S-X-432.1 | 18723815 | 21585401050223 | LEGACY PLASTIC | SW | EVANSVILLE | IN-Evansville-S Red Bank Rd. MOD Project S-X-432.1 - Evansville, IN 1. S Red Bank Road from 2518 S Red Bank Road to 2828 S Red Bank Road Install 500' of 2" plastic main Retire 500' of 2" vintage plastic main Replace 0 SVC | 2023
S-X-433.1 | 18723828 | 21585601050219 | LEGACY PLASTIC | SW | ROCKPORT | IN-Rockport-W County Road 200 N MOD Project S-X-433.1 - Indiana - South - Rockport - Rockport - W County Road 200 N 1. Replacement recommendations for vintage plastic on W County Road 200 N between N Silverdale and County Road 50 W Install 2,441' of 2" plastic main Retire 2,441' of 2" vintage plastic main Replace 2 SVC | 2023
S-X-434.1 | 18723880 | 21585701050214 | LEGACY PLASTIC | SW | WASHINGTON | In-Washington-SE 4th Street MOD Project S-X-434 - Washington, IN Scope of work: SE 4th from E Oak to E South, Alley south of E Main from SE 3rd to SE 5th E Main from NE 5th to SE 11th, NE 7th from E Main to E Walnut, E Walnut from NE 8th to NE 10th. Install 4,593' of 2" and 4" plastic main Retire 4,593' of 2" and 4" vintage plastic main Replace 45 SVC | 2023
S-X-436.1 | 18724491 | 21585701050215 | LEGACY PLASTIC | SW | VINCENNES | IN-Vincennes Rement recommendation. MOD Project S-X-436.1 - Vincennes, IN 1. Replacement recommendation for vintage plastic on W Broadway Street between S 2nd and S 4th. Install 844' of 2" plastic main Retire 844' of 2" vintage plastic main Replace 3 SVC | 2023
S-X-437.1 | 18726588 | 21585601050220 | LEGACY PLASTIC | SW | NEWBURGH | IN-Newburgh Rement recommendation. MOD Project S-X-437.1 - Newburgh, IN 1. Replacement recommendation of vintage plastic on Ferstel Road, west of Martin Road. Install 1,108' of 2" plastic main Retire 1,108' of 2" vintage plastic main Replace 9 SVC | 2023
S-X-435.1 | 18723930 | 21585501050216 | LEGACY PLASTIC | SW | PRINCETON | IN-Princeton-S Main Street and Garfield MOD Project S-X-435.1 - Princeton, IN 1. Replacement recommendation for vintage plastic on S Main and Garfield. Install 792' of 4" plastic main Retire 792' of 4" vintage plastic main Replace 6 SVC | 2023
NA | TBD | 585450003 | LEGACY STEEL | SW | MULTIPLE | SW ISOLATED SERVICES - replaced isolated services | 2023
S-X-16.1 | 18567402 | 21585401050217 | LEGACY STEEL | SW | EVANSVILLE | IN-Evansville- E. Wortman Rd. MOD Project S-X-16.1 - Evansville, IN 1. E. Wortman Rd. west of Old State Rd. - Install 1968' of 2" plastic main and 6 services Retire 1968' of 2" X-trube steel main | 2023
S-X-21.1 | 18567570 | 21585601050213 | LEGACY STEEL | SW | ROCKPORT | IN- Rockport-W CR 775 N MOD Project S-X-21.1 - Rockport, IN 1. W CR 775 N from CR 525 N to 725 W - 5,216' and 14 SVC 2.N CR 450 W from CR 775 N to W CR 775 N - 1,352' and 5 SVC 3.CR 780 N from N CR 450 W to CR 725 W - 715' and 4 SVC 4. W CR 725 N from CR 780 N to End - Install 7,545' of 2" plastic main Retire 7,545' of 2" X-trube steel main Replace 24 SVC | 2023
S-X-22.1 | 18567571 | 21585501050210 | LEGACY STEEL | SW | WADESVILLE | IN- Wadesville- Koester Rd MOD Project S-X-22.1 - Wadesville, IN 1. Koester Rd. between Winery Rd. and St. Wendel Cynthiana Rd. Install 2,277' of 2" plastic main Retire 2,277' of 2" X-trube steel main Replace 20 SVC | 2023
S-X-427.1 | 18589185 | 21585501050213 | LEGACY STEEL | SW | OAKLAND CITY | IN- Oakland City-Broadway between E Columbia and E Harrison. MOD Project S-X-427.1 - Oakland City, IN 1. Legacy Steel recommended for replacement. ~1100' of 4" 1946 steel on Broadway between E Columbia and E Harrison. Install 1,100' of 4" plastic main Retire 1,100' of 4" steel main Replace 12 SVC | 2023
S-X-10.1 | 18559883 | 21585401050212 | LEGACY STEEL | SW | EVANSVILLE | IN-Evansville- Schmuck Rd MOD Project S-X-10.1 - Evansville, IN 1. Koring Rd. between Schmuck Rd. and Camel Ct - Install 2,534' of 2" medium pressure plastic main. Retire 2,534' of 2" X-trube steel main Replace 15 services. | 2023
S-X-12.1 | 18559926 | 21585401050213 | LEGACY STEEL | SW | EVANSVILLE | IN- Evansville- Lexington Rd. MOD Project S-X-12.1 - Evansville, IN 1. Lexington Rd. east of N. St. Joseph Ave - Install 1,375' of 2" plastic main. Retire 1,375' of 2" X-trube steel main Replace: 11 SVC | 2023
S-X-13.1 | 18560006 | 21585401050214 | LEGACY STEEL | SW | EVANSVILLE | IN- Evansville-Laubscher Rd MOD Project S-X-13.1 - Evansville, IN 1. Laubscher Rd West of Kratzville Road - Install 3,484' of 2" plastic main Retire 3,484 of 2" X-trube steel main Replace: 29 SVC | 2023
S-X-14.1 | 18560018 | 21585401050215 | LEGACY STEEL | SW | EVANSVILLE | IN-Evansville- Berry Dr. MOD Project S-X-14.1 - Evansville, IN 1. Berry Dr. west of Holly Hill Drive - Install 850' of 2" plastic main Retire 850' of 2" X-trube steel main Replace 9 SVC | 2023
S-X-15.1 | 18560022 | 21585401050216 | LEGACY STEEL | SW | EVANSVILLE | IN-Evansville-Baumgart Road MOD Project S-X-15.1 - Evansville, IN 1. Baumgart Road North of Mt. Pleasant Road - Install 2043' of 2" plastic main Retire 2,043' of 2" X-trube steel main Replace: 17 SVC | 2023
S-X-17 | 18179933 | 20585401050223 | LEGACY STEEL | SW | EVANSVILLE | IN- Evansville-Crossbow lane between Deer Trail and Saratoga Drive MOD Project S-X-17 - Evansville, IN Crossbow lane between Deer Trail and Saratoga Drive - Install 1,053' of 2" plastic main Retire 1,053' of 2" X-trube steel main Replace 26 SVC | 2023
S-X-18.1 | 18567419 | 21585601050210 | LEGACY STEEL | SW | NEWBURGH | IN- Newburgh-Frame Rd. MOD Project S-X-18.1 - Newburgh, IN 1. Frame Rd. between Willow Pond Rd. and Bice Ln - Install 1,768' of 2" plastic main Retire 1,768' of 2" X-trube steel main Replace 5 SVC | 2023
S-X-19.1 | 18179947 | 20585601050213 | LEGACY STEEL | SW | NEWBURGH | IN - Newburgh - Ferstel Road MOD S-X-19.1 - Newburgh, IN 1. Ferstel Rd between W. Maron Rd and Anderson Rd - 2,654' of 2" X-trube and 10 SVC 2. Anderson Rd from Yosemite Dr to Reg Station RS 132 - 3,434' 2" X-trube and 22 SVC 3. Sharon Rd from Sleepy Hollow Rd and Spring Corner Rd - 500' of X-Trube and 3 SVC Install 6,588' of 2" plastic main Retire 6588' of 2" X-trube steel main Replace 35 SVC | 2023
S-X-20.1 | 18567501 | 21585601050212 | LEGACY STEEL | SW | NEWBURGH | IN- Newburgh- Pine Dr. MOD Project S-X-20.1 - Newburgh, IN 1. Pine Dr. between SR 66 and Outer Lincoln Dr. - Install 2,005' of 2" plastic main Retire 2,005' of 2" X-trube steel main Replace 45 | 2023
S-X-23.1 | 18567582 | 21585401050218 | LEGACY STEEL | SW | EVANSVILLE | IN-Evansville- Motz Rd. MOD Project S-X-23.1 - Evansville, IN 1. Motz Rd. south of St. Wendel Rd - 720' and 2 SVC 2.North of St. Wendel Rd. between Hillview Dr. and Buente Rd - 501' and 2 SVC 3. Buente Rd. north of St. Wendel Rd - 323' and 2 SVC 4. Emge Rd. north of St. Wendel Rd - 438' and 1 SVC Install 1,982' of 2" plastic main Retire 1,982' of 2" X-trube steel main Replace 7 SVC | 2023
S-X-24.1 | 18567586 | 21585601050215 | LEGACY STEEL | SW | RICHLAND | IN- Rockport-W CR 600 N MOD Project S-X-24.1 - Rockport, IN 1. W CR 600 N between CR 675 W and CR 600 W Install 1,723' of 2" plastic main Retire 1,723' of 2" X-trube steel main Replace 1 SVC | 2023
S-X-25.1 | 18567590 | 21585601050216 | LEGACY STEEL | SW | NEWBURGH | IN- Newburgh-Jenner Rd MOD Project S-X-25.1 - Newburgh, IN 1. Jenner Rd. between Fuquay Rd. and Old Plank Rd. Install 1,413' of 2" plastic main Retire 1,413' of 2" X-trube steel main Replace 11 SVC | 2023
S-X-421.1 | 18589004 | 21585401050220 | LEGACY STEEL | SW | EVANSVILLE | IN-Evansville-Schieps Lane MOD Project S-X-421.1 - Evansville, IN 1. Approximately 620' of 0.75" steel main along Schieps Lane and east of St Joseph Ave. This is old steel installed in 1952 and 1955 that has questionable CP history and extensive corrosion found on the line. In WO# 12542932, 9 band clamps were installed with the same hole to repair 9 pinholes. Install 600' of 2" plastic main Retire 600' of 3/4" steel main Replace 5 SVC | 2023
S-X-45.1 | 18723720 | 21585401050221 | LEGACY STEEL | SW | EVANSVILLE | IN-Evansville-Roosevelt and Riverside MOD Project S-X-45.1 - Evansville, IN 1. Roosevelt from Riverside Drive to Rheinhardt 2.Culverson from Roosevelt to S Villa 3.Saint James from Riverside to Rheinhardt 4.S Ruston from Riverside to Rheinhardt 5.S Villa from Riverside to Rheinhardt 6.Rheingardt from Roosevelt to S Villa Install 6,889' of 2" plastic main Retire 6,889' of 2" steel main Replace 138 SVC | 2023
S-X-7.1 | 18559873 | 21585401050210 | LEGACY STEEL | SW | EVANSVILLE | IN - Evansville-Marx Road MOD Project S-X-7.1 - Evansville, IN 1. Marx Road Between Koressel Rd and New Harmon Rd - 4,900' and 24 SVC 2. Koressel Road between New Harmony Road and Upper Mt Vernon Road - 3,875' and 18 SVC 3. Church Road between New Harmony Rd and Marx Rd - 3879' and 22 Install 12,654' of 2" plastic main Retire 12,654' of 2" X-trube steel main Replace 64 SVC | 2023
S-X-9 | 18175839 | 20585401050222 | LEGACY STEEL | SW | EVANSVILLE | Evansville - Lodge Ave - MOD Project S-X-9 - Evansville, IN Evansville - Lodge Ave - Coupled X-trube, 1973-74 Installation 1. Lilac from Lodge to Sunburst - 733' of 1.25" STL and 16 SVC 2.Lodge from Lilac to Beech - 1,086' of 1.25" STL and 31 SVC 3. Beech from Lodge to Sunburst - 537' of 1.25" STL and 7 SVC 4. Sunburst from Beech to Van Bibber - 535' of 1.25" and 7 SVC Total 2,891' and Replace 61 SVC | 2023
TBD | N/A | 585450002 | OBSOLETE EQUIPMENT | SW | MULTIPLE | SW OBSOLETE RISERS - replace obsolete service risers | 2023
S-XA-11876 | 18797027 | 21585401050226 | PRESSURE MONITORING/SCADA/RTU | SW | VANDERBURGH | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) 11 ERXS | 2023
S-X-101.1 | 18723725 | 21585701050213 | REGULATOR STATION | SW | WASHINGTON | IN-Washington-RS-W29 MOD Project S-X-101.1 - Washington, IN 1. 2019 - Indiana - South - Washington - Washington - RS W-29 Regulator Station W-29 near intersection of Portersville Rd. & Everett Ln. Rebuild Reg Station W-29 | 2023
S-X-99.1 | 18723724 | 21585701050212 | REGULATOR STATION | SW | VINCENNES | IN-Vincennes-RS-V02 MOD Project S-X-99.1 - Vincennes, IN 1. 2019 - Indiana - South - Vincennes - Vincennes - RS V-02 Regulator Station V-02 on SE corner of River Rd. and Perdue Rd. Rebuild Reg Station V-02. obsolete equipment | 2023
S-XA-11872 | 18772478 | 21585501050218 | REGULATOR STATION | SW | MT VERNON | MOD Project S-XA-11872: Reg Station 246-Replace existing regulator Fisher 620 with Fisher 627 | 2023
S-XA-11873 | 18772568 | 21585501050219 | REGULATOR STATION | SW | HAUBSTADT | MOD Project S-XA-11873: Reg Station 289-Replace existing regulator Fisher 620 with Fisher 627 - obsolete equipment | 2023
S-XA-11874 | 18772648 | 21585501050220 | REGULATOR STATION | SW | MT VERNON | MOD Project S-XA-11874: Reg Station 314-Replace existing regulator Fisher 620 with Fisher 627 | 2023
S-XA-11875 | 18796363 | 21585701050216 | REGULATOR STATION | SW | VINCENNES | MOD Project S-XA-11875: Reg Station T-05-Replace existing regulator Chaplin-Fulton 461-57S with 2x1 EZR - obsolete equipment | 2023
S-XA-12012 | 18352342 | 21585502050213 | REGULATOR STATION | SW | HAUBSTADT | HAUBSTADT-Install regulator station emergency inlet valve SOUTH OF CR 1100 S & @ 1000' EAST OF | 2023
S-XA-12013 | 18352330 | 21585602050216 | REGULATOR STATION | SW | ROCKPORT | ROCKPORT-Install regulator station emergency inlet valve NORTH SIDE OF HWY 66 - @ 500' EAST O | 2023
S-XA-12014 | 18352305 | 21585602050215 | REGULATOR STATION | SW | ROCKPORT | ROCKPORT-Install regulator station emergency inlet valve SOUTH SIDE OF HWY 66 - @ 4000' WEST | 2023
S-XA-12015 | 18352301 | 21585602050214 | REGULATOR STATION | SW | NEWBURGH | NEWBURGH-Install regulator station emergency inlet valve MARTIN ROAD & VALLEY ROAD | 2023
S-XA-12016 | 18352299 | 21585602050213 | REGULATOR STATION | SW | NEWBURGH | NEWBURGH-Install regulator station emergency inlet valve WEST SIDE OF LENN ROAD - 0.03 MILES | 2023
S-XA-12017 | 18352263 | 21585602050212 | REGULATOR STATION | SW | RICHLAND | RICHLAND-Install regulator station emergency inlet valve NORTHWEST SIDE OF SR 161 & CR 300 N | 2023
S-XA-12018 | 18352256 | 21585602050210 | REGULATOR STATION | SW | NEWBURGH | NEWBURGH-Install regulator station emergency inlet valve EAST SIDE OF FRAME ROAD ( 0.26 MILES | 2023
S-XA-12021 | 18352216 | 21585402050212 | REGULATOR STATION | SW | EVANSVILLE | EVANSVILLE-Install regulator station emergency inlet valve NORTH OF THE INTERSECTION OF RUPPERT | 2023
S-XA-12022 | 18352209 | 21585402050210 | REGULATOR STATION | SW | EVANSVILLE | EVANSVILLE-'Install regulator station emergency inlet valve 330' SOUTHWEST OF THE INTERSECTION | 2023
S-XA-12029 | 18352224 | 21585502050212 | REGULATOR STATION | SW | MOUNT VERNON | MOUNT VERNON-Install regulator station emergency inlet valve NORTH OF WOLFINGER ROAD - WEST OF HA | 2023
S-XA-12030 | 18352219 | 21585502050210 | REGULATOR STATION | SW | MOUNT VERNON | MOUNT VERNON-'Install regulator station emergency inlet valve @ 80' WEST OF THE INTERSECTION OF F | 2023
TBD | N/A | 585450001 | INSIDE METERS | SW | MULTIPLE | SW INSIDE METERS - relocate inside meters to exterior of structure | 2024
S-X-445.2 | N/A | TBD | LEGACY PLASTIC | SW | WASHINGTON | IN-Washington-State from SE th to 2114 State MOD Project S-X-445.2 - Washington 1. State from SE 15th to 2114 State - 2,560 and 26 2. SE 15th from State to Hazel - 314 and 4 SVC 3. NE 21st from Parkdale to Lakeview - 565 and 3 SVC 4. Lakeview from NE 21st to Bedford - 1,129 and 16 SVC Total 4,568 and 49 services | 2024
S-X-440.1 | N/A | TBD | LEGACY PLASTIC | SW | EVANSVILLE | IN-Evansville-Schneider Road from HWY 66 to 7490 Schneider Lane MOD Project S-X-440.1 - Evansville 1. Schneider Road from HWY 66 to 7490 Schneider Lane Total 1,700 and 1 SVC Old MOD 2133 | 2024
NA | TBD | 585450003 | LEGACY STEEL | SW | MULTIPLE | SW ISOLATED SERVICES - replaced isolated services | 2024
S-X-442.1 | N/A | TBD | LEGACY STEEL | SW | BICKNELL | IN-Washington-Martha Street MOD Project S-X-442.1 - Bicknell 1. Alley S of W 10th from Martha Street and Mary - 430' and 5 SVC 2.Martha Street From W 10th to Alley S of W 9th - 400' and 2 SVC 3. Alley S of W 9th from End to Vigo Street - 2,000' and 20 SVC 4. Alexandra from Alley S of W 9th to Alley S of W 10th - 330' and 5 SVC 5. Alley S of W 10th from Alexandra to Saint Clair - 350' and 5 SVC 6. Alley S of W 8th from Mary to Saint Clair - 1,196' and 15 SVC 7. Mary from Alley S of W 9th to Alley S of W 6th - 960' and 4 SVC 8. Alley S of W 7th from Mary to Martha Street - 500' and 7 SVC 9. W 6th from End to Mary - 550' and 4 SVC 10. Alley S of W 6th from Mary to Saint Clair - 1,134' and 23 Install 7,850' of 2" plastic main Retire 7850' of 2" legacy steel main Replace 90 SVC | 2024
S-X-443.1 | N/A | TBD | LEGACY STEEL | SW | MONTGOMERY | In-Montgomery-CR 100 N MOD Project S-X-443.1 - Montgomery 1. CR 100 N from End to Saint Michaels - 1,230' and 9 SVC 2. 3rd Street from CR 100 N to Railroad - 1,131 and 2 SVC 3. Railroad from 4th to Montgomery Park - 1,800 and 11 SVC 4. Saint Michaels from Railroad to Private Road - 1,348 and 8 SVC 5. Lovers from Orleans to Saint Michaels - 790' and 3 SVC Install 6,300' of 2" plastic main Retire 6,300' of 2" steel main Replace 33 SVC | 2024
S-X-443.2 | N/A | TBD | LEGACY STEEL | SW | MONTGOMERY | IN-Montgomery-N 3rd Street to Main MOD Project S-X-443.2 - Montgomery 1. Little Orleans from N 3rd to Main - 760 and 6 2. Mill from Hasting to Hoffmann Dr - 1,500 and 19 SVC 3. Church from 2nd to Main - 575 and 6 SVC 4. Rudolph from Hasting to Main - 1,200 and 18 SVC 5. Alley north of Rudolph from Hasting to End - 300 and 1 SVC 6. Hasting from Rudolph to Alley - 230 and 2 SVC 7. 2nd from Little Orleans to Rudolph - 650' and 5 SVC 8. Alley east of 1st from little Orleans to Railroad - 488' and 5 & RR crossing 9. Main from Mill to Alley S of Rudolph - 800 and 5 SVC 10. Alley E of Main from little Orleans to Mill - 366 and 7 SVC 11. Hoffman from Mill to End - 700 and 3 SVC 12. Easement north of US 50 E from Main to end - 1,400' and 9 SVC Install 8,969' of 2" plastic main Retire 8,969' of 2" steel main Replace 86 SVC | 2024
S-X-444.1 | N/A | TBD | LEGACY STEEL | SW | WASHINGTON | In-Washington-N 240 W to NW 21 Street MOD Project S-X-444.1 - Washington 1. Oakgrove from N 240 W to NW 21 St - 3,600 and 25 SVC 2. Howard from Oakgrove to Vine - 300' and 3 SVC 3. Vine from Howard to Field - 2,000' and 23 SVC 4. Bent from Oakgrove to Poplar - 950 and 7 SVC 5. Poplar from Bent to CR 200 W - 404 and 2 SVC 6. Wright from Oakgrove to Poplar - 577 and 3 SVC Install 7,831' of 2" plastic main Retire 7,831' of 2" steel main Replace 63 SVC | 2024
S-X-444.4 | N/A | TBD | LEGACY STEEL | SW | WASHINGTON | IN-Washington-Wykoff MOD Project S-X-444.4 - Washington 1. Wykoff from Front to NW 11th - 400 and 2 SVC 2. Longfellow Dr from Front to NW 11th - 700 and 6 SVC 3. Apraw from NW 6th to Front - 700 and 8 SVC 4. Front from Greenwood to St Johns - 3,269 and 26 SVC 5. NW 6th from Morton to Apraw - 923 and 10 SVC. Install 5,992' of 2" plastic main Retire 5,992' of 2" steel main Replace 52 SVC | 2024
S-X-445.1 | N/A | TBD | LEGACY STEEL | SW | WASHINGTON | IN-Washington-Lynwood MOD Project S-X-445.1 - Washington 1. Lynwood Drive from Hwy 57 to Coronado - 1,352 and 22 2. Coronado from Lynwood to Lynwood - 780 and 18 3. Lynwood Drive from Northside to End - 200 and 3 SVC 4. Northside from HWY 57 to Lynwood - 663 and 8 SVC 5. State HWY 57 from Lynwood to 912 SR 57 - 275 and 1 SVC 6. E John from HWY 57 to NE 6th - 329 and 2 SVC 7. NE 6th from E John to Hillcrest - 581 and 9 SVC 8. Florence from NE 6th to Alley W of NE 5th - 387 and 4 SVC 9. Brett Cable from Brett Cabel Ct to NE 12th - 1,287' and 11 SVC 10. Thomas from Green Acres to 1307 Thomas Dr - 460' and 3 SVC 11. Bedford / Flora from NE 7th to NE 1st - 1,500 and 12 SVC 12. NE 2nd from E Walnut to E Flora - 600 and 3 SVC 13. NE 6th from E Hefron to Beford - 357 and 1 SVC Install 8,771' of 2" plastic main Retire 8,771' of 2" vintage plastic main Replace 97 SVC | 2024
S-X-442.3 | N/A | TBD | LEGACY STEEL | SW | BICKNELL | IN-Bicknell-E Thomas MOD Project S-X-442.3 - Bicknell 1. Alley E of Thomas from 10th to Kixmiller - 900' and 8 SVC 2. Alley E of Dant from 10th to Kixmiller - 900' and 20 SVC 3. Alley E of Charles Street from 10th to Kixmiller - 900' and 8 SVC 4. Kixmiller from Thomas to End - 900' and 6 SVC 5. Thomas from Kixmiller to E 4th Street - 337 and 1 SVC Install 6,300' of 2" plastic main Retire 6,300' of 2" steel main Replace 33 SVC | 2024
S-X-443.3 | N/A | TBD | LEGACY STEEL | SW | MONTGOMERY | In-Montgomery-Hasting & Rudolph MOD Project S-X-443.3 - Montgomery 1. Hasting from Rudolph to US 50 - 381 - 2 SVC 2. N 3rd from Rudolph to Maple - 750' and 7 SVC 3. 2nd from Rudolph to Walnut - 1,050' and 2 SVC 4. Meyers from 3rd to 1st - 264 and 3 SVC 5. S Oak from 3rd to CR 650 E - 500 and 7 SVC 6. Maple from 3rd to CR 650 - 500 and 5 SVC 7. Walnut from 3rd to CR 650 E - 500 and 3 SVC 8. CR 650 E from Walnut to End - 1,375 and 7 SVC 9. CR 600 E from Haag Dr to US 50 - 979 and 7 SVC 10. Old HWY 50 from CR 600E to end - 450 and 1 SVC Install 6,750' of 2" plastic main Retire 6,750' of 2" steel main Replace 44 SVC | 2024
S-X-444.2 | N/A | TBD | LEGACY STEEL | SW | WASHINGTON | In-Washington-NW 19th MOD Project S-X-444.2 - Washington 1. NW 19th from Alley S of McCormick to End - 482' and 2 SVC 2. Alley S of McCormick from NW 21st to NW 18th - 620 and 14 SVC 3. NW 21st from W Walnuts Street to North - 800 and 3 SVC 4. Alley N of McCormick from NW 21st to NW 18th - 556 and 4 SVC 5. North from NW 21st to NW 19th - 447 and 3 SVC 6. W 19th from North to Maxwell - 724 and 4 SVC 7. Maxwell from W 19th to George Dr - 2,600 and 15 & RR crossing 8. George from Maxwell to Greenwood - 382 and 1 SVC Install 6,611' of 2" plastic main Retire 6,611' of 2" steel main Replace 46 SVC | 2024
S-X-444.3 | N/A | TBD | LEGACY STEEL | SW | WASHINGTON | In-Washington-NW 16th to NW 11th MOD Project S-X-444.3 - Washington 1. NW 16th from Maxwell to CR 100 N to 1080 N 150 W- 3,166 and 19 SVC 2. Wykoff from NW 16th to NW 11th - 1,635 and 11 SVC 3. Alley S of Wyoff from NW 16th to End - 855 and 16 SVC 4. Alley North of 100 N from NW 16th to End - 391 and 1 SVC 5. Cherry from NW 16th to NW 11th - 1,450 and 9 SVC 6. NW 11th from Maxwell to Greenwood - 382 and 3 SVC Install 7,879' of 2" plastic main Retire 7,879' of 2" steel main Replace 59 SVC | 2024
S-X-466.1 | N/A | TBD | LEGACY STEEL | SW | MT VERNON | IN-MT VERNON-COUNTRY CLUB RD MOD Project S-X-466.1 - Mt Vernon 1. Replace main on Country Club Rd 2. W 4th St and Park St - Install 1,511' of 2" plastic main Retire 1,511' of 2" steel main Replace 5 SVC | 2024
S-XA-12085 | N/A | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-XA-12085 - Evansville 1. 1601 Lincoln Ave 2. Leak on 1935 Main St - Main is in bad condition - gas main in easement - ID 47306158 - Dave Han Report | 2024
S-X-442.2 | N/A | TBD | LEGACY STEEL | SW | BICKNELL | IN-Bicknell-W 4th Street MOD Project S-X-442.2 - Bicknell 1. Alley S of West 4th street from 1024 W 3rd Street to N Main Street - 3,323' and 71 SVC 2. Alley S of West 3rd Street from S Bruceville to Cleveland Street 2,718' and 48 SVC 3. Alley E of Freelandville from E 3rd to E 4th - 500' and 11 SVC Install 6,541' of 2" plastic main Retire 6,541' of 2" steel main Replace 130 SVC | 2024
TBD | N/A | 585450002 | OBSOLETE EQUIPMENT | SW | MULTIPLE | SW OBSOLETE RISERS - replace obsolete service risers | 2024
S-XA-11837 | N/A | TBD | REGULATOR STATION | SW | EVANSVILLE | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2024
TBD | N/A | 585450001 | INSIDE METERS | SW | MULTIPLE | SW INSIDE METERS - relocate inside meters to exterior of structure | 2025
NA | TBD | 585450003 | LEGACY STEEL | SW | MULTIPLE | SW ISOLATED SERVICES - replaced isolated services | 2025
S-X-481.1 | N/A | TBD | LEGACY STEEL | SW | FORT BRANCH | MOD Project S-X-481.1 - Fort Branch 1. E Sinclair from N Main to N Railroad - 453 and 7 SVC 2. Alley E of N West from E Ulen to E Sinclair - 388 and 6 SVC 3. E Ulen from N West to N Church - 1,377 and 14 SVC 4. N Main from E Sinclair to E Ulen - 400 and 3 SVC 5. W John from N Railroad to N Elm - 760 and 9 6. N Main from W John to W Williams - 170 and 3 SVC 7. Alley S of W John from N Main to N McCreary - 300 and 1 SVC 8. N West from E Ulen to W Vine - 950 and 15 9. Alley E of S Polk from W WIlliams to E Ulen - 500 and 1 SVC 10. W WIlliams from N West to S Polk - 340 and 2 SVC Total 5,638 and 61 SVC Summary Install 5,638' of 2" plastic main Retire 5,638' of 1-1/4" and 2" steel main Replace 61 SVC | 2025
S-X-481.2 | N/A | TBD | LEGACY STEEL | SW | FORT BRANCH | MOD Project S-X-481.2 - Fort Branch 1. S Polk from W Williams to W Strain - 1,500 and 22 SVC 2. Alley S of W Vine from S Polk to N McCreary - 575 and 7 SVC 3. Alley W of N McCreary from W Williams to W Walnut - 700 and 13 SVC 4. Alley S of W Locust from S Polk to McCreary - 1,000 and 13 SVC 5. Alley S of W Walnut from S Polk to McCreary - 760 and 17 6. W Foster from S Victor to S Cumberland - 380 and 3 SVC 7. S Victor from W Strain to W Red Bank - 700 and 7 SVC 8. S Cumberland from W Strain to W Red Bank - 450 and 10 Total 6,065 and 92 SVC Summary Install 6,065' of 2" plastic main Retire 6,065' of 1-1/4" and 2" steel main Replace 92 SVC | 2025
S-X-481.3 | N/A | TBD | LEGACY STEEL | SW | FORT BRANCH | IN-Fort Branch-N Elm Street MOD Project S-X-481.3 - Fort Branch 1. N Elm from E Ulen to W Strain - 1,800 and 21 SVC 2. Alley S of E Williams from N McCreary to N Elm - 718 and 8 SVC 3. Alley S of E Locust from S Elm to McCreary - 604 and 4 SVC 4. Alley S of Walnut from S Main to S Elm - 350 and 6 SVC 5. S Main from Alley to W Strain - 500 6 SVC 6. S Railroad from W Strain to E Foster - 150 - 1 SVC 7. S Main from W Stain to Foster - 266 and 4 SVC 8. E Foster from S Railroad to S Main - 300 and 3 SVC 9. Alley E of S Railroad from Foster to Mulberry - 231 and 4 SVC 10. Mulberry from S Railroad to Alley - 350 and 6 SVC 11. Alley E of S Main from E Strain to Mulberry - 388 and 5 SVC 12. Railroad from Mulberry and E Oak - 361 and 4 SVC 13. E Oak from Railroad to S Center - 676 and 4 SVC 14. E Poplar from S Main to Center - 447 and 6 SVC 15. Sandy Pizza parking lot - 195 and 1 SVC 16. Alley W of S Center from Poplar to Rosedale - 221 and 4 SVC 17. Rosedale from Railroad to S Center - 500 and 3 SVC 18. S Main from Rosedale to E South - 251 and 1 SVC Total 8,308 and 84 Summary Install 8,308' of 2" plastic main Retire 8,308' of 2" steel main Replace 84 SVC | 2025
S-X-481.4 | N/A | TBD | LEGACY STEEL | SW | FORT BRANCH | MOD Project S-X-481.4 - Fort Branch 1. Iroquois from Chickasaw to E Park - 344 and 1 SVC 2. Alley N of E Park from Iroquois to End - 451 and 6 SVC 3. Hillcrest from E John to Alley N of E Park - 1,000 and 2 SVC 4. Alley S of E Park from N Willard to N Hull - 973 and 11 SVC 5. Alley S of E Sinclair from N Church to N Hillcrest - 1,300 and 14 SVC 6. Alley S of E Ulen from Church to N Hillcrest - 1,300 and 15 SVC 7. N Walters from Ulen to E Park - 250 and 2 SVC 8. Alley S of E Park from N Church and N Walters - 313 and 6 SVC 9. N Willard from E John to Alley S of E Park - 550 and 3 SVC 10. N Eastview from E Ulen to E John - 178 and 0 SVC 11. E Jon from N Eastview and N HIllcrest - 350 and 7 SVC 12. E Sinclair from N Hull to End - 680 and 2 SVC 13. Alley E of N Hull from E Sinclair to Alley N of E Walnut - 1,760 and 21 14. Tretter Park from N Hull to end - 1,057 and 19 SVC Total 10,506 and 109 Summary Install 10,506' of 2" plastic main Retire 10,506' of 2" steel main MOD Project S-X-481.4 - Fort Branch 1. Iroquois from Chickasaw to E Park - 344 and 1 SVC 2. Alley N of E Park from Iroquois to End - 451 and 6 SVC 3. Hillcrest from E John to Alley N of E Park - 1,000 and 2 SVC 4. Alley S of E Park from N Willard to N Hull - 973 and 11 SVC 5. Alley S of E Sinclair from N Church to N Hillcrest - 1,300 and 14 SVC 6. Alley S of E Ulen from Church to N Hillcrest - 1,300 and 15 SVC 7. N Walters from Ulen to E Park - 250 and 2 SVC 8. Alley S of E Park from N Church and N Walters - 313 and 6 SVC 9. N Willard from E John to Alley S of E Park - 550 and 3 SVC 10. N Eastview from E Ulen to E John - 178 and 0 SVC 11. E Jon from N Eastview and N Hillcrest - 350 and 7 SVC 12. E Sinclair from N Hull to End - 680 and 2 SVC 13. Alley E of N Hull from E Sinclair to Alley N of E Walnut - 1,760 and 21 14. Tretter Park from N Hill to end - 1,057 and 19 SVC Total 10,506 and 109 Summary Install 10,506' of 2" plastic main Retire 10,506' of 2" steel main Replace 109 SVC | 2025
S-X-481.5 | N/A | TBD | LEGACY STEEL | SW | FORT BRANCH | MOD Project S-X-481.5 - Fort Branch 1. Alley E of N Lincoln from End to E Strain - 1,171 and 16 2. Alley E of S Walters from E Vine to E Strain - 1,104 and 20 3. Alley S of E Locust from Alley E of S Walters to US HWY 41 - 1,300 and 23 4. Alley E of S Willard from Alley S of E Locust to E Mulberry - 1,039 and 16 SVC 5. Alley S of E Walnut from S Willard to US HWY 41 - 981 and 25 SVC 6. Walters from E Mulberry to E Strain - 428 and 4 SVC 7. Alley E of S Center from E Strain to E Oak - 688 and 12 SVC 8. E Mulberry from Alley E of S Center to US HWY 41 - 2,254 and 17 SVC 9. S Eastview from E Mulberry to E Oak - 340 and 5 SVC 10. S Hillcrest from E Mulberry to E Oak - 340 and 3 SVC Total 8,475 and 141 Summary Install 8,475' of 2" plastic main Retire 8,475' of 2" steel main Replace 141 SVC | 2025
S-X-482.1 | N/A | TBD | LEGACY STEEL | SW | EDWARDSPORT | MOD Project S-X-482.1 - Edwardsport 1. Market from End to Albert - 335 and 2 SVC 2. Albert from Market to SR 67 - 3.060 and 4 SVC 3. N Lincoln from Albert to End - 788 and 2 SVC 4. 1st from Albert to end - 810 and 13 SVC 5. 3rd from Albert to Harrison - 912 and 3 SVC 6. Water from Albert to Harrison - 900 and 0 SVC Total 6,805 and 24 SVC Summary Install 6,805' of 2" plastic main Retire 6,805' of 2" steel main RepMOD Project S-X-482.1 - Edwardsport 1. Market from End to Albert - 335 and 2 SVC 2. Albert from Market to SR 67 - 3.060 and 4 SVC 3. N Lincoln from Albert to End - 788 and 2 SVC 4. 1st from Albert to end - 810 and 13 SVC 5. 3rd from Albert to Harrison - 912 and 3 SVC 6. Water from Albert to Harrison - 900 and 0 SVC Total 6,805 and 24 SVC Summary Install 6,805' of 2" plastic main Retire 6,805' of 2" steel main Replace 24 SVClace 24 SVC | 2025
S-X-482.2 | N/A | TBD | LEGACY STEEL | SW | EDWARDSPORT | MOD Project S-X-482.2 - Edwardsport 1. Harrison from Water to 5th - 1,500 and 9 SVC 2. Shipping from Water to 5th - 1,400 and 12 SVC 3. Carlisle from 2nd st to 5th - 880 and 12 4. 5th from Harrison to Washington - 1,150 and 6 SVC 5. 4th from Harrison to Washington - 1,150 and 8 SVC 6 3rd from Harrison to Charlisle - 550 and 2 SVC 7. 2nd from Harrison to Washington - 1,1150 and 3 Total 7,780 and 52 Summary Install 7,780' of 2" plastic main Retire 7,780' of 2" steel main Replace 52 SVC | 2025
S-X-482.3 | N/A | TBD | LEGACY STEEL | SW | EDWARDSPORT | MOD Project S-X-482.3 - Edwardsport 1. Washington from 5th to 1st - 1,592 and 6 SVC 2. 1st from Washington to End - 400 and 4 SVC 3. 5th from Washington to Jackson - 800 and 6 SVC 4. 4th from Washington to Jackson - 800 and 6 SVC 5. 3rd from Washington to Jackson - 800 and 6 SVC Total 4,392 and 28 Summary Install 4,392' of 2" plastic main Retire 4,392' of 2" steel main Replace 28 SVC | 2025
S-X-483.1 | N/A | TBD | LEGACY STEEL | SW | VINCENNES | MOD Project S-X-483.1 - Vincennes 1. S 21st from Wilbur to Lake - 865 and 12 SVC 2. S20th from Jerry to Lake - 650 and 15 SVC 3. JC from S 20th to S 21 St - 400 and 5 4. Lake from S 20th to S 21st - 400 and 11 5. Jerry from S 21st to S 22nd - 241 and 6 6. Jerry from S 22nd to Duke - 800 and 15 7. Duke from S 22nd to Jerry - 800 and 7 8. Wessell from S 22nd to End - 1,000 and 14 9. S 22nd from Main to Wessell - 460 and 5 SVC 10. S Main from S 21st to S 20th - 350 and 3 SVC 11. N 21st from Main to Broadway - 700 and 20 12. N 20th from Main to Broadway - 700 and 15 13. Broadway from N 21st to N 19th - 800 and 14 Total 7,936 and 142 Summary Install 7,936' of 2" plastic main Retire 7,936' of 2" steel main Replace 142 SVC | 2025
S-X-483.2 | N/A | TBD | LEGACY STEEL | SW | VINCENNES | MOD Project S-X-483.2- Vincennes 1. Prospect Ave from Dailey to Veterans - 2,352 and 8 SVC 2. Dailey from Wabash Ave to 1206 Dailey Ave - 300 and 1 SVC 3. Sugarloaf from Prospect Ave to End - 500 and 2 SVC 4. Veterans from Prospect Ave to College - 800 and 4 SVC 5. College from Veterans and 2021 College - 237 and 3 SVC Total 4,189 and 18 SVC Summary Install 4,189' of 2" plastic main Retire 4,189' of 2" steel main Replace 18 SVC | 2025
S-X-483.3 | N/A | TBD | LEGACY STEEL | SW | VINCENNES | MOD Project S-X-483.3- Vincennes 1. Forbes from McKinley to McDowell - 1,400' and 9 SVC 2. Margaret Dr from Forbest to John R - 1,300 and 12 SVC 3. John R from Margaret to Forbes - 357 and 2 SVC 4. Ridgeway from Forbes to N 19th - 900 and 7 SVC 5. N 20th from McKinley to Ridgeway - 500 and 3 SVC Total 4,457 and 33 Summary Install 4,457' of 2" plastic main Retire 4,457' of 2" steel main Replace 33 SVC | 2025
S-X-483.4 | N/A | TBD | LEGACY STEEL | SW | VINCENNES | MOD Project S-X-483.4- Vincennes 1. N 2nd from 2620 N 2nd to Old State HWY 67 - 1,900 and 10 SVC 2. Old State HWY 67 from N 2nd to 1457 N State HWY 67 - 1,079 and 5 SVC 3. Executive from N 2th to N 6th ST - 950 and 2 SVC 4. Hillcrest Dr from N Hillcrest Rd to 1691 N Hillcrest - 1,400 and 7 SVC 5. Hillcrest from N Manor to US HWY 41 - 560 and 3 SVC Total 5,889 and 27 Summary Install 5,889' of 2" plastic main Retire 5,889' of 2" steel main Replace 27 SVC | 2025
S-X-484.1 | N/A | TBD | LEGACY STEEL | SW | OAKLAND CITY | MOD Project S-X-484.1 - Oakland City 1. Alley E of N Main from 2nd to End - 1,111 and 15 2. Alley East of Polk from 2nd to End - 986 and 10 SVC 3. 2nd from Highland to End - 1,028 and 7 SVC 4. CR 125 E from E Cherry to 802 CR 1225 E - 1,241 and 4 SVC 5. Old Lade Road from Dongola to 1266 E 100 S - 1,723 and 12 SVC 6. Lincoln from E Cherry to End - 518 and 8 SVC Total 6,607 and 56 Summary Install 6,607' of 2" plastic main Retire 6,607' of 2" steel main Replace 56 SVC | 2025
S-X-485.1 | N/A | TBD | LEGACY STEEL | SW | WHEATLAND | MOD Project S-X-485.1 - Wheatland 1. Alley N of W Main from W Walnut to End - 560 and 7 SVC 2. Alley S of W Main from Nickman to End - 219 and 5 SVC 3. N Nickman from Alley S of W Main to W Main - 127 and 0 SVC 4. S Walnut from RR tracks to W SR 550 - 436 and 3 SVC 5. W Main from N Nickman to N Nicholson - 600 and 2 SVC 6. Nicholson from N Railroad Street to W SR 550 - 634 and 2 SVC 7. Alley N of W SR 550 from Walnut to Nicholson - 500 and 3 SVC 8. Alley E of N Walnut from SR 550 and Church - 469 and 9 SVC 9. Alley E of N Nicholson from SR 550 to Church - 447 and 5 10. Church from Nicholson to N Green - 320 and 3 SVC Total 4,312 and 39 Summary Install 4,312' of 2" plastic main Retire 4,312' of 2" steel main Replace 39 SVC | 2025
S-X-485.2 | N/A | TBD | LEGACY STEEL | SW | WHEATLAND | MOD Project S-X-485.2 - Wheatland 1. Alley S SR 550 Nicholson to S Niblack - 2,250 and 26 SVC 2. W Main from Broadway to N Root - 1,978 and 6 SVC 3. Alley S of W Main from N Nicholson to S Jennings - 1,771 and 14 SVC 4. N Green from Alley S of SR 550 to Church - 600 and 2 SVC 5. Overbey from Green to N White River - 200 and 2 SVC 6. White River from Overbey to Bateman - 330 and 1 SVC 7. Bateman from White River to N Hall - 450 and 2 SVC 8. N Hall from Bateman to End - 400 and 1 SVC 9. SR 550 from N White River to Sycamore - 429 and 2 SVC 10. Sycamore from Alley S of 2nd to 2nd - 145 and 1 SVC 11. Wallace from Railroad to E 3rd - 880 and 5 Total 9,433 and 62 Summary Install 9,433' of 2" plastic main Retire 9,433' of 2" steel main Replace 62 | 2025
S-X-485.3 | N/A | TBD | LEGACY STEEL | SW | WHEATLAND | MOD Project S-X-485.3 - Wheatland 1. S Seminary from Old HWY 50 to W Main - 468 and 0 2. S Railroad W from S Seminary to S Green - 500 and 3 SVC 3. Louisville from SR 550 to S Niblack - 760 and 7 SVC 4. E Old HWY 50 from S SR 550 to Louisville - 500 and 5 SVC 5. Depot from Old HWY 50 to East Adams - 350 and 2 SVC 6. East Adams from Louisville to S Portland - 745 and 5 SVC 7. Niblack from E Adams to Main - 700 and 4 SVC 8. Alley S of Washington from S Portland to Klondike - 1,015 and 11 SVC Total 5038 and 37 Summary Install 5,038' of 2" plastic main Retire 5,038' of 2" steel main Replace 37 | 2025
S-X-486.1 | N/A | TBD | LEGACY STEEL | SW | MONROE CITY | MOD Project S-X-486.1 - Monroe City 1. W 1st from Brekeridge to Cleveland - 350 and 1 SVC 2. 2nd from Main to Cleveland - 302 and 1 SVC 3. 3rd from Main to Cleveland - 300 and 3 SVC 4. Brekenridge from W 1st to 4th - 719 and 12 SVC 5. 5th from Grant to Main - 319 and 7 SVC 6. 6th from Grant to Buchanan - 200 and 5 SVC 7. 8th from Main to Grant - 324 and 3 SVC 8. 10th from Main to End - 1,044 and 8 SVC 9. 11th from Main to End - 658 and 2 SVC 10. Harrison from 11th to End - 200 and 3 SVC 11. Grant from 10th to 11th - 200 and 0 SVC 12. E Black from Monroe School and 10564 E Black Rd - 950 and 3 SVC Total 5,566 and 48 Summary Install 5,566' of 2" plastic main Retire 5,566' of 2" steel main Replace 48 | 2025
S-X-487.1 | N/A | TBD | LEGACY STEEL | SW | LOOGOOTEE | MOD Project S-X-487.1 - Loogootee 1. Bloomfield from 601 Bellbrook Road to 300 feet N of Bellbrook Rd - 486 and 2 SVC 2. Dogwood Hill RD from Bloomfield to 519 Dogwood Hill - 626 and 3 SVC 3. Doyle Ave from 315 Doyle Ave to N Line St - 990 and 12 SVC 4. N Clark from Acton to Doyle - 728 and 4 SVC 5. Bloomfield from N Oak to 310 Bloomfield - 450 and 4 SVC 6. Oak from Bloomfield to End - 1,500 and 9 SVC 7. County Court from 194 Country CT to End - 1,118 and 10 SVC 8. Bel Air from Butcher to End - 770 and 9 SVC 9. Butcher from County Court to John F Kennedy - 1,875 and 15 10. Vincennes from N John F Kennedy to N Line - 533 and 5 11. Mulberry from Vincennes to 107 Mulberry - 264 and 4 SVC 12. Alley E of John F Kennedy from Vincennes to Riley - 364 and 5 SVC 13. Walker from Vincennes to Vine - 550 and 1 SVC Total 10,254 and 88 Summary Install 10,254' of 1-1/4” and 2" plastic main Retire 10,254' of 2" steel main Replace 88 | 2025
S-X-487.2 | N/A | TBD | LEGACY STEEL | SW | LOOGOOTEE | MOD Project S-X-487.2 - Loogootee 1. Brooks from Butcher to Costello - 674 and 10 SVC 2. Walker from Butcher to Wood - 1112 and 13 SVC 3. John from Walker to NW 1st - 488 and 7 SVC 4. Cherry from E Broadway to End - 500 and 6 SVC 5. Mill from Walnut to US HWY 31 - 500 and 3 SVC 6. S Oak from Walnut to Em Street - 1,000 and 13 SVC 7. Elm from US HWY 31 and Poplar - 680 and 4 SVC 8. US HWY 231 from Elm to Private Drive - 1,264 and 3 SVC 9. Industrial Ave from Alley to W Broadway - 300 and 3 SVC 10. John C Stronge Street from W Broadway to End - 970 and 11 SVC Total 7,488 and 73 Summary Install 7,488' of 2" plastic main Retire 7,488' of 2" steel main Replace 73 | 2025
TBD | N/A | 585450002 | OBSOLETE EQUIPMENT | SW | MULTIPLE | SW OBSOLETE RISERS - replace obsolete service risers | 2025
S-XA-11841 | N/A | TBD | REGULATOR STATION | SW | EVANSVILLE | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2025
TBD | N/A | 585450001 | INSIDE METERS | SW | MULTIPLE | SW INSIDE METERS - relocate inside meters to exterior of structure | 2026
516.1 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-516.1 - Evansville, IN Install: 1,273' of 2" plastic main Retire: 1,273' of 2" steel main Replace:4 | 2026
517.1 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-517.1 - Evansville, IN Install: 650' of 2" plastic main Retire:650' of 2" steel main Replace: 18 SVC | 2026
518.1 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-518.1 - Evansville, IN Install:617' of 2" plastic main Retire:617' of 2" steel main Replace: 13 SVC | 2026
519.1 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-519.1 – Evansville Install: 5,438’ of 12” steel Retire: 5,438’ of 12” steel Replace: 87 SVC | 2026
519.2 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-519.2– Evansville Install: 8,212' of 2" plastic main Retire: 8,212 of 1.25" and 2" steel Replace: 113 | 2026
520.1 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-520.1 - Evansville, IN Install:9,812' of 2" plastic main Retire:9,812' of 2" steel main Replace:188 | 2026
520.2 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-520.2 - Evansville, IN Install: 7,195' of 2" plastic main Retire: 7,195' of 2" steel main Replace:125 | 2026
521.1 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-521.1 - Evansville, IN Install:12,223' of 2" plastic main Retire:12,233' of 1.25", 2" and 4" steel main Replace:123 | 2026
522.1 | TBD | TBD | LEGACY STEEL | SW | EVANSVILLE | MOD Project S-X-522.1 - Evansville, IN Install:16,700' of 2" and 4" plastic main Retire:16,700' of 1.25", 2" and 4" steel main Replace: 82 SVC | 2026
NA | TBD | 585450003 | LEGACY STEEL | SW | MULTIPLE | SW ISOLATED SERVICES - replaced isolated services | 2026
512.1 | TBD | TBD | Legacy Steel | SW | EVANSVILLE | MOD Project S-X-512.1 - Evansville, IN Install 5,268' of 12" steel, 110' of 6" plastic and 400' of 4" plastic main Retire 5,268' of 12" steel, 110' of 6" steel and 400' of 4" steel main Replace: 38 SVC | 2026
513.1 | TBD | TBD | Legacy Steel | SW | EVANSVILLE | MOD Project S-X-513.1- Evansville, IN Install 3,850' of 2" plastic main Retire 3,850' of 1.25" and 2" steel main Replace: 32 SVC | 2026
514.1 | TBD | TBD | Legacy Steel | SW | MT VERNON | MOD Project S-X-514.1 - Mt Vernon, IN Install: 3,434' of 2" plastic main Retire: 3,434' of 2" steel main Replace: 21 SVC | 2026
515.1 | TBD | TBD | Legacy Steel | SW | NEWBURGH | MOD Project S-X-515.1 - Newburgh, IN Install: 800' of 2" plastic main Retire: 800' of 1.25" and 2" steel main Replace: 9 SVC | 2026
TBD | N/A | 585450002 | OBSOLETE EQUIPMENT | SW | MULTIPLE | SW OBSOLETE RISERS - replace obsolete service risers | 2026

## SAH-6 (Public)
CEI South
Bare Steel and Cast Iron - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
S-1246 | 18198529 | 98785724 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1246-BSCI - Estimated Installed Footage 6170 - Estimated Retired Footage 7015 - Est Svcs 76 | 2022
S-1255 | 18199140 | 98785704 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1255-BSCI - Est Installed Footage 4635 - Est Retired Footage 5615 - Est Svcs 42 | 2022
S-1266 | 18199342 | 98785723 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1266-BSCI - Est Installed Footage 5900 - Est Retired Footage 8275 - Est Svcs 119 | 2022
S-1351 | 17180018 | 98785371 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1351-BSCI - Est Installed Footage 13720 - Est Retired Footage 8270 - Est Svcs 121 | 2022
S-1352 | 17180444 | 98785372 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1352-BSCI - Est Installed Footage 7535 - Est Retired Footage 6350 - Est Svcs 132 | 2022
S-1361 | 18197966 | 98784727 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1361-BSCI - Est Installed Footage 6366 - Est Retired Footage 8628 - Est Svcs 138 | 2022
S-1363 | 18198378 | 98785703 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1363-BSCI - Est Installed Footage 6755 - Est Retired Footage 4310 - Est Svcs 98 | 2022
S-1364 | 17180843 | 98785373 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1364-BSCI - Est Installed Footage 6646 - Est Retired Footage 6700 - Est Svcs 203 | 2022
S-1365 | 17180860 | 98785382 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1365-BSCI - Est Installed Footage 5797 - Est Retired Footage 3947 - Est Svcs 139 | 2022
S-1367 | 17180882 | 98785383 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1367-BSCI - Est Installed Footage 4127 - Est Retired Footage 5014 - Est Svcs 72 | 2022
S-1378 | 18451740 | 98790038 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1378-BSCI - Est Installed Footage 5670 - Est Retired Footage 5670 - Est Svcs 95 | 2022
S-2085 | 17180951 | 98785062 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2085-BSCI - Est Installed Footage 7855 - Est Retired Footage 6580 - Est Svcs 153 | 2022
S-2298 | 18199289 | 98785720 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2298-BSCI - Est Installed Footage 2670 - Est Retired Footage 4460 - Est Svcs 80 | 2022
S-2499 | 17181074 | 98785104 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2499-BSCI - Est Installed Footage 6956 - Est Retired Footage 5647 - Est Svcs 146 | 2022
S-2500 | 17181103 | 98785111 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2500-BSCI - Est Installed Footage 6930 - Est Retired Footage 6895 - Est Svcs 159 | 2022
S-2501 | 17181149 | 98785258 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2501-BSCI - Est Installed Footage 5959 - Est Retired Footage 4987 - Est Svcs 96 | 2022
S-2524 | 18083851 | 98788970 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2524-BSCI - Est Installed Footage 4204 - Est Retired Footage 4351 - Est Svcs 56 | 2022
S-2525 | 18083982 | 98788999 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2525-BSCI - Est Installed Footage 3875 - Est Retired Footage 5663 - Est Svcs 63 | 2022
S-2526 | 18084037 | 98785753 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2526-BSCI - Est Installed Footage 3358 - Est Retired Footage 3153 - Est Svcs 55 | 2022
S-2638 | 18198452 | 98785716 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2638-BSCI - Est Installed Footage 4495 - Est Retired Footage 5945 - Est Svcs 84 | 2022
S-1212 | N/A | 98783116 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1212-BSCI - Est Installed Footage 6000 - Est Retired Footage 6000 - Est Svcs 67 | 2023
S-1213 | N/A | 98783135 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1213-BSCI - Est Installed Footage 5950 - Est Retired Footage 5950 - Est Svcs 85 | 2023
S-1216 | N/A | 98783138 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1216-BSCI - Est Installed Footage 10350 - Est Retired Footage 10350 - Est Svcs 159 | 2023
S-1241 | N/A | 98785212 | BSCI | SW | OAKLAND CITY | IN-OAKLAND CITY-S-1241-BSCI - Est Installed Footage 11860 - Est Retired Footage 13345 - Est Svcs 126 | 2023
S-1245 | N/A | 98785738 | BSCI | SW | OAKLAND CITY | IN-OAKLAND CITY-S-1245-BSCI - Est Installed Footage 6985 - Est Retired Footage 6985 - Est Svcs 107 | 2023
S-1267 | N/A | 98783097 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1267-BSCI - Est Installed Footage 7691 - Est Retired Footage 7691 - Est Svcs 99 | 2023
S-1269 | N/A | 98783106 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1269-BSCI - Est Installed Footage 3500 - Est Retired Footage 3500 - Est Svcs 49 | 2023
S-1270 | N/A | 98783136 | BSCI | SW | VINCENNES | IN-VINCENNES-S-1270-BSCI - Est Installed Footage 6300 - Est Retired Footage 6300 - Est Svcs 96 | 2023
S-1357 | N/A | 98783132 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1357-BSCI - Est Installed Footage 3260 - Est Retired Footage 3260 - Est Svcs 62 | 2023
S-1360 | N/A | 98783111 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1360-BSCI - Est Installed Footage 4350 - Est Retired Footage 4350 - Est Svcs 111 | 2023
S-1368 | N/A | 98783139 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1368-BSCI - Est Installed Footage 11850 - Est Retired Footage 11850 - Est Svcs 184 | 2023
S-1369 | N/A | 98783101 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1369-BSCI - Est Installed Footage 9150 - Est Retired Footage 9150 - Est Svcs 141 | 2023
S-1382 | N/A | 98783114 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1382-BSCI - Est Installed Footage 7087 - Est Retired Footage 7487 - Est Svcs 149 | 2023
S-2121 | N/A | 98783122 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2121-BSCI - Est Installed Footage 6115 - Est Retired Footage 6115 - Est Svcs 125 | 2023
S-2122 | N/A | 98783125 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2122-BSCI - Est Installed Footage 1427 - Est Retired Footage 1427 - Est Svcs 28 | 2023
S-2296 | N/A | 98783115 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2296-BSCI - Est Installed Footage 5419 - Est Retired Footage 5419 - Est Svcs 66 | 2023
S-2299 | N/A | 98783112 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2299-BSCI - Est Installed Footage 2766 - Est Retired Footage 2766 - Est Svcs 41 | 2023
S-2303 | N/A | 98783117 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2303-BSCI - Est Installed Footage 2737 - Est Retired Footage 2737 - Est Svcs 49 | 2023
S-2371 | N/A | 98783130 | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2371-BSCI - Est Installed Footage 6500 - Est Retired Footage 6500 - Est Svcs 112 | 2023
S-2515 | N/A | 98783102 | BSCI | SW | VINCENNES | IN-VINCENNES-S-2515-BSCI - Est Installed Footage 1500 - Est Retired Footage 1500 - Est Svcs 10 | 2023
S-2639 | N/A | 98786461 | BSCI | SW | OAKLAND CITY | IN-OAKLAND CITY-S-2639-BSCI - Est Installed Footage 5700 - Est Retired Footage 5700 - Est Svcs 80 | 2023
S-1217 | N/A | TBD | BSCI | SW | VINCENNES | IN-VINCENNES-S-1217-BSCI - Est Installed Footage 4850 - Est Retired Footage 4850 - Est Svcs 76 | 2024
S-1248 | N/A | TBD | BSCI | SW | OAKLAND CITY | IN-OAKLAND CITY-S-1248-BSCI - Est Installed Footage 7550 - Est Retired Footage 11600 - Est Svcs 122 | 2024
S-1379 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1379-BSCI - Est Installed Footage 5566 - Est Retired Footage 5566 - Est Svcs 76 | 2024
S-1380 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1380-BSCI - Est Installed Footage 8400 - Est Retired Footage 8060 - Est Svcs 115 | 2024
S-1385 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-1385-BSCI - Est Installed Footage 7250 - Est Retired Footage 7250 - Est Svcs 105 | 2024
S-2287 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2287-BSCI - Est Installed Footage 7640 - Est Retired Footage 7640 - Est Svcs 112 | 2024
S-2288 | N/A | TBD | BSCI | SW | VINCENNES | IN-VINCENNES-S-2288-BSCI - Est Installed Footage 5900 - Est Retired Footage 5900 - Est Svcs 91 | 2024
S-2697 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2697-BSCI - Est Installed Footage 6650 - Est Retired Footage 6650 - Est Svcs 98 | 2024
S-2699 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2699-BSCI - Est Installed Footage 9350 - Est Retired Footage 8357 - Est Svcs 115 | 2024
S-2700 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2700-BSCI - Est Installed Footage 6396 - Est Retired Footage 6396 - Est Svcs 38 | 2024
S-2701 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2701-BSCI - Est Installed Footage 5200 - Est Retired Footage 5200 - Est Svcs 52 | 2024
S-2702 | N/A | TBD | BSCI | SW | OAKLAND CITY | IN-EVANSVILLE-S-2702-BSCI - Est Installed Footage 8040 - Est Retired Footage 8040 - Est Svcs 117 | 2024
S-2535 | N/A | TBD | BSCI | SW | FORT BRANCH | IN-FORT BRANCH-S-2535-BSCI-GIS DATA - Est Installed Footage 482 - Est Retired Footage 692 - Est Svcs 12 | 2025
S-2536 | N/A | TBD | BSCI | SW | FRANCISCO | IN-FRANCISCO-S-2536-BSCI-GIS DATA - Est Installed Footage 429 - Est Retired Footage 429 - Est Svcs 8 | 2025
S-2537 | N/A | TBD | BSCI | SW | OAKLAND CITY | IN-OAKLAND CITY-S-2537-BSCI-GIS DATA - Est Installed Footage 1078 - Est Retired Footage 1078 - Est Svcs 14 | 2025
S-2538 | N/A | TBD | BSCI | SW | PRINCETON | IN-PRINCETON-S-2538-BSCI-GIS DATA - Est Installed Footage 1149 - Est Retired Footage 1149 - Est Svcs 8 | 2025
S-2539 | N/A | TBD | BSCI | SW | MONROE CITY | IN-MONROE CITY-S-2539-BSCI-GIS DATA - Est Installed Footage 5634 - Est Retired Footage 5634 - Est Svcs 3 | 2025
S-2540 | N/A | TBD | BSCI | SW | MONROE CITY | IN-MONROE CITY-S-2540-BSCI-GIS DATA - Est Installed Footage 3623 - Est Retired Footage 3623 - Est Svcs 38 | 2025
S-2541 | N/A | TBD | BSCI | SW | VINCENNES | IN-VINCENNES-S-2541-BSCI-GIS DATA - Est Installed Footage 1638 - Est Retired Footage 1638 - Est Svcs 35 | 2025
S-2542 | N/A | TBD | BSCI | SW | WHEATLAND | IN-WHEATLAND-S-2542-BSCI-GIS DATA - Est Installed Footage 1429 - Est Retired Footage 1429 - Est Svcs 6 | 2025
S-2543 | N/A | TBD | BSCI | SW | LOOGOOTEE | IN-LOOGOOTEE- S-2543 -BSCI-GIS DATA - Est Installed Footage 2254 - Est Retired Footage 2254 - Est Svcs 27 | 2025
S-2544 | N/A | TBD | BSCI | SW | WASHINGTON | IN-WASHINGTON-S-2544-BSCI-GIS DATA - Est Installed Footage 1762 - Est Retired Footage 1762 - Est Svcs 24 | 2025
S-2545 | N/A | TBD | BSCI | SW | EVANSVILLE | IN-EVANSVILLE-S-2545-BSCI-GIS DATA - Est Installed Footage 3450 - Est Retired Footage 3450 - Est Svcs 0 | 2025

## SAH-7 (Public)
CEI South
Storage Modernization - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
S-0257 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-001 DANIEL #1 | 2022
S-0258 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-006 FUEGER #4 | 2022
S-0259 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-008 FUEGER #7 | 2022
S-0330 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Install barricade around MCP-018 Downey #1 | 2022
S-0331 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-003 J.H. Becker #4 | 2022
S-0350 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-015 GROVES #4 | 2022
S-0351 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-023 E KIRKLAND #3 | 2022
S-0329 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-034 Stein Mills #2 | 2022
S-0352 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-032 Schroeder #1 | 2022
S-0020 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Purchase land within Midway Storage Field limits to ensure access and manage/prevent development | 2022
S-0279 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Construct access road to MCP-016 Belcher Like #1 | 2022
S-0280 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Construct access road to MCP-013 Small #3 | 2022
S-0281 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Construct access road to MCP-012 Small #1 | 2022
S-0260 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-009 FUEGER #8 | 2022
S-0261 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-010 FUEGER #9 | 2022
S-0271 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Construct access road to MCP-015 Coonce #1 | 2022
S-0299 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-025 H. KIRKLAND #1 | 2022
S-0333 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Install barricade around MCP-001 Stafford #1 | 2022
S-0334 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Install barricade around MCP-002 Stafford #2 | 2022
S-0032 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-001 Daniel #1 for well logging | 2022
S-0033 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-015 Groves #4 for well logging | 2022
S-0034 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-016 Groves #5 for well logging | 2022
S-0035 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-023 E. Kirkland #3 for well logging | 2022
S-0103 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-006 Fueger #4 for well logging | 2022
S-0104 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-008 Fueger #7 for well logging | 2022
S-0205 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SW | MIDWAY | Install bottomhole pressure monitoring equipment in MID-040 Groves#03 to enhance field management/safety | 2022
S-0206 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SW | MONROE | Install bottomhole pressure monitoring equipment in Stafford#02 to enhance field management/safety | 2022
S-0207 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SW | OLIVER | Install bottomhole pressure monitoring equipment in OLP-064 Weolker#05 to enhance field management/safety | 2022
S-0208 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SW | OLIVER | Install bottomhole pressure monitoring equipment in OLP-057 J.H. Becker#05 to enhance field management/safety | 2022
S-0272 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-029 Reineke #6 | 2023
S-0273 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-015 Buente #5 | 2023
S-0274 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-010 Blackburn #6 | 2023
S-0275 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-005 J.H. Becker #7 | 2023
S-0277 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-038 Willis #7 | 2023
S-0319 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-046 Weolker #2 | 2023
S-0335 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-028 Reineke #5 | 2023
S-0336 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-054 A.A. Becker #2 | 2023
S-0353 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-056 Traverse 3 | 2023
S-0354 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-055 Blackburn #1 | 2023
S-0288 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-013 Buente #3 | 2023
S-0289 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-052 Weolker #10 | 2023
S-0290 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-040 Willis #10 | 2023
S-0276 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-053 Weolker #11 | 2023
S-0278 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-041 Willis #13 | 2023
S-0282 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-011 Buente #1 | 2023
S-0283 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-057 J.H. Becker #1 | 2023
S-0284 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-051 Weolker #8 | 2023
S-0332 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-027 Reineke #4 | 2023
S-0327 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-020 Fee #3 | 2023
S-0387 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-016 Esche #1 | 2023
S-0388 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Construct access road to OLP-050 Weolker #7 | 2023
S-0038 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-038 Willis #7 for well logging | 2023
S-0039 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-046 Weolker #2 for well logging | 2023
S-0065 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-005 J.H. Becker #7 for well logging | 2023
S-0068 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-015 Buente #5 for well logging | 2023
S-0070 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-029 Reineke #6 for well logging | 2023
S-0089 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-050 Weolker #7 for well logging | 2023
S-0093 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-010 Blackburn #6 for well logging | 2023
S-0101 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-059 Willis #3 for well logging | 2023
S-0003 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SW | MONROE | Replug 1 (TBD) existing well of 3 that was not plugged to modern standards by previous operator. | 2023
S-0121 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SW | MONROE | Connect 1 Staunton Formation well (MCP-020 W.G. McCoy #06) to existing Mansfield transmission line to restore field capacity lost through plugging of wells | 2023
S-0285 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-014 GROVES #1 | 2024
S-0286 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Construct access road to MCP-017 Like #1 | 2024
S-0287 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Construct access road to MCP-022 Small #5 | 2024
S-0297 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-005 FUEGER #3 | 2024
S-0337 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Install barricade around MCP-006 Bentle #3 | 2024
S-0338 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Install barricade around MCP-007 Belcher #1 | 2024
S-0339 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-005 J.H. Becker #7 | 2024
S-0340 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-065 Vectren Energy Delivery#01 | 2024
S-0355 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-056 Travers #3 | 2024
S-0073 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-005 Fueger #3 | 2024
S-0076 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-019 Johnson #2 | 2024
S-0105 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-009 Fueger #8 | 2024
S-0106 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-010 Fueger #9 | 2024
S-0392 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SW | MONROE | Replug 1 (TBD) existing well of 2 that was not plugged to modern standards by previous operator. | 2024
S-0001 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SW | MIDWAY | Install transmission line to the Midway horizontal | 2024
S-0004 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SW | MIDWAY | Drilling of new horizontal I/W well to replace plugged MID-022 E. Kirkland #1 | 2024
S-0394 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SW | MIDWAY | Drilling of new vertical OBS well - MID-OBS#1. | 2024
S-0291 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-002 DANIEL #3 | 2025
S-0293 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-004 FUEGER #2 | 2025
S-0294 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-005 FUEGER #5 | 2025
S-0295 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-013 GRAHAM #3 | 2025
S-0296 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-021 KINNEY #4 | 2025
S-0341 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-017 Esche #2 | 2025
S-0342 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-061 Henry Metz#01 | 2025
S-0050 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-011 Buente #1 for well logging | 2025
S-0053 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-027 Reineke #4 for well logging | 2025
S-0056 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-039 Willis #9 for well logging | 2025
S-0072 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-048 Weolker #4 for well logging | 2025
S-0085 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-041 Willis #13 for well logging | 2025
S-0095 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-051 Weolker #8 for well logging | 2025
S-0097 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-053 Weolker #11 for well logging | 2025
S-0099 | N/A | TBD | EQUIPMENT | SW | OLIVER | Replace Wellhead on OLP-057 J.H. Becker #1 for well logging | 2025
S-0393 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SW | MONROE | Replug 1 (TBD) existing well that was not plugged to modern standards by previous operator. | 2025
S-0018 | N/A | 18200601055018 | WELL CONSTRUCTION / REMEDIATION | SW | MONROE | McCoy #13 Vertical Observation Well to enhance field monitoring/safety | 2025
S-0292 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-003 FUEGER #1 | 2026
S-0300 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Construct access road to MID-027 H. KIRKLAND #3 | 2026
S-0305 | N/A | TBD | EMERGENCY RESPONSE | SW | MIDWAY | Install barricade around MID-033 White #3 | 2026
S-0302 | N/A | TBD | EMERGENCY RESPONSE | SW | MONROE | Construct access road to MCP-007 Belcher #1 | 2026
S-0343 | N/A | TBD | EMERGENCY RESPONSE | SW | OLIVER | Install barricade around OLP-001 J.H. Becker #2 | 2026
S-0044 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-024 E. Kirkland #4 for well logging | 2026
S-0059 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-003 Fueger #1 for well logging | 2026
S-0074 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-007 Fueger #5 for well logging | 2026
S-0077 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-025 H. Kirkland #1 for well logging | 2026
S-0079 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-031 Weber #1 for well logging | 2026
S-0080 | N/A | TBD | EQUIPMENT | SW | MIDWAY | Replace Wellhead on MID-033 White #3 for well logging | 2026
S-0116 | N/A | TBD | EQUIPMENT | SW | MONROE | Replace Wellhead on MCP-015 Coonce #1 for well logging | 2026
S-0117 | N/A | TBD | EQUIPMENT | SW | MONROE | Replace Wellhead on MCP-001 Stafford #1 for well logging | 2026
S-0118 | N/A | TBD | EQUIPMENT | SW | MONROE | Replace Wellhead on MCP-002 Stafford #2 for well logging | 2026
S-0119 | N/A | TBD | EQUIPMENT | SW | MONROE | Replace Wellhead on MCP-007 Belcher #1 for well logging | 2026
S-0115 | N/A | TBD | EQUIPMENT | SW | MONROE | Replace Wellhead on MCP-003 Bentle-Small #1 for well logging | 2026

## SAH-8 (Public)
CEI South Bare Steel / Cast Iron Replacement Program
As of December 31, 2020
Group # | PowerPlant Project Number | Operating Center | City | Main Type (Mat'l) | Esimated Install Footage - Mains | Estimated Retire Footage - Mains | Estimated Project Services | Estimated Project Cost | ACTUAL Main Footage Installed | ACTUAL Main Footage Retired [G] | ACTUAL Project Services Replaced or Tied-In [E] | ACTUAL Service Footage Installed | ACTUAL Project Services Retired [C] | ACTUAL Service Footage Retired [D] | Actual Project Investment Cost [A] | [15 empty] | Project Status [B] | CSIA Recovery [H]
[15 empty] | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Total
N/A | 08585552703 | Fort Branch | Mt. Vernon | Bare Steel | 445 | 445 | 8 |  | 704 | 700 | 9 | 260 | 0 | 267 | [16 empty] | posted to CPR | Excluded from CSIA
SW-1 | 08585752706 | Vincennes | Vincennes | Bare Steel | 5075 | 6305 | 75 |  | 5510 | 5411 | 56 | 3918 | 0 | 4088 | [16 empty] | posted to CPR | Excluded from CSIA
S-2 | 08585752707 | Vincennes | Vincennes | Bare Steel | 7300 | 7300 | 116 |  | 9123 | 7655 | 154 | 9546 | 0 | 8963 | [16 empty] | posted to CPR | Excluded from CSIA
S-3 | 09585752525 | Vincennes | Vincennes | Bare Steel | 3881 | 6300 | 91 |  | 3896 | 6661 | 73 | 1818 | 3 | 1512 | [16 empty] | posted to CPR | Excluded from CSIA
S-4 | 08585752708 | Washington | Washington | Bare Steel | 2674 | 2989 | 38 |  | 2615 | 2909 | 30 | 1789 | 1 | 1621 | [16 empty] | posted to CPR | Excluded from CSIA
S-5 | 09585752526 | Vincennes | Vincennes | Bare Steel | 3214 | 3741 | 66 |  | 3272 | 3741 | 58 | 3047 | 1 | 2500 | [16 empty] | posted to CPR | Excluded from CSIA
S-7 | 08585752703 | Vincennes | Vincennes | Bare Steel | 3100 | 3100 | 46 |  | 3450 | 3500 | 56 | 3136 | 0 | 2931 | [16 empty] | posted to CPR | Excluded from CSIA
S-8 | 08585752702 | Montgomery | Montgomery | Bare Steel | 10926 | 0 | 1 |  | 12040 | 12346 | 3 | 1093 | 0 | 18 | [16 empty] | posted to CPR | Excluded from CSIA
S-9 | 08585452804 | Evansville | Evansville | Cast Iron | 16963 | 16933 | 285 |  | 14438 | 15400 | 226 | 16644 | 0 | 15501 | [16 empty] | posted to CPR | Excluded from CSIA
S-10 | 08585452806 | Evansville | Evansville | Bare Steel / Cast Iron | 4505 | 4505 | 99 |  | 4471 | 4964 | 102 | 7711 | 0 | 7876 | [16 empty] | posted to CPR | Excluded from CSIA
S-11 | 08585452807 | Evansville | Evansville | Bare Steel / Cast Iron | 2495 | 3108 | 60 |  | 2340 | 3108 | 64 | 6213 | 0 | 6164 | [16 empty] | posted to CPR | Excluded from CSIA
S-13 | 12585401052214 | Evansville | Evansville | Cast Iron | 2072 | 7957 | 108 |  | 1883 | 9359 | 106 | 7654 | 1 | 7700 | [16 empty] | posted to CPR | Excluded from CSIA
S-14 | 12585401052213 | Evansville | Evansville | Bare Steel / Cast Iron | 3825 | 5075 | 119 |  | 3675 | 5075 | 112 | 6642 | 0 | 6684 | [16 empty] | posted to CPR | Excluded from CSIA
S-15 | 13585401052210 | Evansville | Evansville | Cast Iron | 7875 | 9082 | 247 |  | 8617 | 9082 | 248 | 16933 | 0 | 16773 | [16 empty] | posted to CPR | CSIA Recoverable
S-16 | 12585401052215 | Evansville | Evansville | Cast Iron | 6111 | 10511 | 233 |  | 9439 | 10511 | 237 | 15624 | 1 | 15707 | [16 empty] | posted to CPR | CSIA Recoverable
S-18 | 12585401052216 | Evansville | Evansville | Cast Iron | 3720 | 8395 | 151 |  | 3958 | 8395 | 121 | 6721 | 1 | 6843 | [16 empty] | posted to CPR | CSIA Recoverable
S-19 | 09585452527 | Evansville | Evansville | Bare Steel / Cast Iron | 6245 | 11905 | 239 |  | 5863 | 11905 | 248 | 10608 | 0 | 8958 | [16 empty] | posted to CPR | Excluded from CSIA
S-20 [F] | 08585452805 | Evansville | Evansville | Bare Steel / Cast Iron | 0 | 2550 | 8 |  | 0 | 875 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-22 | 12585701052215 | Vincennes | Vincennes | Bare Steel | 6692 | 9942 | 10 |  | 6881 | 9942 | 8 | 824 | 0 | 702 | [16 empty] | posted to CPR | Excluded from CSIA
S-23 | 13585701052214 | Vincennes | Vincennes | Bare Steel | 7330 | 7330 | 108 |  | 7243 | 7330 | 108 | 2928 | 0 | 3286 | [16 empty] | posted to CPR | CSIA Recoverable
S-24 | 17585701052225 | Vincennes | Vincennes | Bare Steel / Plastic | 5450 | 7518 | 67 |  | 5344 | 7520 | 0 | 0 | 2 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-25 | 09585701052525 | Washington | Washington | Bare Steel | 2485 | 2660 | 48 |  | 3340 | 3856 | 48 | 2942 | 1 | 2856 | [16 empty] | posted to CPR | Excluded from CSIA
S-26 | 09585701052526 | Washington | Washington | Bare Steel | 2315 | 2305 | 24 |  | 3426 | 3151 | 27 | 2341 | 0 | 1764 | [16 empty] | posted to CPR | Excluded from CSIA
S-27 | 09585701052527 | Washington | Washington | Bare Steel | 12445 | 11775 | 160 |  | 12129 | 11113 | 138 | 8813 | 4 | 9936 | [16 empty] | posted to CPR | CSIA Recoverable
S-28 | 09585701052528 | Washington | Washington | Bare Steel | 6740 | 7010 | 139 |  | 7564 | 9040 | 143 | 9705 | 10 | 10138 | [16 empty] | posted to CPR | Excluded from CSIA
S-29 | 10585501052011 | Princeton | Princeton | Bare Steel | 3685 | 4895 | 73 |  | 4487 | 3739 | 66 | 4822 | 6 | 4885 | [16 empty] | posted to CPR | Excluded from CSIA
S-30 | 12585701052214 | Vincennes | Vincennes | Bare Steel | 6665 | 6325 | 107 |  | 6486 | 7343 | 86 | 4373 | 4 | 3695 | [16 empty] | posted to CPR | Excluded from CSIA
S-31 | 13585701052219 | Vincennes | Vincennes | Bare Steel | 235 | 285 | 1 |  | 202 | 385 | 1 | 31 | 0 | 38 | [16 empty] | posted to CPR | CSIA Recoverable
S-32 | 12585701052220 | Vincennes | Vincennes | Bare Steel | 3660 | 4220 | 52 |  | 3942 | 4208 | 50 | 4965 | 1 | 5267 | [16 empty] | posted to CPR | CSIA Recoverable
S-504 | 10585701052212 | Vincennes | Vincennes | Bare Steel | 24550 | 24415 | 0 |  | 25050 | 24330 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-505 | 12585701052213 | Washington | Washington | Bare Steel | 3640 | 3760 | 67 |  | 6234 | 5077 | 72 | 4106 | 5 | 4509 | [16 empty] | posted to CPR | CSIA Recoverable
S-506 | 12585701052212 | Washington | Washington | Bare Steel | 3936 | 3707 | 43 |  | 3925 | 3707 | 29 | 1968 | 5 | 1770 | [16 empty] | posted to CPR | CSIA Recoverable
S-531 | 06585451801 | Evansville | Evansville | Cast Iron | 2585 | 2585 | 95 |  | 2560 | 2250 | 98 | 4723 | 0 | 4687 | [16 empty] | #N/A | Excluded from CSIA
S-532 | 07585452801 | Evansville | Evansville | Cast Iron | 1350 | 1350 | 50 |  | 1350 | 1350 | 45 | 2520 | 0 | 2535 | [16 empty] | posted to CPR | Excluded from CSIA
S-533 | 07585452802 | Evansville | Evansville | Cast Iron | 1840 | 1840 | 58 |  | 1840 | 1840 | 48 | 2210 | 0 | 2201 | [16 empty] | posted to CPR | Excluded from CSIA
S-534 | 07585452803 | Evansville | Evansville | Cast Iron | 1900 | 1900 | 63 |  | 2025 | 3560 | 63 | 3015 | 0 | 3026 | [16 empty] | posted to CPR | Excluded from CSIA
S-535 | 06585461029 | Evansville | Evansville | Cast Iron | 400 | 400 | 0 |  | 414 | 410 | 9 | 702 | 0 | 727 | [16 empty] | #N/A | Excluded from CSIA
S-536 | 07585452800 | Evansville | Evansville | Bare Steel / Cast Iron | 5000 | 5000 | 107 |  | 5172 | 5150 | 107 | 5803 | 0 | 5715 | [16 empty] | posted to CPR | Excluded from CSIA
S-537 | 06585551014 | Princeton | Princeton | Bare Steel | 1400 | 1400 | 0 |  | 1400 | 1400 | 15 | 840 | 0 | 865 | [16 empty] | #N/A | Excluded from CSIA
S-538 | 06585751702 | Washington | Washington | Bare Steel | 4165 | 4165 | 55 |  | 4194 | 4180 | 52 | 3380 | 1 | 3450 | [16 empty] | #N/A | Excluded from CSIA
S-539 | 07585751703 | Vincennes | Vincennes | Bare Steel | 350 | 350 | 0 |  | 235 | 225 | 6 | 210 | 0 | 210 | [16 empty] | #N/A | Excluded from CSIA
S-540 | 08585552700 | Princeton | Princeton | Plastic | 400 | 400 | 0 |  | 376 | 400 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-541 | 07585752700 | Vincennes | Vincennes | Bare Steel | 13500 | 21600 | 7 |  | 11986 | 20000 | 7 | 2821 | 0 | 4363 | [16 empty] | posted to CPR | Excluded from CSIA
S-542 | 08585752701 | Vincennes | Vincennes | Bare Steel | 5400 | 21500 | 6 |  | 7200 | 20300 | 5 | 1911 | 1 | 4043 | [16 empty] | posted to CPR | Excluded from CSIA
S-543 | 08585552701 | Princeton | Princeton | Plastic | 12800 | 12800 | 205 |  | 10955 | 12430 | 155 | 11625 | 0 | 11878 | [16 empty] | posted to CPR | Excluded from CSIA
S-555 | 11585501052210 | Princeton | Princeton | Bare Steel | 6099 | 5469 | 73 |  | 7624 | 6641 | 63 | 3483 | 2 | 2959 | [16 empty] | posted to CPR | Excluded from CSIA
S-615 | 13585701052210 | Vincennes | Vincennes | Bare Steel | 5915 | 5990 | 61 |  | 5989 | 6326 | 54 | 5662 | 0 | 5112 | [16 empty] | posted to CPR | Excluded from CSIA
S-634 | 11585401052210 | Evansville | Evansville | Bare Steel / Cast Iron | 3277 | 3145 | 75 |  | 3582 | 3145 | 79 | 5783 | 0 | 5783 | [16 empty] | posted to CPR | Excluded from CSIA
S-635 | 11585401052212 | Evansville | Evansville | Bare Steel / Cast Iron | 3244 | 3241 | 91 |  | 3264 | 3241 | 89 | 5204 | 0 | 5172 | [16 empty] | posted to CPR | Excluded from CSIA
S-636 | 11585401052213 | Evansville | Evansville | Bare Steel / Cast Iron | 3895 | 3795 | 68 |  | 3961 | 3795 | 64 | 3997 | 0 | 3933 | [16 empty] | posted to CPR | Excluded from CSIA
S-686 | 13585701052216 | Vincennes | Vincennes | Bare Steel / Plastic | 6280 | 4635 | 59 |  | 5764 | 5565 | 48 | 2928 | 2 | 3830 | [16 empty] | posted to CPR | CSIA Recoverable
S-687 | 14585701052219 | Vincennes | Vincennes | Bare Steel | 8660 | 8440 | 122 |  | 8216 | 8129 | 94 | 3018 | 3 | 3489 | [16 empty] | posted to CPR | CSIA Recoverable
S-688 | 14585701052220 | Vincennes | Vincennes | Bare Steel / Plastic | 6290 | 6265 | 107 |  | 6000 | 6265 | 99 | 3170 | 5 | 3904 | [16 empty] | posted to CPR | CSIA Recoverable
S-689 | 14585701052221 | Vincennes | Vincennes | Bare Steel / Plastic | 5505 | 6170 | 100 |  | 6011 | 6562 | 97 | 3476 | 5 | 3795 | [16 empty] | posted to CPR | CSIA Recoverable
S-690 | 15585701052217 | Vincennes | Vincennes | Bare Steel / Plastic | 5880 | 5565 | 73 |  | 5764 | 5565 | 38 | 1187 | 5 | 1230 | [16 empty] | posted to CPR | CSIA Recoverable
S-691 | 15585701052218 | Vincennes | Vincennes | Bare Steel / Plastic | 7135 | 8240 | 84 |  | 5764 | 5565 | 62 | 1187 | 0 | 1230 | [16 empty] | posted to CPR | CSIA Recoverable
S-692 | 13585701052220 | Vincennes | Vincennes | Bare Steel | 6680 | 6660 | 158 |  | 6615 | 7170 | 143 | 5904 | 2 | 6081 | [16 empty] | posted to CPR | CSIA Recoverable
S-693 | 12585501052212 | Francisco | Princeton | Bare Steel | 5460 | 5565 | 137 |  | 5690 | 5565 | 121 | 5805 | 7 | 6277 | [16 empty] | posted to CPR | CSIA Recoverable
S-694 | 12585501052210 | Francisco | Princeton | Bare Steel | 7744 | 7890 | 142 |  | 7736 | 7890 | 137 | 7674 | 9 | 7382 | [16 empty] | posted to CPR | CSIA Recoverable
S-695 | 13585501052215 | Princeton | Princeton | Bare Steel | 7085 | 6925 | 80 |  | 7135 | 6925 | 76 | 4727 | 0 | 4363 | [16 empty] | posted to CPR | CSIA Recoverable
S-696 | 12585701052221 | Washington | Washington | Bare Steel | 7835 | 7730 | 127 |  | 7812 | 7730 | 115 | 6017 | 10 | 6555 | [16 empty] | posted to CPR | CSIA Recoverable
S-697 | 15585701052216 | Vincennes | Washington | Bare Steel | 2728 | 3457 | 66 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-698 | 12585701052222 | Washington | Washington | Bare Steel | 7985 | 9880 | 115 |  | 7752 | 10071 | 113 | 4757 | 5 | 4123 | [16 empty] | posted to CPR | CSIA Recoverable
S-699 | 15585401052214 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 8867 | 7954 | 180 |  | 8889 | 8293 | 177 | 12146 | 1 | 11888 | [16 empty] | posted to CPR | CSIA Recoverable
S-700 | 16585401052220 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 5050 | 5027 | 134 |  | 5236 | 5027 | 0 | 0 | 2 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-701 | 15585401052215 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 5753 | 6775 | 169 |  | 5815 | 6675 | 152 | 0 | 19 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-702 | 18585401052222 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4437 | 4276 | 124 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-703 | 12585401052219 | Evansville | Evansville | Cast Iron | 8808 | 10186 | 168 |  | 9213 | 10186 | 161 | 10993 | 0 | 11193 | [16 empty] | posted to CPR | CSIA Recoverable
S-704 | 16585401052218 | Evansville | Evansville | Bare Steel / Cast Iron | 5070 | 4183 | 74 |  | 5018 | 4186 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-705 | 12585401052220 | Evansville | Evansville | Cast Iron | 9870 | 10200 | 216 |  | 10487 | 10200 | 208 | 13370 | 1 | 13464 | [16 empty] | posted to CPR | CSIA Recoverable
S-706 | 14585401052215 | Evansville | Evansville | Bare Steel / Cast Iron | 4985 | 11694 | 139 |  | 5066 | 14209 | 120 | 4906 | 16 | 4720 | [16 empty] | posted to CPR | CSIA Recoverable
S-707 | 13585401052215 | Evansville | Evansville | Bare Steel / Cast Iron | 1069 | 2867 | 40 |  | 1080 | 2705 | 33 | 1672 | 1 | 1435 | [16 empty] | posted to CPR | CSIA Recoverable
S-708 | 13585401052216 | Evansville | Evansville | Cast Iron | 5781 | 7207 | 167 |  | 6117 | 5546 | 149 | 7022 | 16 | 7340 | [16 empty] | posted to CPR | CSIA Recoverable
S-709 | 15585401052222 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4446 | 4270 | 98 |  | 4374 | 4234 | 91 | 4400 | 3 | 4483 | [16 empty] | posted to CPR | CSIA Recoverable
S-726 | 15585401052220 | Evansville | Evansville | Bare Steel / Cast Iron | 2580 | 2593 | 69 |  | 2450 | 2595 | 63 | 2695 | 5 | 2874 | [16 empty] | posted to CPR | CSIA Recoverable
S-727 | 14585401052213 | Evansville | Evansville | Bare Steel / Cast Iron | 5958 | 6142 | 168 |  | 5702 | 6668 | 153 | 8808 | 21 | 10702 | [16 empty] | posted to CPR | CSIA Recoverable
S-732 | 12585701052223 | Washington | Washington | Bare Steel | 7205 | 7830 | 135 |  | 6845 | 7930 | 115 | 6459 | 12 | 6877 | [16 empty] | posted to CPR | CSIA Recoverable
S-750 | 14585401052214 | Evansville | Evansville | Bare Steel / Cast Iron | 4332 | 4740 | 112 |  | 4295 | 4740 | 97 | 4319 | 10 | 4859 | [16 empty] | posted to CPR | CSIA Recoverable
S-789 | 15585401052221 | Evansville | Evansville | Bare Steel / Cast Iron | 4408 | 5931 | 124 |  | 4125 | 5931 | 119 | 5548 | 4 | 5790 | [16 empty] | posted to CPR | CSIA Recoverable
S-799 | 15585401052223 | Evansville | Evansville | Bare Steel / Cast Iron | 3778 | 4725 | 52 |  | 3925 | 4725 | 41 | 2034 | 5 | 2240 | [16 empty] | posted to CPR | CSIA Recoverable
S-803 | 15585401052224 | Evansville | Evansville | Bare Steel / Cast Iron | 3074 | 3488 | 91 |  | 2892 | 3488 | 77 | 3950 | 9 | 4289 | [16 empty] | posted to CPR | CSIA Recoverable
S-805 | 15585401052225 | Evansville | Evansville | Bare Steel / Cast Iron | 2001 | 4767 | 68 |  | 1992 | 4767 | 54 | 2892 | 7 | 3115 | [16 empty] | posted to CPR | CSIA Recoverable
S-806 | 15585401052226 | Evansville | Evansville | Bare Steel / Cast Iron | 4461 | 4192 | 104 |  | 4272 | 4192 | 100 | 5372 | 7 | 6435 | [16 empty] | posted to CPR | CSIA Recoverable
S-807 | 15585401052216 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 3873 | 4111 | 113 |  | 3877 | 4111 | 96 | 0 | 7 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-808 | 12585401052212 | Evansville | Evansville | Cast Iron | 2675 | 3610 | 79 |  | 2798 | 3610 | 67 | 4310 | 1 | 4393 | [16 empty] | posted to CPR | Excluded from CSIA
S-815 | 11585401052214 | Evansville | Evansville | Cast Iron | 6910 | 4725 | 85 |  | 7410 | 5155 | 94 | 5641 | 0 | 6570 | [16 empty] | posted to CPR | Excluded from CSIA
S-863 | 12585701052216 | Vincennes | Vincennes | Bare Steel | 1194 | 1194 | 13 |  | 1186 | 1186 | 14 | 1634 | 0 | 1634 | [16 empty] | posted to CPR | Excluded from CSIA
S-985 | 12585401052217 | Evansville | Evansville | Cast Iron | 10980 | 8955 | 116 |  | 9093 | 8955 | 117 | 11542 | 1 | 11088 | [16 empty] | posted to CPR | CSIA Recoverable
S-986 | 15585401052227 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4890 | 5285 | 143 |  | 5270 | 5285 | 134 | 0 | 9 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-987 | 12585401052218 | Evansville | Evansville | Cast Iron | 11145 | 13205 | 172 |  | 11681 | 13205 | 153 | 9538 | 2 | 12202 | [16 empty] | posted to CPR | CSIA Recoverable
S-1014 | 12585501052214 | Francisco | Princeton | Bare Steel | 10640 | 13940 | 167 |  | 11141 | 13495 | 148 | 8768 | 11 | 6650 | [16 empty] | posted to CPR | CSIA Recoverable
S-1015 | 12585501052213 | Francisco | Princeton | Bare Steel | 2445 | 2590 | 30 |  | 2189 | 2590 | 23 | 1043 | 1 | 1333 | [16 empty] | posted to CPR | CSIA Recoverable
S-1018 | 12585701052217 | Vincennes | Vincennes | Bare Steel | 1888 | 1835 | 30 |  | 2064 | 2064 | 22 | 980 | 1 | 766 | [16 empty] | posted to CPR | Excluded from CSIA
S-1033 | 12585701052218 | Vincennes | Vincennes | Bare Steel | 4610 | 4420 | 72 |  | 5194 | 5000 | 69 | 2662 | 3 | 2748 | [16 empty] | posted to CPR | CSIA Recoverable
S-1034 | 12585701052219 | Vincennes | Vincennes | Bare Steel | 3530 | 3520 | 18 |  | 3434 | 3544 | 14 | 680 | 1 | 531 | [16 empty] | posted to CPR | CSIA Recoverable
S-1175 | 14585701052212 | Vincennes | Washington | Bare Steel / Plastic | 6840 | 6580 | 70 |  | 6983 | 6385 | 0 | 0 | 1 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1176 | 15585701052212 | Vincennes | Washington | Bare Steel / Plastic | 10708 | 10523 | 136 |  | 10919 | 10523 | 123 | 6205 | 13 | 7063 | [16 empty] | posted to CPR | CSIA Recoverable
S-1177 | 16585701052210 | Vincennes | Washington | Bare Steel / Plastic | 7012 | 6625 | 122 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1194 | 15585701052213 | Vincennes | Washington | Bare Steel / Plastic | 7104 | 7153 | 93 |  | 6997 | 6924 | 86 | 4073 | 2 | 4185 | [16 empty] | posted to CPR | CSIA Recoverable
S-1195 | 16585701052212 | Vincennes | Washington | Bare Steel / Plastic | 3442 | 4131 | 43 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1196 | 16585701052213 | Vincennes | Washington | Bare Steel / Plastic | 8960 | 8938 | 108 |  | 9770 | 10248 | 0 | 0 | 8 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1197 | 14585701052213 | Vincennes | Washington | Bare Steel | 1665 | 1480 | 27 |  | 1609 | 1480 | 22 | 1229 | 1 | 1337 | [16 empty] | posted to CPR | CSIA Recoverable
S-1199 | 17585701052210 | Vincennes | Washington | Bare Steel / Plastic | 8696 | 8246 | 121 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-1201 | 17585701052212 | Vincennes | Washington | Bare Steel / Plastic | 8963 | 9462 | 79 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-1203 | 13585701052212 | Vincennes | Vincennes | Bare Steel | 6345 | 9165 | 85 |  | 5611 | 9165 | 63 | 2447 | 2 | 2268 | [16 empty] | posted to CPR | CSIA Recoverable
S-1204 | 17585701052213 | Vincennes | Vincennes | Plastic | 950 | 2901 | 265 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-1206 | 14585501052212 | Fort Branch | Princeton | Bare Steel / Plastic | 9902 | 9882 | 163 |  | 9902 | 9882 | 153 | 8221 | 10 | 8693 | [16 empty] | posted to CPR | CSIA Recoverable
S-1207 | 16585501052210 | Fort Branch | Princeton | Bare Steel / Plastic | 9141 | 7141 | 89 |  | 9136 | 7825 | 85 | 4112 | 3 | 3801 | [16 empty] | posted to CPR | CSIA Recoverable
S-1208 | 16585501052212 | Fort Branch | Princeton | Bare Steel / Plastic | 10101 | 10719 | 110 |  | 10528 | 10719 | 102 | 4936 | 11 | 5080 | [16 empty] | posted to CPR | CSIA Recoverable
S-1214 | 15585701052219 | Vincennes | Vincennes | Bare Steel / Plastic | 14360 | 13635 | 118 |  | 15798 | 15545 | 125 | 13480 | 1 | 12395 | [16 empty] | posted to CPR | CSIA Recoverable
S-1218 | 13585501052214 | Princeton | Princeton | Bare Steel | 3850 | 4745 | 72 |  | 3922 | 4475 | 58 | 2648 | 2 | 2836 | [16 empty] | posted to CPR | CSIA Recoverable
S-1222 | 13585501052210 | Fort Branch | Princeton | Bare Steel / Plastic | 9900 | 10075 | 107 |  | 10876 | 10393 | 119 | 6537 | 2 | 6235 | [16 empty] | posted to CPR | CSIA Recoverable
S-1224 | 16585501052214 | Fort Branch | Princeton | Bare Steel / Plastic | 3251 | 3923 | 44 |  | 3360 | 3907 | 0 | 0 | 1 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1228 | 13585701052217 | Vincennes | Loogootee | Bare Steel | 7288 | 7005 | 115 |  | 8146 | 7275 | 105 | 0 | 5 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1229 | 13585701052218 | Loogootee | Loogootee | Bare Steel | 8811 | 7717 | 78 |  | 8319 | 8237 | 68 | 4362 | 2 | 4368 | [16 empty] | posted to CPR | CSIA Recoverable
S-1230 | 14585701052214 | Vincennes | Loogootee | Bare Steel / Plastic | 4888 | 6437 | 56 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | Excluded from CSIA
S-1231 | 20585701052219 | Vincennes | Loogootee | Bare Steel / Plastic | 9684 | 10925 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1232 | 18585701052221 | Vincennes | Loogootee | Bare Steel / Plastic | 3535 | 3529 | 1515 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1233 | 18585701052212 | Vincennes | Loogootee | Bare Steel / Plastic | 6316 | 7216 | 43 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | Excluded from CSIA
S-1234 | 13585701052215 | Vincennes | Petersburg | Bare Steel / Plastic | 11260 | 9925 | 99 |  | 11384 | 10210 | 96 | 3539 | 12 | 4724 | [16 empty] | posted to CPR | CSIA Recoverable
S-1235 | 14585701052216 | Vincennes | Petersburg | Bare Steel / Plastic | 4001 | 7185 | 71 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-1236 | 14585701052217 | Vincennes | Petersburg | Bare Steel / Plastic | 4108 | 5959 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-1237 | 15585701052214 | Vincennes | Petersburg | Bare Steel / Plastic | 4340 | 5354 | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-1238 | 19585701052212 | Vincennes | Petersburg | Bare Steel / Plastic | 9195 | 8794 | 84 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-1241 | 20585501052210 | Fort Branch | Oakland City | Bare Steel / Plastic | 11860 | 13349 | 127 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | initiated | CSIA Recoverable
S-1243 | 16585701052214 | Vincennes | Vincennes | Bare Steel | 3399 | 2583 | 39 |  | 36263 | 2583 | 31 | 0 | 2 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1244 | 18585701052213 | Vincennes | Vincennes | Plastic | 6165 | 7029 | 61 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-1253 | 13585501052212 | Fort Branch | Francisco | Bare Steel / Plastic | 14204 | 13359 | 122 |  | 14408 | 13356 | 110 | 0 | 12 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1254 | 17585701052214 | Vincennes | Vincennes | Bare Steel / Plastic | 5890 | 6104 | 96 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1257 | 18585701052214 | Vincennes | Vincennes | Bare Steel / Plastic | 3575 | 4155 | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-1260 | 18585701052215 | Vincennes | Vincennes | Bare Steel / Plastic | 5195 | 5472 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-1261 | 19585701052213 | Vincennes | Vincennes | Bare Steel / Plastic | 5645 | 5246 | 4155 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-1262 | 18585701052216 | Vincennes | Vincennes | Bare Steel / Plastic | 6350 | 6976 | 117 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-1264 | 19585701052214 | Vincennes | Vincennes | Bare Steel / Plastic | 6860 | 5912 | 87 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-1265 | 17585701052215 | Vincennes | Vincennes | Plastic | 5075 | 4187 | 66 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-1268 | 15585701052215 | Vincennes | Vincennes | Bare Steel / Plastic | 8610 | 9050 | 79 |  | 8711 | 9525 | 74 | 5757 | 0 | 5270 | [16 empty] | posted to CPR | CSIA Recoverable
S-1271 | 17585701052216 | Vincennes | Vincennes | Plastic | 5010 | 7146 | 85 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1351 | 19585401052212 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 13720 | 8272 | 5265 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | initiated | CSIA Recoverable
S-1352 | 19585401052213 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4535 | 6354 | 6395 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | initiated | CSIA Recoverable
S-1353 | 16585401052212 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 6030 | 6330 | 155 |  | 6271 | 6350 | 158 | 9621 | 0 | 8870 | [16 empty] | posted to CPR | CSIA Recoverable
S-1354 | 16585401052213 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 7690 | 7825 | 158 |  | 7513 | 7825 | 160 | 11477 | 0 | 11274 | [16 empty] | posted to CPR | CSIA Recoverable
S-1355 | 17585401052213 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4906 | 4025 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-1356 | 15585401052210 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 6945 | 7322 | 247 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | Excluded from CSIA
S-1358 | 16585401052215 | Evansville | Evansville | Cast Iron | 5332 | 4957 | 163 |  | 5034 | 4957 | 162 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1359 | 19585401052214 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 1547 | 3684 | 41 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1362 | 19585401052215 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4446 | 3044 | 66 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1366 | 17585401052214 | Evansville | Evansville | Cast Iron / Plastic | 4133 | 4851 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-1367 | 19585401052218 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4213 | 4775 | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | initiated | Excluded from CSIA
S-1370 | 19585401052225 | Evansville | Evansville | Bare Steel / Cast Iron | 5283 | 5356 | 107 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1371 | 18585401052213 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4184 | 2685 | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | Excluded from CSIA
S-1372 | 18585401052214 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 6361 | 5133 | 94 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | Excluded from CSIA
S-1373 | 16585401052219 | Evansville | Evansville | Cast Iron | 4099 | 4354 | 94 |  | 4104 | 4262 | 0 | 0 | 3 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1374 | 18585401052215 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4205 | 1939 | 48 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | Excluded from CSIA
S-1375 | 19585401052226 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 6614 | 8477 | 55 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1376 | 17585401052215 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 2972 | 4439 | 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-1377 | 17585401052216 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 3413 | 6298 | 51 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | Excluded from CSIA
S-1381 | 18585401052216 | Evansville | Evansville | Bare Steel / Cast Iron | 4860 | 4898 | 150 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1383 | 19585401052219 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 7230 | 7577 | 163 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1384 | 19585401052220 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 3808 | 3934 | 53 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | Excluded from CSIA
S-1491 | 13585401052212 | Evansville | Evansville | Bare Steel / Cast Iron | 6795 | 7315 | 111 |  | 6911 | 7315 | 99 | 5891 | 8 | 6258 | [16 empty] | posted to CPR | CSIA Recoverable
S-1492 | 13585401052213 | Evansville | Evansville | Bare Steel / Cast Iron | 9210 | 8355 | 151 |  | 8465 | 8355 | 116 | 6065 | 11 | 7479 | [16 empty] | posted to CPR | CSIA Recoverable
S-1535 | 14585701052218 | Vincennes | Vincennes | Bare Steel | 5780 | 6125 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-1560 | 13585401052217 | Evansville | Evansville | Cast Iron | 1570 | 1490 | 50 |  | 1600 | 1490 | 42 | 1670 | 4 | 1102 | [16 empty] | posted to CPR | Excluded from CSIA
S-1565 | 17585701052217 | Vincennes | Vincennes | Plastic | 2770 | 6008 | 23 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1742 | 14585501052210 | Evansville | Princeton | Bare Steel | 300 | 150 | 0 |  | 659 | 378 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1743 | 15585401052212 | Evansville | Evansville | Bare Steel / Cast Iron | 5258 | 7857 | 168 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-1853 | 14585401052212 | Evansville | Evansville | Bare Steel / Cast Iron | 3570 | 2265 | 51 |  | 3150 | 2265 | 41 | 2198 | 0 | 1835 | [16 empty] | posted to CPR | CSIA Recoverable
S-1912 | 14585701052222 | Washington | Washington | Bare Steel | 2565 | 2600 | 34 |  | 2768 | 2815 | 42 | 2160 | 0 | 1781 | [16 empty] | posted to CPR | CSIA Recoverable
S-1919 | 14585701052223 | Washington | Petersburg | Bare Steel | 260 | 260 | 2 |  | 249 | 249 | 2 | 0 | 0 | 4 | [16 empty] | posted to CPR | CSIA Recoverable
S-1928 | 14585701052224 | Vincennes | Vincennes | Bare Steel / Cast Iron / Plastic | 7505 | 6780 | 90 |  | 7443 | 6780 | 80 | 2855 | 1 | 3102 | [16 empty] | posted to CPR | CSIA Recoverable
S-1929 | 14585701052225 | Vincennes | Vincennes | Bare Steel | 5605 | 4470 | 77 |  | 5641 | 4470 | 65 | 2616 | 3 | 2934 | [16 empty] | posted to CPR | CSIA Recoverable
S-1932 | 16585501052213 | Fort Branch | Princeton | Bare Steel / Plastic | 3835 | 4193 | 44 |  | 3980 | 4441 | 45 | 2309 | 3 | 2420 | [16 empty] | posted to CPR | CSIA Recoverable
S-1982 | 17585701052218 | Washington | Vincennes | Bare Steel / Plastic | 3583 | 3832 | 48 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | Excluded from CSIA
S-2037 | 15585701052210 | Vincennes | Vincennes | Bare Steel / Plastic | 2518 | 2011 | 49 |  | 2913 | 2376 | 41 | 1702 | 11 | 2078 | [16 empty] | posted to CPR | CSIA Recoverable
S-2041 | 15585401052213 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 5818 | 6742 | 207 |  | 7159 | 6742 | 180 | 0 | 27 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2045 | 15585401052217 | Evansville | Evansville | Bare Steel / Cast Iron | 1175 | 800 | 6 |  | 1175 | 1000 | 4 | 312 | 0 | 324 | [16 empty] | posted to CPR | CSIA Recoverable
S-2078 | 15585401052228 | Evansville | Evansville | Bare Steel / Cast Iron | 750 | 998 | 2 |  | 750 | 998 | 2 | 291 | 0 | 293 | [16 empty] | posted to CPR | CSIA Recoverable
S-2079 [F] | 15585401052229 | Evansville | Evansville | Cast Iron | 0 | 1293 | 0 |  | 0 | 1293 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2080 | 16585401052210 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 2690 | 8071 | 107 |  | 2760 | 8081 | 103 | 5746 | 2 | 4646 | [16 empty] | posted to CPR | CSIA Recoverable
S-2085 | 19585401052221 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 7855 | 6593 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | initiated | Excluded from CSIA
S-2101 | 16585401052216 | Evansville | Evansville | Bare Steel / Cast Iron | 4199 | 3467 | 79 |  | 4087 | 3467 | 76 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2102 | 16585501052216 | Fort Branch | Princeton | Bare Steel / Plastic | 6258 | 5453 | 60 |  | 7128 | 6220 | 0 | 0 | 2 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2103 | 16585701052215 | Vincennes | Washington | Bare Steel / Plastic | 2203 | 2237 | 43 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2105 | 16585501052217 | Fort Branch | Princeton | Bare Steel / Plastic | 1658 | 1561 | 9 |  | 1892 | 1571 | 8 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2110 [F] | 16585401052214 | Evansville | Evansville | Cast Iron | 0 | 5178 | 0 |  | 0 | 5058 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2111 | 16585401052217 | Evansville | Evansville | Cast Iron | 1440 | 1703 | 26 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2132 | 16585701052217 | Vincennes | Washington | Bare Steel | 2470 | 3165 | 30 |  | 2841 | 3165 | 0 | 0 | 4 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2134 | 16585701052218 | Vincennes | Washington | Bare Steel / Plastic | 1677 | 2939 | 24 |  | 2058 | 2998 | 24 | 717 | 2 | 848 | [16 empty] | posted to CPR | CSIA Recoverable
S-2169 | 17585401052217 | Evansville | Evansville | Cast Iron / Plastic | 5445 | 5265 | 162 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2170 | 19585401052227 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 5424 | 5337 | 161 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open
S-2172 | 18585401052217 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 3374 | 3095 | 61 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-2173 | 18585401052218 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4521 | 4781 | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-2176 | 18585401052219 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4974 | 4611 | 76 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2177 | 18585401052220 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4817 | 4632 | 93 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2178 | 18585401052221 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 3938 | 3967 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2183 | 17585401052218 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 2135 | 4873 | 13 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2190 | 18585701052217 | Vincennes | Petersburg | Bare Steel / Plastic | 4583 | 4724 | 59 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2192 | 18585701052218 | Vincennes | Petersburg | Bare Steel / Plastic | 2015 | 2153 | 25 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2195 | 17585701052219 | Vincennes | Washington | Bare Steel / Plastic | 5083 | 4544 | 63 |  | 5146 | 4739 | 0 | 65 | 0 | 66 | [16 empty] | posted to CPR | CSIA Recoverable
S-2198 | 19585701052215 | Vincennes | Vincennes | Bare Steel / Plastic | 6645 | 5972 | 5665 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2200 | 17585701052220 | Vincennes | Vincennes | Plastic | 2385 | 2561 | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2285 | 19585401052229 | Evansville | Evansville | Bare Steel / Cast Iron | 5691 | 1476+4194 | 134 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2290 [F] | 17585401052212 | Evansville | Evansville | Cast Iron | 0 | 676 | 0 |  | 3919 | 4553 | 3 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2282 | 17585401052210 | Evansville | Evansville | Bare Steel / Cast Iron | 3630 | 3933 | 62 |  | 3919 | 4553 | 0 | 0 | 3 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2284 | 19585401052228 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4607 | 5207 | 137 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open
S-2297 | 18585701052219 | Vincennes | Vincennes | Bare Steel / Plastic | 3930 | 5932 | 33 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2302 | 19585701052216 | Vincennes | Vincennes | Bare Steel / Plastic | 855 | 7683 | 5780 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open
S-2315 | 17585501052210 | Fort Branch | Princeton | Bare Steel | 3624 | 4414 | 48 |  | 4277 | 4428 | 5 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2347 | 17585701052221 | Vincennes | Washington | Bare Steel / Plastic | 8771 | 5367 | 81 |  | 5652 | 5369 | 0 | 84 | 0 | 85 | [16 empty] | posted to CPR | CSIA Recoverable
S-2372 | 17585701052222 | Vincennes | Vincennes | Plastic | 0 | 3057 | 185 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2373 | 17585701052223 | Vincennes | Vincennes | Plastic | 6540 | 5223 | 114 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2386 | 17585701052224 | Vincennes | Washington | Bare Steel / Plastic | 2845 | 3330 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2395 | 17585401052219 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 7252 | 7415 | 61 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2407 | 17585401052220 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 5735 | 7897 | 25 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2408 | 17585401052221 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 4620 | 6296 | 103 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-2409 | 17585401052222 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 2771 | 3819 | 68 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2416 | 17585401052011 | Evansville | Evansville | Cast Iron | 0 | 125 | 0 |  | 0 | 150 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2420 [F] | 17585401052225 | Evansville | Evansville | Cast Iron | 0 | 2878 | 0 |  | 0 | 2270 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2422 | 17585701052226 | Vincennes | Vincennes | Bare Steel | 0 | 206 | 1 |  | 0 | 205 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2435 | 18585701052210 | Vincennes | Vincennes | Bare Steel / Plastic | 1301 | 914 | 3 |  | 1226 | 879 | 4 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2440 | 18585401052210 | Evansville | Evansville | Cast Iron | 250 | 250 | 0 |  | 0 | 150 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2446 | 18585401052212 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 7120 | 10135 | 0 |  | 7203 | 10135 | 0 | 0 | 1 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2452 | 18585701052220 | Vincennes | Vincennes | Bare Steel / Plastic | 2830 | 4012 | 47 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2464 | 18585701052222 | Vincennes | Petersburg | Bare Steel / Plastic | 5212 | 4711 | 44 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-2465 | 18585701052223 | Vincennes | Petersburg | Bare Steel / Plastic | 1595 | 1618 | 11 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-2466 | 18585701052224 | Vincennes | Petersburg | Bare Steel / Plastic | 1138 | 1869 | 21 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | in service | CSIA Recoverable
S-2467 | 18585701052225 | Vincennes | Loogootee | Bare Steel / Plastic | 5930 | 6300 | 65 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2473 | 19585701052217 | Vincennes | Bicknell | Bare Steel / Plastic | 5700 | 6021 | 66 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
S-2484 | 19585401052210 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 684 | 650 | 12 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | posted to CPR | CSIA Recoverable
S-2488 | 19585701052210 | Vincennes | Vincennes | Bare Steel | 378 | 817 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | completed | CSIA Recoverable
S-2498 | 19585401052230 | Evansville | Evansville | Bare Steel / Cast Iron | 3280 | 4272 | 72 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
2499 | 19585401052222 | Evansville | Evansville | Bare Steel / Cast Iron / Plastic | 6956 | 5656 | 146 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | initiated | CSIA Recoverable
S-2528 | 20585701052210 | Vincennes | Evansville | Bare Steel / Cast Iron / Plastic | 1544 | 1728 | 47 |  | 0 | 0 | 0 | 0 | 0 | 0 | [16 empty] | open | CSIA Recoverable
|  |  |  | TOTALS | 1174179 | 1292441 | 47246 | 0
|  |  |  | TOTALS - COMPLETED / IN-SERVICE | 140105 | 160994 | 1995 | 0 | 829598 | 887489 | 10524 | 547623 | 454 | 555143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[A] Represents only Investment Costs on Projects In Service prior to December 31, 2020, excludes Removal Costs. Negative activity represents corrections posted to the work order during the trailing charge period.
[B] "Open" - Project is currently active and receiving charges, not yet in-service or complete, and not yet depreciating or receiving Post In-Service AFUDC accounting treatment.
"Initiated" - Project is included in the current year plan and is currently awaiting approval.
"Suspended" - Project engineering and planning has been performed. Project status will change to "Open" when construction begins.
"In-Service" - Project is depreciating (deferred) and is receiving Post In-Service AFUDC. Project is not unitized as final as-built is pending; preliminary footage data has been provided (above), if available.
"Complete" - Project is depreciating (deferred) and is receiving Post In-Service AFUDC.
[C] Services Retired represents services retired and not replaced.
[D] Service line footage retired represents the feet of service retired due to a retired or replaced service line.
[E] Services replaced represents the number of services that remain active after the project has been completed. The total count represents the number of steel services replaced + the number of tie-ins of existing plastic services.
[F] Retirement only work order, which only included removal expenses; therefore, no costs are reflected above for this work order.
[G] Main retirement footages may be higer or lower than installed footage. This is attributable to dual mains being replaced with single main, or single main replaced with dual mains, service tie-overs where high pressure mains existed, proximity of existing high pressure mains to customer base and reduced customer base in some areas.
[H] Work orders labeled "CSIA Recoverable" consist of bare steel cast iron replacement work orders that are now eligible for recovery via the CSIA order granted in 2014. CSIA eligible work orders are those that had a zero CWIP balance or had not broken ground on January 1, 2014. Work orders labeled "Excluded from CSIA" are not eligible and will continue to follow the BSCI replacement program.

## SAH-9 (Public)
CEI South
2022-2026 TDSIC Plan
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
N/A | 18540971 | 21585701G61210 | PUBLIC IMPROVEMENT - DIST | SW | BICKNELL | IN BICKNELL-SR 67-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 500' OF 2" PE MAIN DUE TO ROAD & DRAINAGE IMPROVEMENT PROJECT | 2022
N/A | 18540992 | 21585701G61212 | PUBLIC IMPROVEMENT - DIST | SW | VINCENNES | IN-WASHINGTON-WASHINGTON AVE FROM EMISON AVE TO BELLE CROSSING-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 5,100' OF 6", 4", & 2" PE MAIN AND REPLACE APPROXIMATELY 40 SERVICES FOR ROAD RECONSTRUCTION PROJECT. | 2022
N/A | 18541013 | 21585501G61210 | PUBLIC IMPROVEMENT - DIST | SW | MT VERNON | IN-MT VERNON-WESTERN BYPASS ROAD FROM HWY 62 TO NORTH POSEY COUNTY-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 600' OF 4" & 2" PE MAIN DUE TO NEW ROAD CONSTRUCTION PROJECT. | 2022
N/A | 18541051 | 21585501G61212 | PUBLIC IMPROVEMENT - DIST | SW | MT VERNON | IN-MT VERNON-SR 62 & PORT ROAD-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 200' OF 6" STL MAIN DUE TO NEW DRAINAGE IMPROVEMENT PROJECT. | 2022
N/A | 16700672 | 21585401G61215 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-BOONVILLE NEW HARMONY RD FROM PETERSBURG RD TO HWY 57-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 5,000' OF 4" PE MAIN AND REPLACE APPROXIMATELY 40 SERVICES DUE TO ROAD RECONSTRUCTION PROJECT. | 2022
N/A | 18540796 | 21585401G61210 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-WALNUT STREET (PHASE 2) FROM MARTIN LUTHER KING BLVD TO HWY 41-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 4,200' OF 4" & 2" PE MAIN AND REPLACE APPROXIMATELY 20 SERVICES DUE TO ROAD RECONSTRUCTION PROJECT. | 2022
N/A | 18540873 | 21585401G61218 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-WALNUT STREET (PHASE 3) FROM WEINBACH AVENUE TO VANN AVENUE-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 4,800' OF 8", 6", 4", & 2" PE MAIN AND REPLACE APPROXIMATELY 14 SERVICES DUE TO ROAD RECONSTRUCTION PROJECT. | 2022
N/A | 18559619 | 21585701G61216 | PUBLIC IMPROVEMENT - DIST | SW | WASHINGTON | IN-WASHINGTON-HIGHWAY 550 FROM STATE STREET TO SE 3RD STREET-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 7,300' OF 4" & 2" PE MAIN AND 1,000' OF 6" STL MAIN AND REPLACE APPROXIMATELY 31 SERVICES DUE TO ROAD RECONSTRUCTION. | 2022
N/A | N/A | TBD | RURAL EXTENSION | SW | MULTIPLE | RURAL EXTENSION | 2022
S-XA-12109 | 17993513 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | NEWBURGH | Remove 2” Bottleneck on Oak Grove Rd. (Newburgh):Install approximately 3700’ of 6” PE main on Oak Grove from just east of Oak Trails to Anderson to increase system pressure for residential development | 2022
S-XA-12110 | 13060089 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | FRANCISCO | IN-FRANCISCO-STATE ROAD 64 & CR 725 E: INSTALL ~4000' OF MP PE GAS MAIN ON CR 725 & E SR 64 TO FEED CUSTOMERS FED OFF EXISTING REGULATOR STATION (STA #: 315). If Texas Gas had to shut down the transmission line for any reason customers would lose gas service. In order to correct this situation, we must run a gas main extension along SR 64 and transfer the services to the new gas main. | 2022
S-XA-12111 | 17993404 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | MONROE CITY | Rebuild Station V-04 at Hart Street Station so that valves are far enough from the regulators so taps to check upstream, downstream, and for lockup pressure. Enhanced station and system operation and safety. | 2022
S-XA-12112 | 18471423 | 21585601051210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | NEWBURGH | Rebuild RS-164 (Newburgh):Replace existing 399 Regulators with dual run worker/monitor EZRs with 161EB pilots. Increased flow/pressure to Newburgh system for residential development. | 2022
SWTDSIC01 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | MIDWAY | Midway - Full Emergency Shutdown System to enhance safety of storage field. | 2022
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | SW | MULTIPLE | TARGETED ECONOMIC DEVELOPMENT | 2022
N/A | 18540975 | 21585401G61212 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-BOONVILLE NEW HARMONY ROAD AT BRIDGE EAST OF BENDER ROAD AND WEST OF ST JOE AVENUE-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 580' OF 4" & 2" PE MAIN DUE TO NEW BRIDGE RECONSTRUCTION PROJECT. | 2023
N/A | 18540996 | 21585701G61213 | PUBLIC IMPROVEMENT - DIST | SW | VINCENNES | IN-VINCENNES-ELKHORN ROAD & HWY 41 INTERSECTION-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 500' OF 4" PE MAIN DUE TO INTERSECTION IMPROVEMENT PROJECT. | 2023
N/A | 16700702 | 21585401G61217 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-OAK HILL ROAD (PHASE 2) FROM LYNCH ROAD TO EASTWOOD DRIVE-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 10,000' OF 6", 4", & 2" PE MAIN AND REPLACE APPROXIMATELY 70 SERVICES DUE TO ROAD RECONSTRUCTION PROJECT. | 2023
N/A | 16388095 | 21585401G61219 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-OAK HILL ROAD (PHASE 1) FROM EASTWOOD DRIVE TO MILLERSBURG ROAD-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 5,450' OF 6" & 2" PE MAIN AND REPLACE APPROXIMATELY 45 SERVICES DUE TO ROAD RECONSTRUCTION PROJECT. | 2023
N/A | 18540981 | 21585601G61210 | PUBLIC IMPROVEMENT - DIST | SW | NEWBURGH | IN-EVANSVILLE-TELEPHONE ROAD FROM BELL ROAD TO FUQUAY ROAD-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 6,100' OF 6" & 2" PE MAIN AND REPLACE APPROXIMATELY 40 SERVICES DUE TO RECONSTRUCTION PROJECT. | 2023
N/A | 18541018 | 21585401G61214 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-MULTIPLE INTERSECTIONS ALONG LLOYD EXPRESSWAY-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 400' OF 6", 4", & 2" PE MAIN DUE TO INTERSECTION IMPROVEMENT PROJECT. | 2023
N/A | N/A | TBD | RURAL EXTENSION | SW | MULTIPLE | RURAL EXTENSION | 2023
S-XA-12107 | 18471421 | 21585701051212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | WASHINGTON | Improve Pressure and Capacity on Vincennes/Washington HPD:Install approximately 3900’ of 12” steel main. | 2023
S-XA-12108 | 8103475 | 21585501051210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | MOUNT VERNON | IN-MOUNT VERNON-GREENBRIAR RD-GREENBRIAR ROAD REG STATION-UPRATE. Install 1500 and tie over 15 SVC. Replace the existing main on Greenbriar Road, retire RS 336 and test the new gas main to the current MAOP of 60 PSIG test standard. | 2023
SWTDSIC02 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | OLIVER - STAUNTON | OLP #2 Drill vertical well for withdrawal purposes only west of OLP-056 Travers#03. Enhanced storage field reliability | 2023
SWTDSIC03 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | OLIVER - STAUNTON | OLP #1 Drill vertical well for withdrawal purposes only west of OLP-056 Travers#03 . Enhanced storage field reliability | 2023
SWTDSIC04 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | OLIVER - SEBREE | OLP OSS#1 Drill new vertical injection/withdrawal well in Sebree Formation (~550') Enhanced storage field reliability and capacity | 2023
SWTDSIC05 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | OLIVER - SEBREE | OLP OSS#2 Drill new vertical injection/withdrawal well in Sebree Formation (~550') Enhanced storage field reliability and capacity | 2023
SWTDSIC06 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | OLIVER - SEBREE | OLP OSS#3 Drill new vertical injection/withdrawal well in Sebree Formation (~550') Enhanced storage field reliability and capacity | 2023
SWTDSIC07 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | MONROE CITY | Install 2 stage compression and PLC for flow into TGT &MWG utilize current drivers and building. | 2023
5087 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- TRANS | SW Underground Gas Storage | MIDWAY | Reroute station piping at Midway Storage Field to allow compression out of field for increased reliability during peak winter withdrawals. | 2023
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | SW | MULTIPLE | TARGETED ECONOMIC DEVELOPMENT | 2023
N/A | 15944624 | 21585401G61216 | PUBLIC IMPROVEMENT - DIST | SW | EVANSVILLE | IN-EVANSVILLE-BASELINE ROAD (PHASE 2) FROM KORFF ROAD TO OLD STATE ROAD-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 2,300' OF 4" PE MAIN DUE TO ROAD RECONSTRUCTION PROJECT. | 2024
N/A | N/A | TBD | RURAL EXTENSION | SW | MULTIPLE | RURAL EXTENSION | 2024
S-XA-12087 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | VINCENNES | Install 3,000' of 2" PE gas main on HWY 50 from Reg Station W-33 to county road 450 to remove 30 farm taps | 2024
S-XA-12094 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | EVANSVILLE | Replace ~3,200 of 4" MPD main from Lemay to the USI take off with 6" PE. Gain 10# on the inlet to USI. | 2024
S-XA-12088 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | CANNELBURG | IN-CANNELBURG-US 50: EXTEND 2" MP MDPE GAS DIST MAIN ~850' ALONG US 50 TO ELIMINATE USE OF HIGH PRESSURE SERVICES TO SURROUNDING HOUSES. RETIRE FARM TAPS ALONG MAIN EXTENSION AND INSTALL NEW SERVICE TO HOMES EFFECTED. | 2024
S-XA-12089 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | ELBERFELD | IN-ELBERFELD-BROWN ST-RETIRE FARM TAPS: RETIRE 3 FARM TAPS THAT ARE TAPPED OFF TGT LINES NEAR THE WEST END OF BROWN ST. TO MITIGATE SAFETY RISK ASSOCIATED WITH DAMAGE TO THE TAPS. | 2024
SWTDSIC08 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | MIDWAY | Install compression at Midway Station. Backup compressor to ensure injection and withdrawal reliability for peak demand periods. Existing compressor is 1966 vintage | 2024
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | SW | MULTIPLE | TARGETED ECONOMIC DEVELOPMENT | 2024
N/A | N/A | TBD | RURAL EXTENSION | SW | MULTIPLE | RURAL EXTENSION | 2025
S-XA-12096 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | FT BRANCH | Install 1 mile of 4/6" HPD main from SR 68 to the North Warrick Industrial Park and regulator station. Provide high volume gas supply to the North Warrick Industrial Park area. | 2025
S-XA-12090 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | VINCENNES | Replace ~2,700' of 2" MP main with 4" PE MP main on Old US 41.Remove 2 existing bottlenecks and create additional 4" feed to the Vincennes Industrial Park to support development. | 2025
S-XA-12091 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | WASHINGTON | Replace ~250' of 4" MP main with 6" PE MP main on State from SE 15th to Hillside. Remove existing bottleneck in major 6" feed to Washington system for enhanced reliability. | 2025
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | SW | MULTIPLE | TARGETED ECONOMIC DEVELOPMENT | 2025
N/A | N/A | TBD | RURAL EXTENSION | SW | MULTIPLE | RURAL EXTENSION | 2026
S-XA-12093 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SW | FORT BRANCH | Replace ~1,600' of 2" HPD main from E. Gibson to Maple with 4" steel. Gain 35# on the inlet to RS-194 (Fort Branch) for Ft. Branch system reliability improvement. | 2026
SWTDSIC09 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SW | MONROE CITY | Run new transmission line from Staunton formation wells to main facility. | 2026
S-XA-12095 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- TRANS | SW | EVANSVILLE | Evansville VIP to US41 pipeline - Install 4.75 miles of 8" HPD main from VIP north to Baseline Rd and west to US 41 250/385-psig system and regulator station. This improvement will provide support to the Highway 41 HP system and also the Vanderburgh Industrial Park area MP system. | 2026
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | SW | MULTIPLE | TARGETED ECONOMIC DEVELOPMENT | 2026