## Cover Page
Indiana Michigan Power Company
Cause No. 44871 ECR 4
Pifer Workpaper

## Attachment FRP-1
Rockport Unit 2 SCR Project Actual Costs Incurred During Historical Period and Planned Expenditures for Forecast Period
| Rockport U2 I&M1 Direct Ownership Share | Rockport U2 AEG1 Ownership Share | Total Rockport Plant
Historical Period Project Cost2 | 98254473.45 | 98254238.25 | 196508711.7
Historical Period AFUDC2,3,5 | 3181719.8 | 7306706.48 | 10488426.28
Historical Period Total Cost Including AFUDC | 101436193.25 | 105560944.73 | 206997137.98
Forecast April 2020 thru December 2020 Project Cost | 13106596.1167 | 13106596.1167 | 26213192.2334
Forecast April 2020 thru December 2020 AFUDC3,5 | 803511.5206 | 803511.5206 | 1607023.0411
Forecast April 2020 thru December 2020 Total Project Cost Including AFUDC | 13910107.6372 | 13910107.6372 | 27820215.2745
Forecast Period Estimated Project Cost4 | 1087450 | 1087450 | 2174900
Forecast Period Estimated AFUDC3,5
Forecast Period Estimated Total Project Cost Including AFUDC | 1087450 | 1087450 | 2174900
Estimated Project Total Cost6 | 112448519.5667 | 112448284.3667 | 224896803.9334
Estimated Total AFUDC3,5,6 | 3985231.3206 | 8110218.0006 | 12095449.3211
Estimated Project Total Cost Including AFUDC | 116433750.8872 | 120558502.3672 | 236992253.2545
1 - Total Cost for Rockport I&M & AEG projects is estimated at a 50% split
2 - Historical Period represents costs incurred through March 31, 2020
3 - Allowance for Funds Used During Construction (AFUDC)
4 - Forecast Period from January 1, 2021 through December 31, 2021
5 - For I&M's direct ownership share, effective January 2015, I&M records AFUDC on 100% of the FERC jurisdictional component
6 - Through end of Project (December 31, 2021)

## Attachment FRP-2
Rockport Unit 2 SCR Project Total Rockport Plant Estimated Capital Costs, Excluding AFUDC
| Phase II | Phase III | EAC | Delta (EAC vs Phase III)
SCR | 216332024 | 192152241.7596 | 192152241.7596 | 0
Subtotal - Direct Construction Cost | 216332024 | 192152241.7596 | 192152241.7596 | 0
PME&C | 15600000 | 13671842 | 13671842 | 0
Subtotal | 231932024 | 205824083.7596 | 205824083.7596 | 0
Risk Allocation* | 12605111 | 2000000 | 2000000 | 0
Total | 244537135 | 207824083.7596 | 207824083.7596 | 0
AEP Overhead Allocations | 16202679 | 17072720 | 17072720 | 0
Grand Total | 260739814 | 224896803.7596 | 224896803.7596 | 0
* Phase II Risk = 5.43% @ P90
* Phase III Risk = 5.27% @ P90
* EAC includes Actuals thru March 31, 2020
EAC = Estimate at Completion
SCR = Selective Catalytic Reduction
PME&C = Project Management, Engineering & Construction Management
AFUDC is not included in the values above.

## Attachment FRP-3
Total Rockport Plant Forecast Period1 Consumables and Environmental Allowance Expenses
Total I&M Share
Environmental Allowances | 429000
Anhydrous Ammonia | 575906.7047
Sodium Bicarbonate | 14883381.3492
Activated Carbon | 1831533.0815
Estimated Total2 | 17719821.1354
1 - Forecast Period is January 1, 2021 through December 31, 2021.
2 - I&M's Share of Total Rockport Plant Consumables and Environmental Allowance Expenses.

## Consumables
Monthly Consumption - Prepared by Jason Echelbarger - Snapshot ID#436 - Based on Current Operational Forecast as of 5/19/2020
RP Unit 1 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | Total
Activated Carbon (Total Dollars) | 308361.344 | 170279.7697 | 272688.8414 | 134850.69 | 0 | 148003.8188 | 270030.554 | 221323.8678 | 60122.6615 | 0 | 0 | 230199.1179 | 1815860.6652
Anhydrous Ammonia (Total Dollars) | 96961.0471 | 53542.719 | 85744.1963 | 42402.4099 | 0 | 46538.2757 | 84908.3252 | 69593.0096 | 18904.9514 | 0 | 0 | 72383.7406 | 570978.6749
Sodium Bicarbonate (Total Dollars) | 2505802.1184 | 1383725.3472 | 2215920.672 | 1095822 | 0 | 1202706.792 | 2194318.9296 | 1798519.2624 | 488568.024 | 0 | 0 | 1870641.2088 | 14756024.3544
RP Unit 2 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
Activated Carbon (Total Dollars) | 270416.4344 | 135619.6847 | 206060.1528 | 101988.6142 | 1114.7657 | 109249.8052 | 237573.7218 | 203787.7458 | 115598.1607 | 90338.8976 | 149331.5795 | 226125.9355 | 1847205.4979
Anhydrous Ammonia (Total Dollars) | 85029.6613 | 42644.2124 | 64793.4917 | 32069.2688 | 350.5266 | 34352.4755 | 74702.6088 | 64078.9568 | 36348.6505 | 28406.1355 | 46955.7764 | 71102.9703 | 580834.7345
Sodium Bicarbonate (Total Dollars) | 2197454.6664 | 1102070.9952 | 1674483.4512 | 828778.608 | 9058.7952 | 887784.408 | 1930568.6232 | 1656017.4456 | 939372.336 | 734110.8264 | 1213496.424 | 1837541.7648 | 15010738.344
Total | 5464025.2717 | 2887882.7282 | 4519690.8055 | 2235911.5909 | 10524.0875 | 2428635.5752 | 4792102.7625 | 4013320.2881 | 1658914.784 | 852855.8595 | 1409783.7799 | 4307994.7379 | 34581642.2709
| 2021-01-01: Amount provided in testimony pg. 9; 2021-12-01: I&M's 50% Share | 17290821.1354
Amount providedin FRP-3
| 2021-10-01: I&M's Share of; 2021-11-01: Emissions Allowance Costs | 429000
| 2021-10-01: I&M's Share of; 2021-11-01: Total Emissions and Consumables | 17719821.1354

## Emissions Allowances
From: Todd A March <tamarch@aep.com>
Sent: Friday, May 22, 2020 9:10 AM
To: Tara D Beske <tdbeske@aep.com>
Cc: Scott Weaver <saweaver@aep.com>; Jeffrey D Clark <jdclark2@aep.com>; David J Long <djlong@aep.com>
Subject: RE: Rockport Plant Emission Allowances - 2021 Forecast
Tara,
Our last forecast shows the following costs of environmental compliance for I&M for calendar year 2021. We did not anticipate the need to buy any allowances for compliance in 2021. Our expense occurs when we have emissions and subsequently surrender allowances that have a book value. The only I&M allowances with a book value in the last forecast were Title IV SO2 and CSAPR OSNX.
Title IV
SO2 $857,000
CSAPR
SO2-1 $0
ANNx $0
OSNx $1,000
Gain or offsets come from the sale of excess allowances. In the last forecast we estimated I&M would sell 1,000 OSNx allowances at $50. So offsets are estimated to be $50,000.
If you have questions, let me know.
TODD A MARCH ¦ ENVIRONMENTAL SPEC CONSULT
TAMARCH@AEP.COM ¦ A:8.200.6263 ¦ C:614.743.3951
1 RIVERSIDE PLAZA, COLUMBUS, OH 43215
From: Todd A March <tamarch@aep.com>
Sent: Thursday, May 21, 2020 11:23 AM
To: Tara D Beske <tdbeske@aep.com>
Cc: Jeffrey D Clark <jdclark2@aep.com>; David J Long <djlong@aep.com>; Scott Weaver <saweaver@aep.com>
Subject: Rockport Plant Emission Allowances - 2021 Forecast
Tara, Per your request, below are the 2021 Rockport total plant allowance allocations and forecasted emissions.
2021 CSAPR Allowance Allocations for Rockport Plant (CSAPR unit allocations are less than the unit budgets due to a small holdback for new sources. Any of the hold backs not used are returned to their assigned units. There are typically reissued allowances in each of the CSAPR programs but there are no guarantees there will be any in a given year. No reissuance allowances are shown in the quantity below. In 2019 AEP received 728 SO2, 377 ANNx and 73 OSNx allowances).
SO2-1 31,021
ANNx 19,660
OSNx 3,791
2021 Title IV Allowance Allocations for Rockport Plant
SO2 66,122
2021 Forecasted Emissions for Rockport Plant , Total Plant (tons, based on Q120_East 2021_BU_2114 Sources v10e forecast dated April 6, 2020)
SO2 5,684 (SO2 emissions consume from both the CSAPR and Title IV programs)
ANNx 3,327
OSNx 1,258
If there are questions, let me know.
TODD A MARCH ¦ ENVIRONMENTAL SPEC CONSULT
TAMARCH@AEP.COM ¦ A:8.200.6263 ¦ C:614.743.3951
1 RIVERSIDE PLAZA, COLUMBUS, OH 43215

## Decker Input - Project Capital
[30 empty] | Forecast April 2019 thru Sept 2019 | [5 empty] | Forecast Oct 2019 thru DEC 2020
|  | Through 2016 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | Historical Period Totals | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | Forecast Through End of Project Total | Project Total (Actuals + Forecast) | Forecast April 1, 2018 thru Sept 30, 2019 | Forecast Oct1,2019 thru Aug. 20120 | Project Total (Actuals + Forecast thru Sept 2019 + Forecast Oct 2019 thru Aug. 2020.
U2 Cashflow
SCR | Controllable (I&M) | 1002742 | 243791 | 261034 | 518272 | 649462 | 846318 | 781123 | 1426201 | 965676 | 1102977 | 1618593 | 779069 | 578919 | 507544 | 636233 | 553405 | 529363.79 | 4573294.22 | 2678814.11 | 1046838.3 | 1596018.38 | 1756410.77 | 4798512.95 | 4443680.7 | 5622553.32 | 3047568.44 | 1525267.98 | 5020592.65 | 6492050.38 | 6109252.52 | 3662809.27 | 4118104.58 | 3219217.04 | 3714211.21 | 5529008.45 | 2647732.794 | 1749196.264 | 1637158.35 | 3990309.36 | 1756071.1 | 93735395.928 | 2140751.705 | 3257907.0665 | 2108967.085 | 2159068.5 | 1201329 | 668576.5 | 389927 | 161184 | 42714.695 | 1000000 | 13130425.5515 | 106865821.4795 | 27315645 | 121912895.6025 | 242963936.5305
SCR | Controllable (AEG) | 875480 | 199381 | 206532 | 434540 | 580166 | 777054 | 701526 | 1360287 | 892566 | 968252 | 1513799 | 699522 | 491620 | 446027 | 548150 | 430514 | 430030.03 | 4461359.29 | 2543510.79 | 923403.8 | 1380857.99 | 1613698.93 | 4643199.1 | 4291033.58 | 5457465.1 | 2926483.74 | 1364835.61 | 4766121.5 | 6313997.53 | 5941479.6 | 3539073.87 | 3961716.47 | 2927801.94 | 3421235.29 | 5412232.84 | 2398949.25 | 1496696.17 | 1246629.32 | 3519974.54 | 1720636.05 | 87827838.33 | 2140751.705 | 3257907.0665 | 2108967.085 | 2159068.5 | 1201329 | 668576.5 | 389927 | 161184 | 42714.695 | 1000000 | 13130425.5515 | 100958263.8815 | 26105304.7 | 114490979.8565 | 228424122.8865
SCR | Allocations (I&M) | 11788 | 27201 | 6022 | -731 | -2505 | 9045 | 32204 | 24718 | 58426 | 223171 | 53482 | 172440 | 121741 | 132063 | 120781 | 159791 | 143379.25 | 119785.29 | 164132.98 | 169880.94 | 109429.55 | 119700.45 | 136377.58 | 122629.74 | -25848.84 | 266512.75 | 139897.28 | 130774.65 | 148189.45 | 128384.74 | 153740.28 | 167792.48 | 195330.69 | 103235.95 | 299726.24 | 188379.47 | 235366.73 | -36983.49 | 5228.58 | 184400.07 | 4519079.81 | 100592.81 | 284724.473 | 186589.4489 | 188810.5403 | 105056.2211 | 58467.0149 | 34099.1162 | 14095.5408 | 3735.4001 | 87450 | 1063620.5652 | 5582700.3752 | 896673.59 | 6260970.9033 | 11676724.3033
SCR | Allocations (AEG) | 139050 | 71612 | 60524 | 83001 | 66791 | 78310 | 111800 | 90633 | 131536 | 357896 | 158275 | 251988 | 209040 | 193579 | 208864 | 282682 | 242713.29 | 231720.58 | 299436.75 | 293315.87 | 324590.27 | 262412.71 | 291691.85 | 275277.24 | 139239.91 | 387597.88 | 300330.04 | 385246.36 | 326242.81 | 296158.09 | 277476.35 | 324181.29 | 486746.44 | 396212.37 | 416502.6 | 437163.52 | 487616.84 | 353546 | 475563.85 | 219835.5 | 10426399.41 | 100592.81 | 284724.473 | 186589.4489 | 188810.5403 | 105056.2211 | 58467.0149 | 34099.1162 | 14095.5408 | 3735.4001 | 87450 | 1063620.5652 | 11490019.9752 | 2107017.35 | 13682401.2133 | 26215817.9733 | 224896805.7114
SCR | AFUDC (I&M) | 4301 | 3344 | 4231 | 5396 | 6127 | 8667 | 11797 | 12173 | 22784 | 28504 | 35725 | 42564 | 43527 | 43954 | 49957 | 50669 | 54771.14 | 57680.35 | 95640.07 | 116190.49 | 131265.13 | 139916.66 | 154428.28 | -41815.02 | 65113.54 | 74776.76 | 82565.08 | 90459.01 | 96160.95 | 106184.63 | 116137.52 | 119380.52 | 126436.67 | 137252.64 | 141031.07 | 357140.01 | 153866.88 | 133606.97 | 143868.34 | 155941.97 | 3181719.66 | 332531.165 | 470980.3556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803511.5206 | 3985231.1806 | 701552.93 | 5070686.4206 | 8953959.0106
SCR | AFUDC (AEG) | 591 | 2569 | 5111 | 6652 | 5142 | 9789 | 12502 | 12793 | 15547 | 6819 | 8872 | 21889 | 47032 | 16083 | 28168 | 51946 | 72381.12 | 84017.18 | 91626.31 | 62669.89 | 84072.33 | 136401.22 | 155017.17 | 176547.33 | 199158.07 | 219123.14 | 250079.53 | 264508.19 | 291111.7 | 325311.75 | 352816.37 | 391007.32 | 365550.68 | 364868.09 | 479327.04 | 510108.84 | 532075.11 | 543360.22 | 546487.35 | 557574.94 | 7306705.89 | 332531.165 | 470980.3556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803511.5206 | 8110217.4106 | 2090665.91 | 11279150.9106 | 20676522.7106
SCR | Total | 2033952 | 547898 | 543454 | 1047130 | 1305183 | 1729183 | 1650952 | 2926805 | 2086535 | 2687619 | 3388746 | 1967472 | 1491879 | 1339250 | 1592153 | 1529007 | 1472638.62 | 9527856.91 | 5873161.01 | 2612299.29 | 3626233.65 | 4028540.74 | 10179226.93 | 9267353.57 | 11457681.1 | 6922062.71 | 3662975.52 | 10657702.36 | 13667752.82 | 12906771.33 | 8102053.66 | 9082182.66 | 7321083.46 | 8137015.55 | 12277828.24 | 6539473.884 | 4654817.994 | 3877317.37 | 8681432.02 | 4594459.63 | 206997139.028 | 5147751.36 | 8027223.79 | 4591113.0679 | 4695758.0806 | 2612770.4421 | 1454087.0299 | 848052.2323 | 350559.0816 | 92900.1902 | 2174900 | 29995115.2745 | 236992254.3025 | 59216859.48 | 272697084.9066 | 538911083.4146
SCR
Total RP U2 Cashflow SCR |  | 2033952 | 547898 | 543454 | 1047130 | 1305183 | 1729183 | 1650952 | 2926805 | 2086535 | 2687619 | 3388746 | 1967472 | 1491879 | 1339250 | 1592153 | 1529007 | 1472638.62 | 9527856.91 | 5873161.01 | 2612299.29 | 3626233.65 | 4028540.74 | 10179226.93 | 9267353.57 | 11457681.1 | 6922062.71 | 3662975.52 | 10657702.36 | 13667752.82 | 12906771.33 | 8102053.66 | 9082182.66 | 7321083.46 | 8137015.55 | 12277828.24 | 6539473.884 | 4654817.994 | 3877317.37 | 8681432.02 | 4594459.63 | 206997139.028 | 5147751.36 | 8027223.79 | 4591113.0679 | 4695758.0806 | 2612770.4421 | 1454087.0299 | 848052.2323 | 350559.0816 | 92900.1902 | 2174900 | 29995115.2745 | 236992254.3025 | 59216859.48 | 272697084.9066 | 538911083.4146
U2 CWIP (I&M)
SCR | CWIP Controllable (I&M) | 1002742 | 243791 | 261034 | 518272 | 649462 | 846318 | 781123 | 1426201 | 965676 | 1102977 | 1618593 | 779069 | 578919 | 507544 | 636233 | 553405 | 529363.79 | 4573294.22 | 2678814.11 | 1046838.3 | 1596018.38 | 1756410.77 | 4798512.95 | 4443680.7 | 5622553.32 | 3047568.44 | 1525267.98 | 5020592.65 | 6492050.38 | 6109252.52 | 3662809.27 | 4118104.58 | 3219217.04 | 3714211.21 | 5529008.45 | 2647732.794 | 1749196.264 | 1637158.35 | 3990309.36 | 1756071.1 | 93735395.928 | 2140751.705 | 3257907.0665 | 2108967.085 | 2159068.5 | 1201329 | 668576.5 | 389927 | 161184 | 42714.695 | 1000000 | 13130425.5515 | 106865821.4795 | 27315645 | 121912895.6025 | 242963936.5305
SCR | Allocations (I&M) | 11788 | 27201 | 6022 | -731 | -2505 | 9045 | 32204 | 24718 | 58426 | 223171 | 53482 | 172440 | 121741 | 132063 | 120781 | 159791 | 143379.25 | 119785.29 | 164132.98 | 169880.94 | 109429.55 | 119700.45 | 136377.58 | 122629.74 | -25848.84 | 266512.75 | 139897.28 | 130774.65 | 148189.45 | 128384.74 | 153740.28 | 167792.48 | 195330.69 | 103235.95 | 299726.24 | 188379.47 | 235366.73 | -36983.49 | 5228.58 | 184400.07 | 4519079.81 | 100592.81 | 284724.473 | 186589.4489 | 188810.5403 | 105056.2211 | 58467.0149 | 34099.1162 | 14095.5408 | 3735.4001 | 87450 | 1063620.5652 | 5582700.3752 | 896673.59 | 6260970.9033 | 11676724.3033
SCR | AFUDC (I&M) | 4301 | 3344 | 4231 | 5396 | 6127 | 8667 | 11797 | 12173 | 22784 | 28504 | 35725 | 42564 | 43527 | 43954 | 49957 | 50669 | 54771.14 | 57680.35 | 95640.07 | 116190.49 | 131265.13 | 139916.66 | 154428.28 | -41815.02 | 65113.54 | 74776.76 | 82565.08 | 90459.01 | 96160.95 | 106184.63 | 116137.52 | 119380.52 | 126436.67 | 137252.64 | 141031.07 | 357140.01 | 153866.88 | 133606.97 | 143868.34 | 155941.97 | 3181719.66 | 332531.165 | 470980.3556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803511.5206 | 3985231.1806 | 701552.93 | 5070686.4206 | 8953959.0106
SCR | CWIP (I&M) Total | 1018831 | 274336 | 271287 | 522937 | 653084 | 864030 | 825124 | 1463092 | 1046886 | 1354652 | 1707800 | 994073 | 744187 | 683561 | 806971 | 763865 | 727514.18 | 4750759.86 | 2938587.16 | 1332909.73 | 1836713.06 | 2016027.88 | 5089318.81 | 4524495.42 | 5661818.02 | 3388857.95 | 1747730.34 | 5241826.31 | 6736400.78 | 6343821.89 | 3932687.07 | 4405277.58 | 3540984.4 | 3954699.8 | 5969765.76 | 3193252.274 | 2138429.874 | 1733781.83 | 4139406.28 | 2096413.14 | 101436195.398 | 2573875.68 | 4013611.895 | 2295556.5339 | 2347879.0403 | 1306385.2211 | 727043.5149 | 424026.1162 | 175279.5408 | 46450.0951 | 1087450 | 14997557.6372 | 116433753.0352 | 28913871.52 | 133244552.9263 | 263594619.8443
SCR
Total RP U2 CWIP (I&M) SCR |  | 1018831 | 274336 | 271287 | 522937 | 653084 | 864030 | 825124 | 1463092 | 1046886 | 1354652 | 1707800 | 994073 | 744187 | 683561 | 806971 | 763865 | 727514.18 | 4750759.86 | 2938587.16 | 1332909.73 | 1836713.06 | 2016027.88 | 5089318.81 | 4524495.42 | 5661818.02 | 3388857.95 | 1747730.34 | 5241826.31 | 6736400.78 | 6343821.89 | 3932687.07 | 4405277.58 | 3540984.4 | 3954699.8 | 5969765.76 | 3193252.274 | 2138429.874 | 1733781.83 | 4139406.28 | 2096413.14 | 101436195.398 | 2573875.68 | 4013611.895 | 2295556.5339 | 2347879.0403 | 1306385.2211 | 727043.5149 | 424026.1162 | 175279.5408 | 46450.0951 | 1087450 | 14997557.6372 | 116433753.0352 | 28913871.52 | 133244552.9263 | 263594619.8443
U2 CWIP (AEG)
SCR | CWIP Controllable (AEG) | 875480 | 199381 | 206532 | 434540 | 580166 | 777054 | 701526 | 1360287 | 892566 | 968252 | 1513799 | 699522 | 491620 | 446027 | 548150 | 430514 | 430030.03 | 4461359.29 | 2543510.79 | 923403.8 | 1380857.99 | 1613698.93 | 4643199.1 | 4291033.58 | 5457465.1 | 2926483.74 | 1364835.61 | 4766121.5 | 6313997.53 | 5941479.6 | 3539073.87 | 3961716.47 | 2927801.94 | 3421235.29 | 5412232.84 | 2398949.25 | 1496696.17 | 1246629.32 | 3519974.54 | 1720636.05 | 87827838.33 | 2140751.705 | 3257907.0665 | 2108967.085 | 2159068.5 | 1201329 | 668576.5 | 389927 | 161184 | 42714.695 | 1000000 | 13130425.5515 | 100958263.8815 | 26105304.7 | 114490979.8565 | 228424122.8865
SCR | Allocations (AEG) | 139050 | 71612 | 60524 | 83001 | 66791 | 78310 | 111800 | 90633 | 131536 | 357896 | 158275 | 251988 | 209040 | 193579 | 208864 | 282682 | 242713.29 | 231720.58 | 299436.75 | 293315.87 | 324590.27 | 262412.71 | 291691.85 | 275277.24 | 139239.91 | 387597.88 | 300330.04 | 385246.36 | 326242.81 | 296158.09 | 277476.35 | 324181.29 | 486746.44 | 396212.37 | 416502.6 | 437163.52 | 487616.84 | 353546 | 475563.85 | 219835.5 | 10426399.41 | 100592.81 | 284724.473 | 186589.4489 | 188810.5403 | 105056.2211 | 58467.0149 | 34099.1162 | 14095.5408 | 3735.4001 | 87450 | 1063620.5652 | 11490019.9752 | 2107017.35 | 13682401.2133 | 26215817.9733
SCR | AFUDC (AEG) | 591 | 2569 | 5111 | 6652 | 5142 | 9789 | 12502 | 12793 | 15547 | 6819 | 8872 | 21889 | 47032 | 16083 | 28168 | 51946 | 72381.12 | 84017.18 | 91626.31 | 62669.89 | 84072.33 | 136401.22 | 155017.17 | 176547.33 | 199158.07 | 219123.14 | 250079.53 | 264508.19 | 291111.7 | 325311.75 | 352816.37 | 391007.32 | 365550.68 | 364868.09 | 479327.04 | 510108.84 | 532075.11 | 543360.22 | 546487.35 | 557574.94 | 7306705.89 | 332531.165 | 470980.3556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 803511.5206 | 8110217.4106 | 2090665.91 | 11279150.9106 | 20676522.7106
SCR | CWIP (AEG) Total | 1015121 | 273562 | 272167 | 524193 | 652099 | 865153 | 825828 | 1463713 | 1039649 | 1332967 | 1680946 | 973399 | 747692 | 655689 | 785182 | 765142 | 745124.44 | 4777097.05 | 2934573.85 | 1279389.56 | 1789520.59 | 2012512.86 | 5089908.12 | 4742858.15 | 5795863.08 | 3533204.76 | 1915245.18 | 5415876.05 | 6931352.04 | 6562949.44 | 4169366.59 | 4676905.08 | 3780099.06 | 4182315.75 | 6308062.48 | 3346221.61 | 2516388.12 | 2143535.54 | 4542025.74 | 2498046.49 | 105560943.63 | 2573875.68 | 4013611.895 | 2295556.5339 | 2347879.0403 | 1306385.2211 | 727043.5149 | 424026.1162 | 175279.5408 | 46450.0951 | 1087450 | 14997557.6372 | 120558501.2672 | 30302987.96 | 139452531.9803 | 275316463.5703
SCR
Total RP U2 CWIP (AEG) SCR |  | 1015121 | 273562 | 272167 | 524193 | 652099 | 865153 | 825828 | 1463713 | 1039649 | 1332967 | 1680946 | 973399 | 747692 | 655689 | 785182 | 765142 | 745124.44 | 4777097.05 | 2934573.85 | 1279389.56 | 1789520.59 | 2012512.86 | 5089908.12 | 4742858.15 | 5795863.08 | 3533204.76 | 1915245.18 | 5415876.05 | 6931352.04 | 6562949.44 | 4169366.59 | 4676905.08 | 3780099.06 | 4182315.75 | 6308062.48 | 3346221.61 | 2516388.12 | 2143535.54 | 4542025.74 | 2498046.49 | 105560943.63 | 2573875.68 | 4013611.895 | 2295556.5339 | 2347879.0403 | 1306385.2211 | 727043.5149 | 424026.1162 | 175279.5408 | 46450.0951 | 1087450 | 14997557.6372 | 120558501.2672 | 30302987.96 | 139452531.9803 | 275316463.5703
U2 EPIS (I&M)
SCR | EPIS Controllable (I&M) | [40 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | bar: 2019-04-01 to 2020-03-01
SCR | Allocations (I&M) | [40 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | bar: 2019-04-01 to 2020-03-01
SCR | AFUDC (I&M) | [40 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | bar: 2019-04-01 to 2020-03-01
SCR | EPIS (I&M) Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCR
Total RP U2 EPIS (I&M) SCR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
U2 EPIS (AEG)
SCR | EPIS Controllable (AEG) | [40 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | bar: 2019-04-01 to 2020-03-01
SCR | Allocations (AEG) | [40 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | bar: 2019-04-01 to 2020-03-01
SCR | AFUDC (AEG) | [40 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | bar: 2019-04-01 to 2020-03-01
SCR | EPIS (AEG) Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCR
Total RP U2 EPIS (AEG) SCR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[43 empty] | 0 | 0 | 0

## Decker Input - FRP-1
Rockport Unit 2 SCR Project: Actual Costs Incurred During Historical Period and Planned Expenditures for Forecast Period
| Rockport U2 I&M1 Direct Ownership Share | Rockport U2 AEG1 Ownership Share | Total Rockport Plant
Historical Period Project Costs2 | 98254473.45 | 98254238.25 | 196508711.7
Historical Period AFUDC2,3,5 | 3181719.8 | 7306706.48 | 10488426.28
Historical Period Total Cost Including AFUDC2,3,5 | 101436193.25 | 105560944.73 | 206997137.98
Forecast April 2020 thru Dec 2020 Project Cost | 13106596.1167 | 13106596.1167 | 26213192.2334
Forecast April 2020 thru Dec 2020 AFUDC | 803511.5206 | 803511.5206 | 1607023.0411
Forecast April 2020 thru Dec 2020 Total Cost Including AFUDC | 13910107.6372 | 13910107.6372 | 27820215.2745
Forecast Period Project Costs4 | 1087450 | 1087450 | 2174900
Forecast Period AFUDC3,4,5
Forecast Period Total Cost Including AFUDC3,4,5 | 1087450 | 1087450 | 2174900
Estimated Project Total Cost6 | 112448519.5667 | 112448284.3667 | 224896803.9334
Estimated Total AFUDC3,5,6 | 3985231.3206 | 8110218.0006 | 12095449.3211
Estimated Project Total Cost Including AFUDC3,5,6 | 116433750.8872 | 120558502.3672 | 236992253.2545
1 - Total Cost for Rockport I&M & AEG projects is estimated at a 50% split
2 - Historical Period represents costs incurred through March 31, 2020
3 - Allowance for Funds Used During Construction (AFUDC)
4 - Forecast Period from January 1, 2021 through December 31, 2021
5 - For I&M's direct ownership share, effective January 2015, I&M records AFUDC on 100% of the FERC jurisdictional component
6 - Through end of Project (December 31, 2020)

## Decker Input - FRP-2
Rockport Unit 2 SCR Project: Total Rockport Plant Estimated Project Capital Costs, Excluding AFUDC Total Rockport Plant Estimated Project Capital Costs, Excluding AFUDC
| Phase II | Phase III | EAC | Delta (EAC vs Phase III)
SCR | 216332024 | 192152241.7596 | 192152241.7596 | 0
Subtotal - Direct Construction Cost | 216332024 | 192152241.7596 | 192152241.7596 | 0
PME&C | 15600000 | 13671843 | 13671843 | 0
Subtotal | 231932024 | 205824084.7596 | 205824084.7596 | 0
Risk Allocation* | 12605111 | 2000000 | 2000000 | 0
Total | 244537135 | 207824084.7596 | 207824084.7596 | 0
AEP Overhead Allocations | 16202679 | 17072720 | 17072720 | 0
Grand Total | 260739814 | 224896804.7596 | 224896804.7596 | 0
* Phase II Risk = 5.43% @ P90
* Phase III Risk = 5.27% @ P90
* EAC includes Actuals thru March 31, 2020
EAC = Estimate at Completion
SCR = Selective Catalytic Reduction
PME&C = Project Management, Engineering & Construction Management
AFUDC is not included in the values above.