## Cover Page
Petitioner's Exhibit No. 2
Public Attachments SAH-2 through SAH-9
CEI North
Cause No. 45611
FILED
September 10, 2021
INDIANA UTILITY
REGULATORY COMMISSION

## SAH-2
CEI North
Compliance Projects - Investment Summary
Compliance Projects | 2022 | 2023 | 2024 | 2025 | 2026 | 2022-2026
BS/CI Replacements | 69443993.21 | 68555805.8086 | 67082386.4074 | 28050362.6907 | 0 | 233132548.1168
Distribution Modernization | 16271553.56 | 12730381.7626 | 27856031.1869 | 79730070.0895 | 78678312.1007 | 215266348.6996
Transmission Modernization | 33681220.2 | 78622067.927 | 26934107.4286 | 57641244.0042 | 115022836.6191 | 311901476.179
Storage Modernization | 9365309.48 | 14210468.7053 | 6994410.7912 | 6456749.8941 | 2705408.3385 | 39732347.2091
Compliance Total | 128762076.45 | 174118724.2035 | 128866935.8142 | 171878426.6784 | 196406557.0583 | 800032720.2045

## SAH-3
CEI North
2022-2026 TDSIC Plan Investment Summary
TDSIC Plan | 2022 | 2023 | 2024 | 2025 | 2026 | 2022-2026
Targeted Economic Development | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 10500000
Rural Extension | 5509067.81 | 1400000 | 1400000 | 1400000 | 1400000 | 11109067.81
System Improvement - Safety and Reliability | 7819319.71 | 49782112.9216 | 175264592.5916 | 93950093.002 | 34685908.8772 | 361502027.1024
Public Improvement | 13290762.57 | 9169408.2765 | 7605008.2038 | 2653162.36 | 2853332.7296 | 35571674.1399
TDSIC Total | 28719150.09 | 62451521.1981 | 186369600.7954 | 100103255.362 | 41039241.6068 | 418682769.0523

## SAH-4 (Public)
CEI North
Transmission Modernization - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
5090 | N/A | TBD | CASINGS | SE Storage | DOLAN | Remove casings at three locations in Dolan Storage Field where the existing casings are shorted to the carrier pipe. | 2022
NS5057-4296 | N/A | TBD | GAS QUALITY / CONDITIONING | SE | BLOOMINGTON | Install gas chromatograph and filter/separator at Needmore PP Regulator Station 24000264 to be able to monitor the quality of gas being delivered. | 2022
NS5017-3921 | N/A | TBD | ILI RETROFITS | SE | CHARLESTOWN | NS5017: Replace existing 1965 vintage 6" pipe from Measure 8163 to Measure 13082 (4,919'). Replace with pipe with a hoop stress <20%. NS5700: Replace 500' of existing 1968 vintage pipe. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats. | 2022
NS5052-3124 | N/A | TBD | ILI RETROFITS | SE | GRANDVIEW | 10" Grandview PP to Waynesville TBS - ILI Retrofit to allow for In-Line Inspection | 2022
NS5143-4266 | N/A | TBD | ILI RETROFITS | SE | SHELBYVILLE | 16" Whiteland to Shelbyville ILI retrofit to allow for In-Line Inspection. MAOP Reconfirmation and Material verification for 5143-5105 included | 2022
5075 | N/A | TBD | OBSOLETE EQUIPMENT | NE | DUNKIRK | Replace the outdated controller at Dunkirk Station due to obsolete equipment. | 2022
5076 | N/A | TBD | OBSOLETE EQUIPMENT | NW | HENDRICKS COUNTY JUNCTION | Replace 3 pressure controllers at HCJ due to obsolete equipment. | 2022
N-XA-11721 | 14000034 | 19595602051210 | OBSOLETE EQUIPMENT | NW | ATTICA | IN-ATTICA-SUMMIT ST REG STATION-REBUILD SUMMIT ST ~~Station needs rebuilt has obsolete equipment, leaky valves and riser corrosion (0 - services) | 2022
NE4001-4875 | N/A | 21202802054018 | PRIORITY PIPE | NE | ZIONSVILLE | Replace 1978 vintage pipe between Hendricks County Junction and Zionsville due to seam defects including hook cracks identified through ILI. | 2022
NW3103-5143 | N/A | TBD | PRIORITY PIPE | NW | LAFAYETTE | Replace small section of 8" pipe with 12" pipe on Subaru Line. Assessment needed in 2023 | 2022
NW3124-3164 | N/A | TBD | PRIORITY PIPE | NW | GREENCASTLE | ILI retrofit and combine with NW3128 to allow for In-Line Inspection of NW3124 and NW3128. | 2022
5052 | N/A | TBD | GAS QUALITY / CONDITIONING | SE Storage | DOLAN | Install Gas Chromatograph at Unionville to monitor gas quality | 2023
NE4006-2960 | N/A | TBD | GAS QUALITY / CONDITIONING | NE | ANDERSON | Install Gas Chromatograph and filter/separator and Anderson #2 Station to ensure gas quality | 2023
NS5013-3919 | N/A | TBD | GAS QUALITY / CONDITIONING | SE | CRESTWOOD, KY | Install Gas Chromatograph at Crestwood PP to monitor gas quality. | 2023
NS5142-5102 | N/A | TBD | PRESSURE TEST | NW | DANVILLE | MAOP Reconfirmation - Pressure Test and Material Verification. PT from HCJ (0.00) to I-70 (104131.32) (104,131 ft). Replace lateral Route NS5142.L089 to RS #46000033 Lake of Lanterns. Replace through reg runs. | 2023
NW3117-3088 | N/A | 19202802054022 | PRESSURE TEST | NW | TERRE HAUTE | Replace approximately 13 miles of 8" steel transmission line between Texas Gas PP to Centerpoint Station. Pipeline requires MAOP reconfirmation but cannot be pressure tested because it is only supply to single-feed system. | 2023
NW3125-5108 | N/A | TBD | PRESSURE TEST | NW | LEBANON | MAOP Reconfirmation - Pressure Test and Material Verification. PT from Measure 0 to 15056.04 (15056 ft). | 2023
NE4001-5002 | N/A | TBD | PRIORITY PIPE | NE | ZIONSVILLE | Replace 30,894' of 1978 vintage pipe between Hendricks County Junction and Zionsville due to seam defects including hook cracks. | 2023
NE4006-5147 | N/A | TBD | PRIORITY PIPE | NE | ANDERSON | Replace 103' of unknown vintage pipe from Measure 24222.6 to Measure 24119.12 at Orebaugh Creek. | 2023
NE4036-5089 | N/A | TBD | PRIORITY PIPE | NE | MUNCIE | Phase 1 Construct new 12" pipeline from Gate 12 in Muncie to the Rushville Take Off Station to eliminate the existing pipeline with defects. | 2023
NW3107-3231 | N/A | TBD | PRIORITY PIPE | NW | CRAWFORDSVILLE | Install new rectifiers and/or ground beds on NW3107 line to improve cathodic protection. Current protection not adequate to prevent corrosion. | 2023
NW3108-3230 | N/A | TBD | PRIORITY PIPE | NW | CRAWFORDSVILLE | Install new rectifiers and/or ground beds on NW3108 line to improve cathodic protection. Current protection not adequate to prevent corrosion. | 2023
NE4015-3295 | N/A | TBD | GAS QUALITY / CONDITIONING | NE | RICHMOND | Install filter/separator and gas chromatograph at Panhandle PP (Richmond #2) to monitor and maintain gas quality. | 2024
NE4018-3880 | N/A | TBD | GAS QUALITY / CONDITIONING | NE | PONETO | Install relief valve, gas chromatograph and filter/separator at Huntington purchase point | 2024
NS5145-3471 | N/A | TBD | GAS QUALITY / CONDITIONING | SE | ST PAUL | Install gas chromatographs at REX PP to monitor the quality of gas being delivered in Vectren facilities. | 2024
NW3112-3275 | N/A | TBD | GAS QUALITY / CONDITIONING | NW | TERRE HAUTE | Install filter and separator at Heartland Steel PP to improve gas quality in the south Terre Haute system. | 2024
NW3003-3149 | N/A | TBD | ILI RETROFITS | NW | LAFAYETTE | Replace 17 fittings on the 16" main from Taylor trap to McCormic Station. Remediate exposure on concord road west of the Wea Valve. Replace the leaking 8" valve at Fox Station. Install 9 filters at regulator stations. This project will require 4 stopple and distribution support. ILI retrofit to allow for In-Line Inspection | 2024
5081 | N/A | TBD | OBSOLETE EQUIPMENT | SE Storage | DOLAN | Install Ultrasonic Metering at Dolan Storage Field to replace obsolete meters and provide enhanced reservoir inventory monitoring and control | 2024
5082 | N/A | TBD | OBSOLETE EQUIPMENT | NW Storage | WOLCOTT | Install Ultrasonic Metering at Wolcott Storage Field to replace obsolete meters and provide enhanced reservoir inventory monitoring and control | 2024
NE4003-5092 | N/A | TBD | PRESSURE TEST | NE | NOBLESVILLE | MAOP Reconfirmation - Pressure Test and Material Verification. (45 miles total): •PT from Zionsville (0) to 111th St (29757) (30, 000 ft); include Gate 1 (Routes NE4003.L058 & NE4003.Y003) •PT from 111th St (29757) to Lantern Rd (72987) (43, 000 ft) •PT from Lantern Rd (72987) to east of May's Landing Dr (74348) (1361 ft) •PT from Promise Rd (85700) to Gate 6 (145392.77) (60, 000 ft) •PT from Measure 173206 (Anderson #1 Station) to 264364.68 (Gate 12) (91,158 ft) •PT from Measure 264364.68 (Gate 12) to 280512.55 (King Station) (16, 100 ft) | 2024
NS5009-3290 | N/A | TBD | PRESSURE TEST | SE | CLARKSVILLE | Pressure test of 10" Quarry Bluff to Longview Beach (DS) due to no existing pressure test documentation. | 2024
NS5010-3292 | N/A | TBD | PRESSURE TEST | SE | CLARKSVILLE | Pressure test of 10" Quarry Bluff to Longview Beach (US) due to no existing pressure test documentation. | 2024
NS5055-5142 | N/A | TBD | PRESSURE TEST | SE | BLOOMINGTON | NS5055 assessment along Old SR-37 due in 2025; Pressure Test for MAOP Reconfirmation (NS5153 Measure 65387.98 to 67076.12) and Assessment and replace any vintage 1948 or unknown adjacent pipe. Also replace or PT nearby Reconfirmation segment from NS5153 Measure 64929.68 to 64941.67. | 2024
NS5056-5141 | N/A | TBD | PRESSURE TEST | SE | BLOOMINGTON | NS5056 assessment at 3rd St due in 2024; Pressure Test for Reconfirmation (NS5153 Measure 96684.08 to 96758.91) and Assessment and replace any vintage 1956 adjacent pipe | 2024
NS5059-5100 | N/A | TBD | PRESSURE TEST | SE | BLOOMINGTON | Pressure test from Measure 22901.91 to 28197.42 for Assessment and Reconfirmation.MAOP Reconfirmation - Pressure Test and Material Verification - segment from Measure 26119 to 28197.42 (2,078 ft) | 2024
NS5059-5101 | N/A | TBD | PRESSURE TEST | SE | BLOOMINGTON | MAOP Reconfirmation replacement - cannot pressure test. Route NS5059.L003 - lateral to 19th & Dunn Streets Station 29000011 and rebuild Station 29000011 | 2024
NS5143-5042 | N/A | TBD | PRIORITY PIPE | SE | WHITELAND | Material verification to establish traceable, verifiable, and complete pipeline records. Collect cutouts on sections not completed in 2022 | 2024
NW3112-3057 | N/A | TBD | PRIORITY PIPE | NW | TERRE HAUTE | Install new Rectifier and Ground Bed to improve cathodic protection. Current protection not adequate to prevent corrosion. | 2024
NE4021-3937 | N/A | TBD | ILI RETROFITS | NE | GREENFIELD | ILI retrofit. Install launcher and receiver and filters on side stations. | 2025
NW3122-3032 | N/A | TBD | ILI RETROFITS | NW | CAYUGA | Newport tie-over to feed the town of Newport from the Cayuga PP. Necessary to allow ILI retrofit and assessment of 16" Cayuga to Duke pipeline - NW3122-3076 | 2025
NW3122-3076 | N/A | TBD | ILI RETROFITS | NW | CAYUGA | ILI Retrofit of 16" Cayuga to Duke to allow for In-Line Inspection. | 2025
5083 | N/A | TBD | OBSOLETE EQUIPMENT | SE Storage | SELLERSBURG | Install Ultrasonic Metering at Sellersburg Storage Field to replace obsolete meters and provide enhanced reservoir inventory monitoring and control | 2025
NS5006-5097 | N/A | TBD | PRESSURE TEST | SE | SELLERSBURG | Reconfirmation Pressure Test and MatV - PT from Holman (26768.84) to Utica (7459.01) (19309 ft) | 2025
NS5057-5139 | N/A | TBD | PRESSURE TEST | SE | BLOOMINGTON | Reconfirmation pressure test from Measure 22224 to 24237.26 (2013 ft) (Fullerton 2014 reroute). Reconfirmation pressure test cannot be performed - replace from Measure 24237.26 to 24592.95 (HCA), and 81163 to 82186.55 (HCA). | 2025
NE4036-5089 | N/A | TBD | PRIORITY PIPE | NE | MUNCIE | Phase 2 Construct new 12" pipeline from Gate 12 in Muncie to the Rushville Take Off Station to replace the existing pipeline with defects | 2025
NS5053-5049 | N/A | TBD | PRIORITY PIPE | SE | COLUMBUS | Replace 638' of 1946 vintage 8" pipe due to older vintage pipe. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats. | 2025
NS5059-5050 | N/A | TBD | PRIORITY PIPE | SE | BLOOMINGTON | Replace 1,829' of 1955 vintage pipe between Dolan Station and IU Metering Station due to older vintage pipe. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats. | 2025
NS5060-5051 | N/A | TBD | PRIORITY PIPE | SE | BLOOMINGTON | Replace 7,045' of 1959 vintage and unknown vintage pipe between Dolan Station and Dolan Storage Field. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats. | 2025
NW3114-3424 | N/A | TBD | PRIORITY PIPE | NW | TERRE HAUTE | 6" Margaret #2 to Texas Gas PP - Replacement // NW3114. Replace 200 feet of 6" pipe due to unsupported MAOP | 2025
NW3800-5137 | N/A | TBD | PRIORITY PIPE | NW | WOLCOTT | Replace 2.88 miles of 16" trunk line and replace all lateral lines to wells due to internal corrosion. | 2025
9999 | N/A | TBD | GAS QUALITY / CONDITIONING | NW | MONROVIA | Replace odorizer at Monrovia Station due to obsolete equipment. | 2026
NS5145-3085 | N/A | TBD | GAS QUALITY / CONDITIONING | SE | GREENSBURG | Install new odorizer tanks at Greensburg 261 station due to existing tanks being in poor condition. | 2026
NE4012-3031 | N/A | TBD | OBSOLETE EQUIPMENT | NE | NEW CASTLE | Eliminate Joyner Farm regulator pit/Station 1645 Equipment no longer needed that increases likeliness of incorrect operation threat. Replacement with distribution piping eliminates transmission asset. | 2026
NE4015-5094 | N/A | TBD | PRESSURE TEST | NE | RICHMOND | Reconfirmation Pressure Test and Material verification; MatV for fittings only; PT entire pipeline (53517.03 ft) | 2026
NE4037-5091 | N/A | TBD | PRESSURE TEST | NE | HUNTINGTON | Phase 1 Easement acquisition and construct new pipeline from the Huntington PP to Huntington TBS. Required Pressure test of existing transmission pipeline cannot be completed - single feed system | 2026
NE4037-5147 | N/A | TBD | PRESSURE TEST | NE | HUNTINGTON | Phase 2 of Replacement Huntington PP to Huntington TBS to allow for pressure test of NE4018 pipeline which is a one way feed with new NE4037 pipeline. | 2026
NS5011-5098 | N/A | TBD | PRESSURE TEST | SE | SELLERSBURG | MAOP Reconfirmation Pressure Test - from Measure 4310.22 to 8428.02 (across river) (4118 ft) | 2026
NS5012-5099 | N/A | TBD | PRESSURE TEST | SE | SELLERSBURG | Reconfirmation Pressure Test - PT from Measure 4252.73 to 8255.71 (across river) (4002 ft) | 2026
5077 | N/A | TBD | PRIORITY PIPE | SE | BLOOMINGTON | Replace roughly 6,500' of the 8" Needmore to Bloomington pipeline east of Childs School to just south of St. Remy Dr. | 2026
NE4005-5045 | N/A | TBD | PRIORITY PIPE | NE | GREENFIELD | Replace 29,315' of 1956 vintage pipe, 853.3' of 1963 vintage pipe and 101.7' of 1965 vintage pipe. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats as well as poor girth welds. | 2026
NE4036-5089 | N/A | TBD | PRIORITY PIPE | NE | MUNCIE | Phase 3 Construct new 12" pipeline from Gate 12 in Muncie to the Rushville Take Off Station to eliminate the existing pipeline with defects. | 2026
NS5001-4993 | N/A | TBD | PRIORITY PIPE | SE | CLARKSVILLE | Replace 5,758' of 8" 1952 vintage between Applegate Station and Clarksville TBS. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats. ECDA not effective as pipeline coating is not sufficient. | 2026
NS5008-5046 | N/A | TBD | PRIORITY PIPE | SE | CLARKSVILLE | Replace 4,295' of 1953 vintage pipe due to older vintage pipe. This vintage is associated with manufacturing and construction threats that interact with outside force, external corrosion, third party damage, incorrect operation threats. Replacement of the vintage pipe will eliminate interactive threats. | 2026
NS5014-3791 | N/A | TBD | PRIORITY PIPE | SE | CRESTWOOD, KY | Replace 1.1 miles of 10"line for Crestwood to the river with 16" through HCA | 2026

## SAH-5 (Public)
CEI North
Distribution Modernization - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
N-X-163 | 18103261 | 17595002G50228 | BRIDGE CROSSINGS | NW | TERRE HAUTE | IN-TERRE HAUTE-HULMAN ST ~~ BRIDGE CROSSING N-X-163 - INSTALL: 470' OF 6" PLASTIC UNDER THOMPSON DITCH AND INDIANA RAILROAD, RETIRE: 385' OF 6" STEEL AND 6" PLASTIC, REPLACE: 0 SERVICES | 2022
N-X-3643 | 13498647 | 16595002050222 | CASINGS | NW | TERRE HAUTE | IN-TERRE HAUTE- 3001 KUSSVEDINNER ST N-X-3643-Shorted Casings-Replace shorted 12" main and casing near 30001 Kussner St. in Terre Haute, IN. Retire 10" main crossing. | 2022
N-X-3810 | 17506775 | 20592402050214 | EXPOSURES | SE | BEDFORD | IN-BEDFORD-SHAWNEE WOODS DR~~REPLACE 500' OF 8" HP STL MAIN IN DITCH AT EAST END OF FIELD NEAR 378 SHAWNEE WOODS . INSTALL 335' OF 8" STEEL. NO SERVICES | 2022
N-X-3811 | 17508498 | 20592402050215 | EXPOSURES | SE | BEDFORD | IN-BEDFORD-PEERLESS RD~~REPLACE 500' OF 8" HP STL MAIN IN CREEK NEAR 831 PEERLESS RD | 2022
N-X-11101 | N/A | TBD | EXPOSURES | NW | BRAZIL | IN-BRAZIL- CR425 6" MP Steel Main - Exposure Near Int. of CR425 and CR900W - Replace Approx. 500' of existing 6" Steel main to remedy an existing exposure. | 2022
N-X-3762 | 18058848 | 20592602050212 | EXPOSURES | SE | GREENSBURG | IN-GREENSBURG-S CR 180 E EXPOSED 6" STEEL HP MAIN ON S CR 180 E APPROX 2,000' NORTH OF E CR 300. INSTALL 570' OF 6" STEEL MAIN. NO SERVICES. | 2022
N-X-1715 | 17503311 | 20592402050212 | EXPOSURES | SE | MITCHELL | IN-MITCHELL-8" STL EXPOSURE #27 MITCHELL @ ART SANDERS PROPERTY SOUTH OF DOTT'S REPLACE APPROX. 500' OF 8" HP STEEL MAIN | 2022
Multiple | Multiple | Multiple | INSIDE METERS | VEDIN | MULTIPLE | INSIDE METERS - relocate inside meters to exterior of structure | 2022
N-X-2003 | 18040843 | 20595502054210 | LEGACY PLASTIC | NW | LAFAYETTE | IN-LAFAYETTE-6th Street Replacement of 1972 Vintage Plastic, 6th Street, 7th Street, 9th Street - Vintage Plastic - Replace approx. 8,500' of existing 2" main and approx. 1,200' of exist. 6" main. Replace approx. 170 services. | 2022
N-X-3001 | 18041793 | 20595302054210 | LEGACY PLASTIC | NW | PLAINFIELD | IN-PLAINFIELD-N CENTER RD~~REPLACE VINTAGE PLASTIC - REPLACE APPROX. 4,300' OF EXISTING 2" MAIN AND APPROX. 4,250' OF EXIST. 6" MAIN. REPLACE APPROX. 56 SERVICES. | 2022
N-X-14701 | 18017496 | 20592402050217 | LEGACY STEEL | SE | BEDFORD | IN-BEDFORD-4TH & H ST INEFFECTIVELY COATED STEEL AND CORROSION LEAKS - 8" HP STEEL DISTRIBUTION MAIN. REPLACE APPROX. 3,400' OF 8" HP STEEL MAIN BETWEEN THE INTERSECTION OF 4TH ST & H ST AND 900' SOUTH OF THE INTERSECTION OF 9TH ST & I ST. | 2022
N-X-15301 | 18017549 | 20592402050218 | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-E 3RD ST INEFFECTIVELY COATED STEEL - 4" MP STEEL DISTRIBUTION MAIN. REPLACE APPROX. 1,150' OF 4" MP STEEL MAIN IN ALLEY S OF E 3RD ST BETWEEN S FESS AVE & S WOODLAWN AVE AND 1,200' IN ALLEY W OF S PARK AVE, BETWEEN 3RD ST & UNIVERSITY AVE; ALSO INCLUDES REPLACING APPROX. 18 SERVICES | 2022
N-X-15210 | 18581521 | TBD | LEGACY STEEL | SE | GREENFIELD | IN-GREENFIEILD- Lantern Woods Regulator Station 48001181 – Lantern Woods – replace 20psig System and tie-in to 60psig System and retire station. -Work Order 34841 for 170’ of 2” Plastic main, but it is Vintage Adyl-A. The rest of the main is M/W Steel. 15 services total | 2022
N-X-4331 | 18059041 | 20583302050213 | LEGACY STEEL | SE | GREENFIELD | IN-GREENFIELD-N FORTVILLE PIKE~~REPLACE 940' OF 2" AND 2,970' OF 3" MP INEFFECTIVELY COATED STL MAIN AND 10 SERVICES | 2022
N-X-9859 | 17510027 | 20592002050213 | LEGACY STEEL | SE | JEFFERSONVILLE | IN-JEFFERSONVILLE-CENTER ST~~REPLACE 1,700' OF 2" INEFFECTIVELY COATED STL MAIN AND 41 SERVICES | 2022
N-X-9959 | 17510005 | 20592002050212 | LEGACY STEEL | SE | JEFFERSONVILLE | IN-JEFFERSONVILLE-SPRINGDALE/LONG ST/SANDRA ST~~REPLACE 1,350' OF 2"AND 1,900' OF 4" INEFFECTIVELY COATED STL MAIN AND 63 SERVICES | 2022
Multiple | Multiple | Multiple | LEGACY STEEL | VEDIN | MULTIPLE | ISOLATED SERVICES - replaced isolated services | 2022
N-X-4392 | 18027432 | 20575102050218 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~RETIRE REG STA 1837 AND INSTALL AND RETIRE 5,000' OF MAIN AND 100 SERVICES | 2022
N-X-4393 | 18027440 | 20575102050219 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~RETIRE REG STA 1835 AND INSTALL AND RETIRE 1,000' OF 8" STL MAIN | 2022
N-X-4394 | 18027447 | 20575102050220 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~RETIRE REG STA 1886 AND INSTALL 5,300' AND RETIRE 3,200' WITH 125 SERVICES | 2022
N-X-4500 | 18027501 | 20575102050222 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~RETIRE REG STA 1810 AND INSTALL AND RETIRE 9,500' OF MAIN WITH 100 SERVICES | 2022
N-X-6000 | 17527739 | 20575102050223 | LEGACY STEEL | NE | RICHMOND | REPLACE 6350' OF COATED LP MAIN AND REPLACE 120 SERICES. RETIRE REG ST 1876 | 2022
N-XA-11735 | 18340598 | 21592402050210 | OBSOLETE EQUIPMENT | SE | MARTINSVILLE | FIRST CUT REMOVAL SR 42 PHASE 2. INSTALL NO MAIN. REPLACING 103 SERVICES | 2022
Multiple | Multiple | Multiple | Obsolete Equipment | VEDIN | MULTIPLE | OBSOLETE RISERS - replace obsolete service risers | 2022
N/A | 18878297 | 21582102050224 | PRESSURE MONITORING/SCADA/RTU | NE | ANDERSON | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 13 ERXs | 2022
N/A | 18881265 | 21595602050210 | PRESSURE MONITORING/SCADA/RTU | NW | ATTICA | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - Station 51000002 - Lithia Street | 2022
N/A | 18883235 | 21592502050210 | PRESSURE MONITORING/SCADA/RTU | SE | BEDFORD | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 2 ERXS | 2022
N/A | 18883250 | 21592402050219 | PRESSURE MONITORING/SCADA/RTU | SE | BLOOMINGTON | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 5 ERXS | 2022
N/A | 18883453 | 21583302050214 | PRESSURE MONITORING/SCADA/RTU | SE | GREENSBURG | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 7 ERXS | 2022
N/A | 18880516 | 21574102050212 | PRESSURE MONITORING/SCADA/RTU | NE | HUNTINGTON | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 10 ERXs | 2022
N/A | 18883477 | 21592902050217 | PRESSURE MONITORING/SCADA/RTU | SE | MARTINSVILLE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 5 ERXS | 2022
N/A | 18881171 | 21573302050220 | PRESSURE MONITORING/SCADA/RTU | NE | NEW CASTLE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 4ERXS | 2022
N/A | 18881193 | 21583002050210 | PRESSURE MONITORING/SCADA/RTU | NE | NOBLESVILLE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 3 ERXS | 2022
N-XA-11921 | 18747210 | 21582102050215 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve - CR 200 E - N OF US 36 | 2022
N-XA-11923 | 18747218 | 21582102050217 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve - S/S OF MALL PARKING LOT | 2022
N-XA-11924 | 18747219 | 21582102050218 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve - CR 600 W - N OF W CR 200 S | 2022
N-XA-11925 | 18747244 | 21582102050219 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve - CR 700 W - N OF W CR 200 S | 2022
N-XA-12008 | 18747181 | 21582102050210 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve - E/S OF PEARL ST @ 26TH ST | 2022
N-XA-12009 | 18747183 | 21582102050212 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve - SE CORNER OF 25TH & MADISON | 2022
N-XA-12010 | 18747199 | 21582102050213 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve - INTERSECTION OF CROSS & WENDELL | 2022
N-XA-12028 | 18745367 | 21592402050218 | REGULATOR STATION | SE | BROOKLYN | Install regulator station emergency inlet valve - BROOKLYN 18745367 | 2022
N-XA-11888 | 18346685 | 21595002050210 | REGULATOR STATION | NW | CLINTON | Install regulator station emergency inlet valve - CLINTON 18346685 | 2022
N-XA-11897 | 18351653 | 21592602050210 | REGULATOR STATION | SE | COLUMBUS | Install regulator station emergency inlet valve - COLUMBUS 18351653 | 2022
N-XA-12007 | 18747176 | 21583402050210 | REGULATOR STATION | NE | ELWOOD | Install regulator station emergency inlet valve - SR 37 - N OF PLAZA & S OF YARLING | 2022
N-X-4302 | 18103270 | 20595502054212 | REGULATOR STATION | NW | FRANKFORT | IN-Frankfort- S CR 130 W N-X-4302-MOD project in support of project 18202802054017 (12" HJC to Fox Retrofit). Project installs 5,500 feet of 4 inch plastic along S CR 130 W from W CR 300 S to W CR 200 S in Frankfort Indiana. The project connects an isolated distribution system (Reg Sta 60000028) to the Frankfort distribution system. | 2022
N-XA-11894 | 18351980 | 21583502050210 | REGULATOR STATION | SE | FRANKLIN | Install regulator station emergency inlet valve - FRANKLIN 18351980 | 2022
N-XA-11889 | 18352055 | 21583302050213 | REGULATOR STATION | SE | GREENFIELD | Install regulator station emergency inlet valve - GREENFIELD 18352055 | 2022
N-XA-11890 | 18352049 | 21583302050212 | REGULATOR STATION | SE | GREENFIELD | Install regulator station emergency inlet valve - GREENFIELD 18352049 | 2022
N-XA-11895 | 18351974 | 21592702050212 | REGULATOR STATION | SE | GREENSBURG | Install regulator station emergency inlet valve - GREENSBURG 18351974 | 2022
N-XA-11896 | 18351743 | 21592702050210 | REGULATOR STATION | SE | GREENSBURG | Install regulator station emergency inlet valve - GREENSBURG 18351743 | 2022
N-XA-11885 | 18352105 | 21595502050212 | REGULATOR STATION | NW | LAFAYETTE | Install regulator station emergency inlet valve - LAFAYETTE 18352105 | 2022
N-XA-11886 | 18352069 | 21595502050210 | REGULATOR STATION | NW | LAFAYETTE | Install regulator station emergency inlet valve - LAFAYETTE 18352069 | 2022
N-XA-12001 | 18746394 | 21595402050210 | REGULATOR STATION | NW | LEBANON | Install regulator station emergency inlet valve - LEBANON 18746394 | 2022
N-XA-12002 | 18746395 | 21595402050212 | REGULATOR STATION | NW | LEBANON | Install regulator station emergency inlet valve - LEBANON 18746395 | 2022
N-XA-12025 | 18352035 | 21583302050210 | REGULATOR STATION | SE | NEW PALESTINE | Install regulator station emergency inlet valve - NEW PALESTINE 18352035 | 2022
N-XA-11922 | 18747212 | 21582102050216 | REGULATOR STATION | NE | PENDLETON | Install regulator station emergency inlet valve - N/S OF US 36 - W OF CARRIAGE LN | 2022
N-XA-12011 | 18747204 | 21582102050214 | REGULATOR STATION | NE | PENDLETON | Install regulator station emergency inlet valve - WATER ST - E OF PENDLETON PIKE | 2022
N-XA-12024 | 18352066 | 21595002050212 | REGULATOR STATION | NW | ROSEDALE | Install regulator station emergency inlet valve - ROSEDALE 18352066 | 2022
N-XA-11892 | 18352018 | 21575302050212 | REGULATOR STATION | SE | RUSHVILLE | Install regulator station emergency inlet valve - RUSHVILLE 18352018 | 2022
N-XA-11893 | 18351985 | 21575302050210 | REGULATOR STATION | SE | RUSHVILLE | Install regulator station emergency inlet valve - RUSHVILLE 18351985 | 2022
N-X-4102 | 15131328 | 18595002050213 | REGULATOR STATION | NW | TERRE HAUTE | IN-TERRE HAUTE-STATION 34000144-7TH STREET-UPSUPPOTED N-X-4102 - Regulator Station 34000144 (-87.406601, 39.419701) has unsupported Fisher 621 regulators and compression valves. Located at 7th St and Royce Street, near Rea Park. | 2022
N-XA-12003 | 18746397 | 21595002050218 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve - TERRE HAUTE 18746397 | 2022
N-XA-12004 | 18746398 | 21595002050219 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve - TERRE HAUTE 18746398 | 2022
N-XA-12005 | 18746399 | 21595002050220 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve - TERRE HAUTE 18746399 | 2022
N-XA-12006 | 18746401 | 21595002050221 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve - TERRE HAUTE 18746401 | 2022
N-X-179 | 9581826 | 14595002050222 | BRIDGE CROSSINGS | NW | TERRE HAUTE | IN-TERRE HAUTE-WABASH RIVER BRIDGE~ IN-TERRE HAUTE-WABASH RIVER BRIDGE~~REPLACE 8" STL MAIN - EXPOSURE - REPLACE APPROX. 1,200' OF EXIST. 8" MP STEEL MAIN AT THE WABASH RIVER CROSSING. | 2023
N-X-3714 | 18457978 | 21583502050212 | EXPOSURES | SE | FRANKLIN | IN-FRANKLIN-E GREENSBURG RD EXPOSURE~~REPLACE 500' OF 6" STL MAIN | 2023
N-X-1707 | 18457926 | 21592402050216 | EXPOSURES | SE | MITCHELL | IN-MITCHELL-SHOALS LINE EXPOSURE #13~~REPLACE 500' OF 6" STL MAIN. INSTALLING 500' OF 6" STEEL. NO SERVICES. | 2023
Multiple | Multiple | Multiple | INSIDE METERS | VEDIN | MULTIPLE | INSIDE METERS - relocate inside meters to exterior of structure | 2023
N-X-4003 | 18455270 | 21595302050210 | LEGACY PLASTIC | NW | BROWNSBURG | IN-BROWNSBURG-LAKE FOREST DR~ IN-BROWNSBURG-LAKE FOREST DR~~REPLACE VINTAGE PLASTIC - REPLACE APPROX. 100' OF EXISTING 2" MAIN AND APPROX. 2,550' OF EXIST. 6" MAIN. REPLACE APPROX. 19 SERVICES. | 2023
N-X-10005 | 18455278 | 21592402050212 | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-KINSER PIKE~~REPLACE 1,700' OF 4" INEFFECTIVELY COATED STL MAIN AND 18 SERVICES | 2023
N-X-15302 | 18457830 | 21592402050214 | LEGACY STEEL | SE | BLOOMINGTON | IN- BLOOMINGTON-1OTH Ineffective Coated Steel - Replace approx. 1,300' of 2" Steel and 600' of 4" Steel main located along 10th St between Forest Ave and Jordan Ave; and 400' of 2" Steel along Walnut Grove between 10th St and Cottage Grove; and 1750' of 4" Steel main along Jordan Ave between 7th St and Law Ln; also includes replacing approx. 14 services. | 2023
N-X-483 | 18457998 | 21592402050217 | LEGACY STEEL | SE | BLOOMINGTON | IN-Bloomington-13th street N-X-483 - Ineffectively Coated Steel - Replace 2,650' of 4" and 2" steel main with poor CP along 13th St. between Fee Ln. and Indiana Ave. and 500' of 2" steel main along 14th St, between Park Ave and Forest Ave and Replace Approx. 9 Services | 2023
N-X-9858 | 18458023 | 21592002050210 | LEGACY STEEL | SE | CLARKSVILLE | IN-CLARKSVILLE-ACCRUSIA AVE~~REPLACE 2,200' OF 2"AND 1,000' OF 4" INEFFECTIVELY COATED MP STL MAIN AND 66 SERVICES | 2023
N-X-15910 | 18457869 | 21592602050212 | LEGACY STEEL | SE | COLUMBUS | IN-COLUMBUS- FAIRLANE DR-FROM 25TH TO 29TH STREETS- REPLACE 5,650' INEFFECTIVELY COATED STL MAIN AND 87 SERVICES | 2023
N-X-16710 | 18457894 | 21592402050215 | LEGACY STEEL | SE | ELLETTSVILLE | IN-ELLETTSVILLE-LAKEVIEW RD~~REPLACE 2,400' OF 4" INEFFECTIVELY COATED STL MAIN AND 30 SERVICES | 2023
Multiple | Multiple | Multiple | LEGACY STEEL | VEDIN | MULTIPLE | ISOLATED SERVICES - replaced isolated services | 2023
N-X-4388 | 18027491 | 20575102050221 | LEGACY STEEL | NE | RICHMOND | IN-Richmond-REPLACE BS E-F-G-3-4-5TH STREETS- INSTALL 5075' OF 2" PL AND 91 SERVICES. REPLACE 5075' OF 6" STL. | 2023
N-X-4501 | 18120305 | 21575102050210 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 3,500' OF VARIOUS SIZE INEFFECTIVELY COATED LP STL MAIN AND 70 SERVICES | 2023
N-X-4503 | 18120321 | 21575102050213 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 6,000' INSTALL 6000' OF INEFFECTIVELY COATED LP STL MAIN AND 100 SERVICES, RETIRE REG STA 1830 | 2023
N-X-4504 | 18120353 | 21575102050214 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 6,500' OF INEFFECTIVELY COATED LP STL MAIN AND 75 SERVICES | 2023
N-X-4505 | 18120355 | 21575102050215 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 5,000' OF INEFFECTIVELY COATED LP STL MAIN AND 75 SERVICES | 2023
N-X-4506 | 18120367 | 21575102050216 | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 3,000' OF INEFFECTIVELY COATED LP STL MAIN AND 75 SERVICES | 2023
N-X-4707 | 18120317 | N/A | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND-TOOSBURY ST~~REPLACE 2,000' OF INEFFECTIVELY COATED LP STL MAIN AND 16 SERVICES | 2023
N-X-3005 | 18455221 | 21595002050215 | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE - WILKIE, W OAK GROVE, BENJAMIN IN-TERRE HAUTE~~UNKOWN STL - WILKIE, W OAK GROVE, BENJAMIN - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 3,200' OF EXIST. 2" MP STEEL MAIN. REPLACE APPROX. 27 SERVICES. | 2023
Multiple | Multiple | Multiple | Obsolete Equipment | VEDIN | MULTIPLE | OBSOLETE RISERS - replace obsolete service risers | 2023
N-X-3002 | 18062976 | 20595002050212 | OBSOLETE EQUIPMENT | NW | TERRE HAUTE | IN-TERRE HAUTE-SR 42/US 231~ | 2023
N/A | 18883256 | 21592002050212 | PRESSURE MONITORING/SCADA/RTU | SE | CLARKSVILLE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 8 ERXS | 2023
N/A | 18880254 | 21582102050225 | PRESSURE MONITORING/SCADA/RTU | NE | ELWOOD | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 6 ERXs | 2023
N/A | 18883399 | 21583502050214 | PRESSURE MONITORING/SCADA/RTU | SE | FRANKLIN | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 4 ERXS | 2023
N/A | 18883464 | 21592302050210 | PRESSURE MONITORING/SCADA/RTU | SE | MADISON | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 6 ERXS | 2023
N/A | 18880576 | 21573302050219 | PRESSURE MONITORING/SCADA/RTU | NE | MUNCIE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 17 ERXS | 2023
N/A | 18881071 | 21575102050217 | PRESSURE MONITORING/SCADA/RTU | NE | RICHMOND | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 13 ERXs | 2023
N/A | 18883506 | 21583202050210 | PRESSURE MONITORING/SCADA/RTU | SE | SHELBYVILLE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 3 ERXS | 2023
N/A | 18881317 | 21595002050232 | PRESSURE MONITORING/SCADA/RTU | NW | TERRE HAUTE | Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - 3 ERXS | 2023
N-XA-11963 | 18747275 | 21573302050215 | REGULATOR STATION | NE | ALBANY | Install regulator station emergency inlet valve -CR 575 E - SOUTH OF SR 67 | 2023
N-XA-11958 | 18747247 | 21582102050221 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve -S/S OF 25TH ST - W OF LAYTON RD | 2023
N-XA-11959 | 18747248 | 21582102050222 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve -S/E CORNER OF 22ND ST & PITT ST | 2023
N-XA-11960 | 18747251 | 21582102050223 | REGULATOR STATION | NE | ANDERSON | Install regulator station emergency inlet valve -S/E CORNER OF 22ND ST & PITT ST | 2023
N-XA-11961 | 18747255 | 21573302050213 | REGULATOR STATION | NE | DALEVILLE | Install regulator station emergency inlet valve -CR 600 W - 1/2 MILE S OF SR 67 | 2023
N-X-4301 | 16225804 | 18202802054230 | REGULATOR STATION | NW | DANVILLE | IN-Danville- CR W 300 N under Interstate 65 N-X-4301-Distribution project in support of project 18202802054017 (12" HJC to Fox Retrofit). Install 1,300 feet of 4 inch plastic on CR W 300 N under Interstate 65 to connect an isolated distribution system (Reg. Station 53000057) to the Lebanon distribution system. | 2023
N-XA-11965 | 18747278 | 21573302050217 | REGULATOR STATION | NE | EATON | Install regulator station emergency inlet valve - E OF MERIDIAN ST - N OF CHURCH ST | 2023
N-XA-11946 | 18746072 | 21583502050213 | REGULATOR STATION | SE | FRANKLIN | Install regulator station emergency inlet valve -CR 525 EAST - SOUTH OF GREENSBURG ROAD | 2023
N-XA-11943 | 18746022 | 21592702050213 | REGULATOR STATION | SE | GREENSBURG | Install regulator station emergency inlet valve -E/S OF CR 60 E @ INTERSECTION OF CR 700 S | 2023
N-XA-11937 | 18745641 | 21592902050210 | REGULATOR STATION | SE | MARTINSVILLE | Install regulator station emergency inlet valve -843 MORTON AVENUE @ HACKER DRIVE | 2023
N-XA-11938 | 18745882 | 21592902050212 | REGULATOR STATION | SE | MARTINSVILLE | Install regulator station emergency inlet valve -SOUTH MORTON @ HACKER DRIVE | 2023
N-XA-11939 | 18745935 | 21592902050213 | REGULATOR STATION | SE | MARTINSVILLE | Install regulator station emergency inlet valve -SOUTH MORTON @ HACKER DRIVE | 2023
N-XA-11940 | 18745962 | 21592902050214 | REGULATOR STATION | SE | MARTINSVILLE | Install regulator station emergency inlet valve -COUNTY ROAD 150 S @ SEWAGE PLANT - 1285 ROGERS ROAD | 2023
N-XA-11941 | 18745992 | 21592902050215 | REGULATOR STATION | SE | MARTINSVILLE | Install regulator station emergency inlet valve -PLUMMER ROAD @ STATE ROAD 44 | 2023
N-XA-11942 | 18746007 | 21592902050216 | REGULATOR STATION | SE | MARTINSVILLE | Install regulator station emergency inlet valve -DEERFIELD FARMS @ STATE ROAD 44 | 2023
N-XA-12031 | 18747282 | 21573302050218 | REGULATOR STATION | NE | MT SUMMIT | IN-Mt Summit-W CR 400 N 51' E OF N & S RR - 850' S OF W CR 400 N | 2023
N-XA-11962 | 18747262 | 21573302050214 | REGULATOR STATION | NE | MUNCIE | Install regulator station emergency inlet valve -EAST CENTENNIAL - EAST OF ELGIN ST | 2023
N-XA-11964 | 18747276 | 21573302050216 | REGULATOR STATION | NE | MUNCIE | Install regulator station emergency inlet valve -DELAWARE RD - S OF MT PLEASANT BLVD | 2023
N-XA-11966 | 18747280 | 21575202050210 | REGULATOR STATION | NE | NEW CASTLE | Install regulator station emergency inlet valve -IN-New Castle-E CR 300 N 1100' E OF SR 3 & 12' S OF E CR 300 N | 2023
N-XA-11957 | 18747245 | 21582102050220 | REGULATOR STATION | NE | PENDLETON | Install regulator station emergency inlet valve - CR -625 W @ 1/2 MILE N OF SR 38 | 2023
N-XA-11944 | 18746060 | 21592802050210 | REGULATOR STATION | SE | SEYMOUR | Install regulator station emergency inlet valve -E/S OF SR11 - 0.7 MILES NORTH OF I-65 | 2023
N-XA-11945 | 18746063 | 21592802050212 | REGULATOR STATION | SE | SEYMOUR | Install regulator station emergency inlet valve -W/S OF SR11 - 1.5 MILES SOUTH OF I-65 | 2023
N-XA-11947 | 18746402 | 21595002050222 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -N/E CORNER OF N 17TH ST @ LEE AVE | 2023
N-XA-11948 | 18746405 | 21595002050223 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve - N/E CORNER OF N 16TH ST @ ELIZABETH ST | 2023
N-XA-11949 | 18746406 | 21595002050224 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -LATTA MOBILE HOME PARK | 2023
N-XA-11950 | 18746407 | 21595002050225 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -W/S OF SR 150 @ WOODLAND AVE | 2023
N-XA-11951 | 18746408 | 21595002050226 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -W/S OF SR 150 @ FERGUSON HILL | 2023
N-XA-11952 | 18746409 | 21595002050227 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -FRUITRIDGE AVE @ LINDEN ST | 2023
N-XA-11953 | 18746410 | 21595002050228 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -US HIGHWAY 40A @ ROBINWOOD LN | 2023
N-XA-11954 | 18746411 | 21595002050229 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -N/W CORNER OF WABASH AVE & BOURNE ST | 2023
N-XA-11955 | 18746412 | 21595002050230 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -N/W CORNER OF WABASH AVE & BOURNE ST | 2023
N-XA-11956 | 18746413 | 21595002050231 | REGULATOR STATION | NW | TERRE HAUTE | Install regulator station emergency inlet valve -W/S OF SR 63 @ DEMOREST ST | 2023
N-XA-11765 | 13999958 | 19595402051210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LEBANON | IN - Lebanon - S OUTER DR - Replace obsolete regulator S OUTER DR Valve Repair- Replacing obsolete regulator. | 2023
N-X-3906 | N/A | N/A | BRIDGE CROSSINGS | SE | GREENSBURG | IN-GREENSBURG-DECATUR COUNTY BRIDGE #102~~REPLACE 6" HP STL MAIN | 2024
N-X-1706 | N/A | N/A | EXPOSURES | SE | MITCHELL | IN-MITCHELL-SHOALS LINE EXPOSURE #12~~REPLACE 500' OF 6" STL MAIN AT HACK AND BAKER PROPERTY | 2024
N-X-1702 | N/A | N/A | EXPOSURES | SE | SHOALS | IN-SHOALS-SHOALS LINE EXPOSURE # 2 AND # 3~~REPLACE 500' OF 6" STL MAIN | 2024
N-X-1705 | N/A | N/A | EXPOSURES | SE | SHOALS | IN-SHOALS-SHOALS LINE EXPOSURE # 9, # 10, AND # 11~~REPLACE 500' OF 6" STL MAIN IN CREEK WEST OF HINDOSTAN LANE | 2024
Multiple | Multiple | Multiple | INSIDE METERS | VEDIN | MULTIPLE | INSIDE METERS - relocate inside meters to exterior of structure | 2024
N-X-9999 | N/A | N/A | LEGACY PLASTIC | SE | NEW ALBANY | IN-NEW ALBANY-SILVER HILLS RESIDENTAL SUBDIVISION~~REPLACE UNLOCATABLE MP PLASTIC MAIN. REPLACE/INSTALL 6000' OF 2" HDPE AND 115 SERVICES. | 2024
N-X-3004 | 18455214 | 2159502050214 | LEGACY PLASTIC | NW | ROCKVILLE | IN-ROCKVILLE-HERMAN LN/INDIANA ST~~REPLACE VINTAGE PLASTIC MAIN SECTIONS - REPLACE APPROX. 4,100 FT OF 2" AND APPROX. 2,400 FT OF 4" MAIN. REPLACE APPROX. 80 SERVICES. | 2024
N-X-14702 | N/A | N/A | LEGACY STEEL | SE | BEDFORD | IN-BEDFORD-9TH ST/I ST~~REPLACE 5,600' OF 8" HP INEFFECTIVELY COATED STL MAIN | 2024
N-X-16770 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-SR45~~REPLACE 5,500' OF 4" INEFFECTIVELY COATED STL MAIN AND 85 SERVICES | 2024
N-X-16771 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-SR45~~REPLACE 5,800' OF 4" INEFFECTIVELY COATED STL MAIN AND 90 SERVICES | 2024
N-X-16930 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-HIGH ST/WOODSTOCKDR~~REPLACE 7,320' OF 4" INEFFECTIVELY COATED STL MAIN AND 80 SERVICES | 2024
N-X-13201 | N/A | N/A | LEGACY STEEL | NW | BROWNSBURG | IN-BROWNSBURG-S Jefferson St DIMP Project ID 416 - 02.26.2021 - Ineffectively Coated Steel - Replace approx. 1,400' of 2" MP Steel main along S Jefferson St between. E Tilden and Hamilton St and approx. 400' of 2" MP Steel main along Maplebrook between Jefferson and School St. Total service replace approx. 40 services. | 2024
N-X-9758 | N/A | N/A | LEGACY STEEL | SE | CLARKSVILLE | IN-CLARKSVILLE-N MARSHALL ST~~REPLACE 1,400' OF 2" INEFFECTIVELY COATED MP STL MAIN AND 32 SERVICES | 2024
N-XA-12122 | N/A | N/A | LEGACY STEEL | NW | CLINTON | IN-CLINTON-E SR163 - JUST EAST OF INT OF SR63 IN - CLINTON - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 1,000 FT OF EXISTING 6" STEEL MAIN AND REPLACE APPROX. 6 SERVICES. | 2024
N-X-15990 | N/A | N/A | LEGACY STEEL | SE | COLUMBUS | IN-COLUMBUS~~TAYLOR RD, COVE RD, PARK VALLEY, LAKESIDE DR, SADDLE DR, SOUTH DR, SHANNON CT, AND CLOVER CT.-REPLACE 7,250' OF INEFFECTIVELY COATED STL MAIN AND 111 SERVICES | 2024
N-X-16702 | N/A | N/A | LEGACY STEEL | NW | GREENCASTLE | IN-GREENCASTLE-Cameron Dr Ineffectively coated steel - DIMP Project ID 49 Area - Replace approx. 600' of existing 2" MP Steel main located along Cameron Dr, between Arlington and Linwood; and approx. 800' of existing 2" MP Steel main located along Ritter Dr, between Cameron and Tacoma Street. Replace approx. 20 services. | 2024
N-X-16260 | N/A | N/A | LEGACY STEEL | SE | HOPE | IN-HOPE~~JACKSON ST, WASHINGTON ST, ALLEY WEST OF ELM ST, ALLEY WEST OF MARKET ST, AND DEPOT ST.REPLACE 7,000' INEFFECTIVELY COATED STL MAIN AND 108 SERVICES | 2024
N-X-9659 | N/A | N/A | LEGACY STEEL | SE | JEFFERSONVILLE | IN-JEFFERSONVILLE-MORRIS ST/LYNNDALE ST~~REPLACE 1,200' OF 2" AND 1,100' OF 4" INEFFECTIVELY COATED MP STL MAIN AND 72 SERVICES | 2024
N-X-17901 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-Owen St DIMP Project ID 417 - 02.26.2021 - Vintage Plastic - Replace approx. 1,200' of 2" MP Plastic main along Owen St, between S 9th St and Highland Ave; and approx. 320' of 2" Plastic main along Wea St, between Central Ave and Owen Street. Replace approx. 28 services. | 2024
N-X-17902 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-Adams St DIMP Project ID 418 - 02.26.2021 - Vintage Plastic - Replace approx. 850' of 2" MP Plastic main along Adams St, between S 16th St and 14th Street. Replace approx. 35 services. | 2024
N-X-17912 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-Erie St Ineffectively coated steel - Replace approx. 1,000' of 4" MP Steel main along Ferry St, between Erie St and Tinkler St; and approx. 450' of 4" MP Steel main along Carson St, between Tinkler and Asher Street. Replace approx. 22 services. | 2024
N-X-9960 | N/A | N/A | LEGACY STEEL | SE | MADISON | IN-MADISON-ALLEY BETWEEN 2ND ST/MAIN ST~~REPLACE 1,900' OF 3" INEFFECTIVELY COATED STL MAIN AND 53 SERVICES | 2024
N-XA-12121 | N/A | N/A | LEGACY STEEL | NW | MARSHALL | IN-MARSHALL-MAIN STREET IN - MARSHALL - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 500 FT OF EXISTING 2" STEEL MAIN AND REPLACE APPROX. 4 SERVICES. ALSO REPLACE 2 EXISTING MAIN LINE VALVES | 2024
Multiple | Multiple | Multiple | LEGACY STEEL | VEDIN | MULTIPLE | ISOLATED SERVICES - replaced isolated services | 2024
N-X-13208 | N/A | N/A | LEGACY STEEL | NW | PLAINFIELD | IN-Plainfield-South St, Buchanan St Ineffectively Coated Steel - Legacy Map 46-312 - Replace approx. 9,000' of 2" MP Steel main along Center St, South St, Buchanan St, Carter St, Mill St, Vine St, and Lewis St; between Mill Street, East St, and Main St (US40 - Downtown Area) Replace approx. 120 services | 2024
N-X-4708 | 18120388 | N/A | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 9,100' OF INEFFECTIVELY COATED LP STL MAIN AND 75 SERVICES | 2024
N-X-4709 | 18124755 | N/A | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 9,500' OF INEFFECTIVELY COATED LP STL MAIN AND 70 SERVICES | 2024
N-X-4807 | 18120388 | N/A | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 4,950' OF INEFFECTIVELY COATED LP STL MAIN AND 80 SERVICES | 2024
N-X-5010 | 18120395 | N/A | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 10,400' OF INEFFECTIVELY COATED LP STL MAIN AND 75 SERVICES, RETIRE REG STA 1829 & 1818 | 2024
N-X-5011 | 18120398 | N/A | LEGACY STEEL | NE | RICHMOND | IN-RICHMOND~~REPLACE 6,500' OF INEFFECTIVELY COATED LP STL MAIN AND 50 SERVICES | 2024
N-X-12304 | N/A | N/A | OBSOLETE EQUIPMENT | NW | ATTICA | Replace the Regulator Outlet Valve and Regulator at Reg. Station No. 4 - Kentucky Street - Attica Replace Obsolete Equipment - Replace Valve to Remedy a Leak | 2024
N-X-11201 | N/A | N/A | OBSOLETE EQUIPMENT | NW | FRANKFORT | Replace the Relief Blocking Valve at Reg. Station No. 60000292 - Fox Station - Frankfort Replace Obsolete Equipment - Replace Valve to Remedy a Leak | 2024
N-X-3003 | 18063029 | 20595702050210 | OBSOLETE EQUIPMENT | NW | FRANKFORT | IN-FRANKFORT-FRANKFORT LOOP~~1950 STL - 6" FRANKFORT LOOP - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 7,700 FT OF EXISTING 6" STL MAIN. REPLACE APPROX. 64 SERVICES. | 2024
N--X-4002 | 1845566 | 2159552050216 | OBSOLETE EQUIPMENT | NW | GREENCASTLE | IN-GREENCASTLE-SR42/US231~~FIRST CUT REMOVAL-CLOVERDALE-SR42/US231~CLAY COUNTY - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 5,300 FT OF 6" MP STEEL MAIN ALONG SR42 - BTWN CR 200E, HEADING EAST TO MCINTYRE CREEK. REPLACE APPROX. 20 SERVICES. | 2024
N-X-5003 | N/A | N/A | OBSOLETE EQUIPMENT | NW | GREENCASTLE | IN-GREENCASTLE-SR42/US231~~FIRST CUT REMOVAL- PUTNAM COUNTY - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 5,500 FT OF 6" MP STEEL MAIN ALONG SR42. REPLACE APPROX. 12 SERVICES. | 2024
Multiple | Multiple | Multiple | Obsolete Equipment | VEDIN | MULTIPLE | OBSOLETE RISERS - replace obsolete service risers | 2024
N-X-2004 | N/A | N/A | OBSOLETE EQUIPMENT | NW | TERRE HAUTE | IN-TERRE HAUTE-SR42/US231~~FIRST CUT REMOVAL SR 42 - CLAY CO. - BTWN EAST FORK BIRCH CREEK AND CR200E. REPLACE APPROX. 10,000' OF INEFFECTIVELY COATED 6" STEEL MP MAIN. REPLACE APPROX. 12 SERVICES. | 2024
N-X-12303 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | NW | ATTICA | IN-ATTICA-ERX Replace 2 Replace obsolete paper chart recorders with electronic pressure measurement (ERX) in Attica - Replace Obsolete Equipment | 2024
N-X-11003 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | CLARKSVILLE | IN-CLARKSVILLE-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - | 2024
N-X-11004 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | CLARKSVILLE | IN-CLARKSVILLE-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - | 2024
N-X-10302 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | COLUMBUS | IN-COLUMBUS-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - | 2024
N-X-10303 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | COLUMBUS | IN-COLUMBUS-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - | 2024
N-X-2096 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | COLUMBUS | IN-COLUMBUS- Pressure Monitoring / SCADA / RTU, replacing the existing chart | 2024
N-X-13003 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | GREENFIELD | IN-GREENFIELD-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) - | 2024
N-X-2104 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | SEYMOUR | IN-SEYMOUR- Pressure Monitoring / SCADA / RTU, replacing existing chart | 2024
N-XA-11835 | N/A | N/A | REGULATOR STATION | NW | DANVILLE | Replace the Relief Blocking Valve at Reg. Station No. 60000292 - Fox Station - Frankfort Replace Obsolete Equipment - Replace Valve to Remedy a Leak | 2024
N-XA-11844 | N/A | N/A | REGULATOR STATION | SE | FRANKLIN | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2024
N-X-394 | N/A | N/A | REGULATOR STATION | SE | MARTINSVILLE | IN-MARTINSVILLE-LIBERTY CHURCH RD~~REBUILD REG STA 40000074 DUE TO BEING IN A PIT | 2024
N-XA-11834 | N/A | N/A | REGULATOR STATION | NE | MUNCIE | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2024
N-X-3907 | N/A | N/A | SHALLOW PIPE | SE | GREENSBURG | IN-GREENSBURG-CR E 650 S~~REPLACE 5,142' OF 2" SHALLOW STL MAIN AND 3 SERVICES EAST OF CR S 60 E | 2024
N-XA-11783 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | ATTICA | IN - Attica - Station 51000004 - Attica Station 51000004 Broken Outlet Valve | 2024
N-X-4233 | N/A | N/A | ENCROACHMENTS | SE | BLOOMINGTON | IN-BLOOMINGTON-LAMPLIGHTER ESTATES MOBILE~~REPLACE 2,400' OF 2" MP STL MAIN AND 39 SERVICES DUE TO TRAILERS ENCROACHING ON MAIN | 2025
N-X-409 | N/A | N/A | EXPOSURES | SE | BEDFORD | IN-SHOALS-SHOALS LINE EXPOSURE #28, 29, 30~~REPLACE 300' OF 6" EXPOSED STL MAIN IN CREEK | 2025
N-X-4884 | N/A | N/A | EXPOSURES | SE | BLOOMINGTON | IN-BLOOMINGTON-W BLOOMFIELD RD~~REMEDIATE 4" MP EXPOSED STL MAIN. INSTALL 500' OF 4" HDPE. NO SERVICES. | 2025
N-X-3872 | N/A | N/A | EXPOSURES | SE | FRANKLIN | IN-FRANKLIN-US31/MAUXFERRY RD~~REPLACE 500' OF 8" HP EXPOSED STL MAIN | 2025
N-X-3873 | N/A | N/A | EXPOSURES | SE | FRANKLIN | IN-FRANKLIN-US31/MAUXFERRY RD~~REPLACE 500' OF 8" HP EXPOSED STL MAIN | 2025
N-X-436 | N/A | N/A | EXPOSURES | SE | MARTINSVILLE | IN-MARTINSVILLE-BIG HURRICANE RD~~REPLACE 6" HP EXPOSED LINE. INSTALL 300' OF 6" STEEL. NO SERVICES. | 2025
N-X-443 | N/A | N/A | EXPOSURES | SE | MARTINSVILLE | IN-MARTINSVILLE-HINSON RD CREEK~~REPLACE 500' OF 10" HP LINE. INSTALL 500' OF 10' STEEL MAIN. NO SERVICES. | 2025
N-X-469 | N/A | N/A | EXPOSURES | SE | MARTINSVILLE | IN-MARTINSVILLE-OLD MOORE RD~~REPLACE 300' OF 6" EXPOSED STL MAIN. INSTALL 500' OF 6" STEEL MAIN. NO SERVICES. | 2025
N-X-4906 | N/A | N/A | EXPOSURES | SE | MARTINSVILLE | IN-MARTINSVILLE-LAMBS CREEK~~ Remediate exposed 8" MP steel main along bank of Lambs Creek south of Bain Rd. in Martinsville near 39.4510, -86.4933. INSTALL 500' OF 8" STEEL MAIN. NO SERVICES. | 2025
N-X-1709 | N/A | N/A | EXPOSURES | SE | MITCHELL | IN-MITCHELL-SHOALS LINE EXPOSURE #16 AND # 17~~REPLACE 500' OF 6" STL MAIN | 2025
N-X-3838 | 18027501 | 20575102050222 | EXPOSURES | SE | MITCHELL | IN-MITCHELL-MERIDIAN RD~~REMEDIATE 500' OF 8" HP EXPOSED STL MAIN IN CREEK | 2025
N-X-3839 | 18120367 | N/A | EXPOSURES | SE | MITCHELL | IN-MITCHELL-MERIDIAN RD~~REPLACE 500' OF 8" HP EXPOSED STL MAIN | 2025
N-X-4653 | N/A | N/A | EXPOSURES | SE | MITCHELL | IN-MITCHELL-OLD STATE HWY 37~~REMEDIATE 4" MP EXPOSED STL MAIN IN CREEK. REPLACE 500' OF 4" MP WITH 4" HDPE. NO SERVICES. | 2025
N-X-1703 | N/A | N/A | EXPOSURES | SE | SHOALS | IN-SHOALS-SHOALS LINE EXPOSURE #4~~REPLACE 500' OF 6" STL MAIN | 2025
N-X-1704 | N/A | N/A | EXPOSURES | SE | SHOALS | IN-SHOALS-SHOALS LINE EXPOSURE #5~~REPLACE 500' OF 6" STL MAIN | 2025
N-X-1708 | N/A | N/A | EXPOSURES | SE | SHOALS | IN-SHOALS-SHOALS LINE EXPOSURE # 14 AND # 15~~REPLACE 500' OF 6" STL MAIN | 2025
N-X-5006 | 18159315 | 20595002050214 | EXPOSURES | NW | ST. BERNICE | IN - ST. BERNICE - EXPOSURE - REPLACE APPROX. 500' OF EXIST. 2" STEEL MAIN. | 2025
Multiple | Multiple | Multiple | INSIDE METERS | VEDIN | MULTIPLE | INSIDE METERS - relocate inside meters to exterior of structure | 2025
N-X-5001 | N/A | N/A | LEGACY PLASTIC | NW | BROWNSBURG | IN-BROWNSBURG-GREEN ST/SYCAMORE ST~~REPLACE VINTAGE PLASTIC - REPLACE APPROX. 9,000 FT OF EXISTING 2" MAIN. REPLACE APPROX. 100 SERVICES. | 2025
N-X-2001 | 18455143 | 2159552050213 | LEGACY PLASTIC | NW | DAYTON | IN-DAYTON~~REPLACE VINTAGE PLASTIC Replacement of 1972 Vintage Plastic - Replace approx. 7,700' of existing 2" main. Replace approx. 99 services. | 2025
N-X-4891 | 17144495 | 19592402050210 | LEGACY PLASTIC | SE | ELLETTSVILLE | IN-ELLETTSVILLE-N DEER PARK~~ N-X-4891 - Replace Vintage Plastic. Replace approx. 1,402' of 3" & 981' of 2" pre-1974 Aldyl-A main with new 2" Plastic main and replace approx. 24 services along N Deer Park and adjacent cul-de-sacs in Ellettsville. | 2025
N-X-14101 | N/A | N/A | LEGACY PLASTIC | SE | GREENWOOD | IN-Greenwood-Countryside Drive-Part 1 Part 1: Replace 4050' of main and 149 services. DIMP Project 57 Project boundaries—Countryside Drive to the west, E Worthsville Road to the south, W Stop 18 Road to the north, and US HWY 31 to the east 0.33 miles of pre‐1974 plastic􀆟c Recommend􀆟on to target vintage plastic􀆟c. Risk targeted is Pipe, Weld, Joint Tier 2 facility􀆟es in this area are 3.41 miles of pre‐1984 plastic􀆟c and 1.02 miles of unknown install􀆟on date plastic􀆟c. Map Grid 191‐178 | 2025
N-X-14102 | N/A | N/A | LEGACY PLASTIC | SE | GREENWOOD | IN-Greenwood-Countryside Derive-Part 2 Part 2: Replace 6000' of main and 137 services. DIMP Project 57 Project boundaries—Countryside Drive to the west, E Worthsville Road to the south, W Stop 18 Road to the north, and US HWY 31 to the east 0.33 miles of pre‐1974 plastic􀆟c Recommend􀆟on to target vintage plastic􀆟c. Risk targeted is Pipe, Weld, Joint Tier 2 facility􀆟es in this area are 3.41 miles of pre‐1984 plastic􀆟c and 1.02 miles of unknown install􀆟on date plastic􀆟c. Map Grid 191‐178 | 2025
N-X-9998 | N/A | N/A | LEGACY PLASTIC | SE | JEFFERSONVILLE | IN-JEFFERSONVILLE- S INDIANA AVE/W MARKET ST~~ Reported from Local Ops - Unlocatable Plastic Main - MP: Replace approx. Southern Indiana Ave- Main and Services W Market St Between Southern Indiana and Market St Missouri Ave@ West Market. INSTALL 5000' OF 2" HDPE. REPLACE 100 SERVICES. | 2025
N-X-2002 | 18455149 | 21595502050214 | LEGACY PLASTIC | NW | LAFAYETTE | IN-LAFAYETTE-PARADISE/FOXWOOD/CREST DR~~ IN-LAFAYETTE-PARADISE/FOXWOOD/CREST DR~~REPLACE VINTAGE PLASTIC - REPLACE APPROX. 5,000' OF EXIST. 2" MAIN. REPLACE APPROX. 69 SERVICES. | 2025
N-X-1547 | N/A | N/A | LEGACY STEEL | NE | ALEXANDRIA | 11TH ST, HARRISON ST, PARK AVE, HANNAH ST, COOK ST, 9TH ST REPLACE 3,050' OF 4" MP STL PIPE. INSTALL 47 SERVICES | 2025
N-X-1548 | N/A | N/A | LEGACY STEEL | NE | ALEXANDRIA | SHELBY, MARION AVE, RANDOLPH AVE, 4TH ST, 8TH ST, 5TH ST, CLARK AVE REPLACE 5,150' OF 2" & 4" MP STL PIPE. INSTALL 80 SERVICES | 2025
N-XA-11745 | N/A | N/A | LEGACY STEEL | NE | ALEXANDRIA | In-Alexanria-7th Street INSTALL 6800 OF 2" MAIN OF STEEL PIPE-7TH AND 9TH STREETS-90 SERVICES | 2025
N-X-1641 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | RD 300 EAST, SCHOOL ST REPLACE 4,500' OF 2" MP STL PIPE. INSTALL 69 SERVICES | 2025
N-X-1722 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | MINSI DR, UNAMI DR, MIAMI DR, SENECA DR REPLACE 3,450' OF 2" MP STL PIPE. INSTALL 52 SERVICES | 2025
N-XA-11744 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | In-Anderson-8th Street INSTALL 3200' OF 8" STEEL AND 2630' OF 2" STEEL ALONG 8TH STREET FROM CHESTNUT TO SCATTERFIELD-50 SERVICES | 2025
N-XA-11746 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | In-Anderson-3rd Street INSTALL 5930 OF 2" AND 4" STEEL PIPE-3RD, 4TH AND FOWLER STREETS-110 SERVICES | 2025
N-XA-11747 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | In-Anderson-Harrison Street REPLACE 5,500' OF 2" & 4" MP STL PIPE. INSTALL 85 SERVICES | 2025
N-XA-11754 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | IN- ANDERSON-PARK ROAD, 18TH ST, MANGER LANE, ROSEWOOD DRIVE, WESLOW CT REPLACE 5,500' OF 2" & 4" MP STL PIPE. INSTALL 85 SERVICES | 2025
N-XA-11755 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | SUNSET BLVD, CANADAY DR, LORAL DR, SUNNYSIDE DR, VALLEY GROVE RD REPLACE 7,150' OF 2" & 4" MP STL PIPE. INSTALL 110 SERVICES | 2025
N-XA-11756 | N/A | N/A | LEGACY STEEL | NE | ANDERSON | 38TH ST, PITT ST, CLARK ST, ST CHARLES ST, LYNN ST, 46TH ST, SADDLE LANE REPLACE 3600' OF 2" MP STL PIPE. INSTALL 56 SERVICES | 2025
N-X-12301 | N/A | N/A | LEGACY STEEL | NW | ATTICA | IN-Attica-Sycamore-Brady Ineffectively Coated Steel - Legacy Map 130-131 - Replace approx. 5,500' of 2" MP Steel main along Sycamore, Brady, McDonald, and Division St ; between Perry, Pine, Division, and Sycamore; just north of Sycamore St. Replace approx. 90 services | 2025
N-X-10001 | N/A | N/A | LEGACY STEEL | SE | BEDFORD | IN-BEDFORD-OLD SR37/DIXIE HIGHWAY~~REPLACE 4,000' OF 4" INEFFECTIVELY COATED STL MAIN AND 21 SERVICES | 2025
N-X-10002 | N/A | N/A | LEGACY STEEL | SE | BEDFORD | IN-BEDFORD-ALLEY BETWEEN 4TH ST & 8TH ST~~REPLACE 1,100' OF 4" AND 800' OF 6" INEFFECTIVELY COATED STL MAIN AND 9 SERVICES | 2025
N-X-10003 | N/A | N/A | LEGACY STEEL | SE | BEDFORD | IN-BEDFORD-WHITE RIVER CROSSING~~REPLACE 5,000' OF 4" INEFFECTIVELY COATED STL MAIN AND 7 SERVICES | 2025
N-X-14703 | N/A | N/A | LEGACY STEEL | SE | BEDFORD | IN-BEDFORD-EASTVIEW DR/22ND ST~~ IN-BEDFORD-EASTVIEW DR/22ND ST~~REPLACE 1, 950' 8" HP INEFFECTIVELY COATED STL MAIN | 2025
N-X-15303 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-Bloomington- Allendale Drive Ineffective Coated Steel - Replace approx. 1,600' of 2" Steel and 2,700' of 4" Steel main located along Allendale Drive between Winslow Road and Bainbridge Drive (Map 29-246); also includes replacing approx. 78 services. | 2025
N-X-15305 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-Bloomington-Sunny Slopes Drive Ineffective Coated Steel - Replace approx. 6,400' of 2" Steel and 700' of 4" Steel main located along Sunny Slopes Drive and Ridgeview Drive between S Walnut Street and S Walnut St Pike, also includes the area along S Walnut St Pike between Sherwood Hills Drive and Allendale Drive (Map 29-245); also includes replacing approx. 106 services. | 2025
N-X-15306 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-Bloomington-South Old State Road 37 Ineffective Coated Steel - Replace approx. 6,000' of 6" Steel main located along South Old State Road 37, between Dellsville Road and Zikes Road; to the south of the Bloomington City Limits (Maps 29-312, 29-329, 29-346); also includes replacing approx. 64 services. | 2025
N-X-15307 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-Bloomington-Westminster Drive Unlocatable Vintage Plastic - Replace approx. 6,700' of 2" plastic main located along Westminster Drive, Buckingham Drive, and Piccadilly Drive between Winslow Road and Allendale Drive (Map 29-245); also includes replacing approx. 170 services. | 2025
N-X-16790 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-GOURLEY PIKE/KINSER PIKE~~REPLACE 5,000' OF 4" INEFFECTIVELY COATED STL MAIN AND 37 SERVICES | 2025
N-X-16791 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTONARLINGTON RD~~REPLACE 1,700' OF 6" AND 1,800' OF 2" INEFFECTIVELY COATED STL MAIN AND 40 SERVICES | 2025
N-X-17000 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-MADISON ST/BRYAN ST~~REPLACE 4,450' OF 2" INEFFECTIVELY COATED STL MAIN AND 70 SERVICES | 2025
N-X-17010 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-MILTON AVE~~REPLACE 6,000' OF 4" INEFFECTIVELY COATED STL MAIN AND 80 SERVICES | 2025
N-X-17011 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-BROWN AVE/BROADVIEW DR~~REPLACE 4,800' OF 2" INEFFECTIVELY COATED STL MAIN AND 80 SERVICES | 2025
N-X-268 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-BLOOMINGTON-MUSGRAVE'S HORSE RANCH~~REPLACE 500' OF 10" STL MAIN NORTH OF MUSGRAVE'S HORSE RANCH | 2025
N-X-13202 | N/A | N/A | LEGACY STEEL | NW | BROWNSBURG | IN-BROWNSBURG-E Tilden St DIMP Project ID 416 - 02.26.2021 - Ineffectively Coated Steel - Replace approx. 1,200' of 4" MP Steel main along E Tilden between S Jefferson St and Grant St; and approx. 1,100' of 4" MP Steel main along S School St between Tilden and Hamilton St; and approx. 900' of 2" MP Steel main along Gordon Court from Tilden St to Terminus; and approx. 500' of 2" MP Steel main along Maplebrook between School and Grant St; and approx. 600' pf 2" MP Steel main along Jackson St between Maplebrook and Jackson Court. Total service replace approx. 80 services. | 2025
N-X-13204 | N/A | N/A | LEGACY STEEL | NW | BROWNSBURG | IN-Brownsburg-Locust Ineffectively Coated Steel - Legacy Map 46-132 - Replace approx. 8,000' of 2" MP Steel main along Locust, between Tilden and Dover; Eaton, Hamben, Weston (Alpha South), Dover, Thornleigh, Briarwood, Foxwood, Brownsburg Dr., Beechwood, Dogwood. Replace approx. 120 services. | 2025
N-X-9958 | 17509967 | 20592002050210 | LEGACY STEEL | SE | CLARKSVILLE | IN-CLARKSVILLE-TAGGART AVE/ANDALUSIA AVE IN-CLARKSVILLE-TAGGART AVE/ANDALUSIA AVE~~REPLACE 1,150' OF 2", 1,200' OF 4" AND 300' OF 6" INEFFECTIVELY COATED STL MAIN AND 73 SERVICES | 2025
N-X-16230 | N/A | N/A | LEGACY STEEL | SE | CLIFFORD | IN-CLIFFORD~~550 N, POPLAR ST, WASHINGTON ST, MILL ST, SUGAR ST, AND 250 E.REPLACE 7,450' INEFFECTIVELY COATED STL MAIN AND 115 SERVICES | 2025
N-X-53510 | N/A | N/A | LEGACY STEEL | SE | COLUMBUS | IN-COLUMBUS- Replace 4350' and services and 87 services. Ineffective coated steel: (Leaks) Replace 4350' and services and 87 services. | 2025
N-X-1834 | 17503975 | 20583502050212 | LEGACY STEEL | SE | EDINBURGH | IN-EDINBURGH-COUNTY LINE RD & THOMPSON ST REPLACE VARIOUS SIZE PIPELINE WITH APPROX 5,600' OF 2" PL MAIN AND APPROX 73 SERVICES DUE TO POOR CATHODIC PROTECTION AND LEAK HISTORY. LOCATION IS BETWEEN COUNTY LINE RD & THOMPSON ST AND WALNUT ST & EISENHOWER DR | 2025
N-X-1543 | N/A | N/A | LEGACY STEEL | NE | ELWOOD | NORTH E,18TH ST, ALLEY WEST OF, NORTH D ST, ALLEY NORT, 26TH ST REPLACE 5,950' OF 2" MP STL PIPE. INSTALL 93 SERVICES | 2025
N-X-1544 | N/A | N/A | LEGACY STEEL | NE | ELWOOD | JACKLEY RD, EAST DRIVE, ROAD 1200 NORTH REPLACE 1,900' OF 2" MP STL PIPE. INSTALL 29 SERVICES | 2025
N-X-1745 | N/A | N/A | LEGACY STEEL | NE | ELWOOD | CARTER ADD EASEMENTS SOUTH OF, ROAD 900 WEST, ROAD 1300 NORTH REPLACE 2,950' OF 2" & 4" MP STL PIPE. INSTALL 61 SERVICES | 2025
N-X-1746 | N/A | N/A | LEGACY STEEL | NE | ELWOOD | 16TH ST, ALLEY WEST OF, NORTH K ST, 18TH ST, NORTH J ST, 19TH ST, PARKVIEW REPLACE 3,480' OF 4" MP STL PIPE. INSTALL 54 SERVICES | 2025
N-X-16703 | N/A | N/A | LEGACY STEEL | NW | GREENCASTLE | IN-GREENCASTLE- Highwood St Ineffectively coated steel - DIMP Project ID 49 Area - Replace approx. 900' of existing 2" MP Steel main located along Highwood St, between Arlington and Highridge Ave; and approx. 800' of existing 4" MP Steel main located along Terrace Dr, between Arlington and Redbud St; and approx. 800' of 4" MP Steel main along Redbud, between Terrace and Shadowlawn; and approx. 750' of 2" MP Steel main along Dogwood, between Redbud and Shadowlawn Street. Replace approx. 62 services. | 2025
N-X-16270 | N/A | N/A | LEGACY STEEL | SE | HOPE | IN-HOPE~~ALLEY NORTH OF WASHINGTON ST, WASHINGTON ST, MILL ST, LOCUST ST, SEMINARY ST, ALLEY WEST OF BROAD ST, ALLEY WEST OF MAPLE ST, AND ALLEY WEST OF WALNUT STREPLACE 6,800' OF INEFFECTIVELY COATED STL MAIN AND 105 SERVICES | 2025
N-X-16280 | N/A | N/A | LEGACY STEEL | SE | HOPE | IN-HOPE~~ALLEY WEST OF MAIN ST, ALLEY WEST OF HARRISON ST, ALLEY WEST OF VINE ST, JACKSON ST, VINE DR, AND WASHINGTON ST. REPLACE 6,650' OF INEFFECTIVELY COATED STL MAIN AND 102 SERVICES | 2025
N-X-1732 | N/A | N/A | LEGACY STEEL | NE | HUNTINGTON | GARDENDALE, ALLEY EAST OF CHARLES S, COLUMBIA, BRIANT, GARFIELD REPLACE 8,780' OF 4" & 6" & 8" MP STL PIPE. INSTALL 136 SERVICES | 2025
N-X-17903 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-Virginia St DIMP Project ID 418 Area - 02.26.2021 - Vintage Plastic - Replace approx. 900' of 2" MP Plastic main along Virginia St, between S 16th St and 14th Street. Replace approx. 28 services. | 2025
N-X-17911 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-Ferry St Vintage Plastic - Replace approx. 1,400' of 2" MP Plastic main along Ferry St, between 19th St and Tinkler St; and approx. 500' of 2" Plastic main along 19th St, between Ferry and South Street. Replace approx. 42 services. | 2025
N-X-17913 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-Kossuth to the south DIMP Project ID 419 Area - 02.26.2021 - Vintage Plastic - Replace approx. 5,100' of 2" MP Plastic main between Kossuth to the south, S 18th St to the east, Heath to the north, Wabash to the west. Western Replacement Area. Replace approx. 100 services. | 2025
N-X-9860 | N/A | N/A | LEGACY STEEL | SE | MADISON | IN-MADISON-PRESBYTERIAN AVE~ Madison Heat Map Area 3 - Ineffectively Coated Steel - MP" Replace approx. 4,800' of 2" Steel main and 57 services along Presbyterian Ave, W 3rd St, and Crossing Main St between W 3rd St and W 2nd Street. | 2025
N-X-10000 | N/A | N/A | LEGACY STEEL | SE | MITCHELL | IN-MITCHELL-CITY OF MITCHELL WASTE WATER TREATMENT PLANT~~REPLACE 200' OF 8" INEFFECTIVELY COATED HP STL MAIN AND EXISTING INLINE TEE FITTING | 2025
N-X-10004 | N/A | N/A | LEGACY STEEL | SE | MITCHELL | IN-MITCHELL-OLD SR37/DIXIE HIGHWAY~~6,400' OF 4" INEFFECTIVELY COATED STL MAIN AND 21 SERVICES | 2025
Multiple | Multiple | Multiple | LEGACY STEEL | VEDIN | MULTIPLE | ISOLATED SERVICES - replaced isolated services | 2025
N-X-1418X | N/A | N/A | LEGACY STEEL | NE | MUNCIE | NEELEY AVE, WHEELING AVE , NEW YORK AVE, RIVERSIDE DR REPLACE 8,450' OF 2" & 6" MP STL PIPE. INSTALL 127 SERVICES | 2025
N-XA-11850 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-Main Street 9400' MAIN 70 SERVICES | 2025
N-XA-11852 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-SR 167 8700' MAIN 0 SERVICES | 2025
N-XA-11848 | N/A | N/A | LEGACY STEEL | NE | NOBLESVILLE | IN-Noblesville-ROXBURY LANE 6235' MAIN 90 SERVICES | 2025
N-XA-11849 | N/A | N/A | LEGACY STEEL | NE | NOBLESVILLE | IN-Noblesville-PERSIMON PL 5615' MAIN 80 SERVICES | 2025
N-X-13207 | N/A | N/A | LEGACY STEEL | NW | PLAINFIELD | IN-Plainfield-Center St Ineffectively Coated Steel - Legacy Map 46-292 - Replace approx. 7,700' of 2" MP Steel main along Center St, Lincoln St, North St, Avon St, Vine St, and Krewson St; between Mill Street, CR300S, and Main St (US40), just west of SR267 (Avon Ave.) Replace approx. 90 services. | 2025
N-X-16310 | N/A | N/A | LEGACY STEEL | SE | TAYLORSVILLE | IN-TAYLORSVILLE~~CHARLES LN, DACIA ST, WALNUT ST, RESERVOIR ST, AND EVELYN ST. -REPLACE 5,000' OF INEFFECTIVELY COATED STL MAIN AND 52 SERVICES | 2025
N-X-16311 | N/A | N/A | LEGACY STEEL | SE | TAYLORSVILLE | IN-TAYLORSVILLE~~WALNUT ST, RESEVOIR ST, FRANKLIN ST, AND GRACE ST.-REPLACE 5,000' OF INEFFECTIVELY COATED STL MAIN AND 52 SERVICES | 2025
N-X-16320 | N/A | N/A | LEGACY STEEL | SE | TAYLORSVILLE | IN-TAYLORSVILLE~~TANNEHILL RD, MAIN ST, EAST ST, WALNUT ST, PEARL ST, AND MULBERRY ST. -REPLACE 8,050' OF INEFFECTIVELY COATED STL MAIN AND 123 SERVICES | 2025
N-X-16701 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-Cloverdale Replace Existing HP Distribution Mains Due To Existing Conditions Being Shallow. Replace approx. 3,200' of existing 6" HP Steel Distribution Main and approx. 3,200' of existing 4" HP Steel Distribution Main, near Cloverdale to the East of US231 and to the South of US40 from approx. Upper Limestone Creek - heading South | 2025
N-X-18401 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-1st Street 10" MP Steel Main - Replace existing main and services located along Hulman Street between. 1st Street and 6th Street - Ineffectively Coated Steel - Replace approx. 2,000 FT of Existing 10" STL main and replace approx. 10 services. | 2025
N-X-18402 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-Lockport Rd NW Future TH MOD Project 2 - Replace 12" HP Steel Main Pipe Section and Valve Located Near INRR Xing at Lockport Rd - Ineffectively Coated Steel - Replace approx. 1,400 FT of Existing 12" HP STL main. | 2025
N-X-18405 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-1st St and Arleth Ineffectively coated steel - DIMP Project ID 46 Area - Map 34-195 - Replace approx. 200' of existing 4" MP Steel main located along Vorhees St, between 1st Street and Arleth; and approx. 1,250' of existing 2" MP Steel main located along Alley between 1st St and Arleth, between Voorhees and Demorest St; and approx. 1,200' of 2" MP Steel main along Alley between Arleth and Dillman, between Voorhees and Demorest; and approx. 450' of 2" Steel in Alley between Dillman and Prairietown, between Demorest and Boring; and approx. 850' of 2" MP Steel main along Demorest St, between 1st St and Prairietown Street. Replace approx. 44 services. | 2025
N-X-18406 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-Farrington St Ineffectively coated steel - DIMP Project ID 48 Area - Replace approx. 700' of existing 4" MP Steel main located along Farrington St, between 5th Street and 3rd Street; and approx. 2,300' of existing 2" MP Steel main located along the Alley between 3rd St and 5th St, between College and Walnut Street. Replace approx. 40 services. | 2025
N-X-1747 | N/A | N/A | LEGACY STEEL | NE | TIPTON | ADAMS ST, ALLEY NORTH OF, S EAST ST, ALLEY WEST OF REPLACE 760' OF 6" MP STL PIPE. INSTALL 12 SERVICES | 2025
N-X-5002 | N/A | N/A | LEGACY STEEL | NW | VEEDERSBURG | IN-VEEDERSBURG~~STEEL-UNKNOWN THIN WALLED HP DISTRIBUTION - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 6,000 FT OF EXIST. 4" HP STEEL MAIN. | 2025
N-X-17910 | N/A | N/A | LEGACY STEEL | NW | WEST POINT | IN-WEST POINT-S CR600W Ineffectively coated steel - Replace approx. 5,300' of 10" HP Steel main located along W CR500 S, S CR600W and S CR500W. This project will also eliminate approx. 6 existing blow down valves. | 2025
N-X-17921 | N/A | N/A | OBSOLETE EQUIPMENT | NW | LAFAYETTE | Replace the Valves Nos. 59002167 and 59002171 at Reg. Station No. 59000870 - West TBS - Lafayette Replace Obsolete Equipment - Replace Valves to Remedy Leaks | 2025
Multiple | Multiple | Multiple | Obsolete Equipment | VEDIN | MULTIPLE | OBSOLETE RISERS - replace obsolete service risers | 2025
N-X-11001 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | CLARKSVILLE | IN-CLARKSVILLE-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) Michigan Rd, Tube Mill | 2025
N-X-11002 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | CLARKSVILLE | IN-CLARKSVILLE-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) 3rd St Parking Riser | 2025
N-X-10301 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | COLUMBUS | IN-COLUMBUS-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) Greensburg Michigan Ave. | 2025
N-X-13001 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | GREENFIELD | IN-GREENFIELD-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) C.R. 250 W. #48-1180 | 2025
N-X-13002 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | SE | GREENFIELD | IN-GREENFIELD-ERX Replace obsolete paper chart recorders with electronic pressure measurement (ERX) Ingalls Sewer Plant | 2025
N-X-18409 | N/A | N/A | PRESSURE MONITORING/SCADA/RTU | NW | TERRE HAUTE | IN-TERRE HAUTE-ERX Replace 2 Replace obsolete paper chart recorders with electronic pressure measurement (ERX) in Terre Haute | 2025
N-X-3949 | 15157435 | 18582102050212 | REGULATOR STATION | NE | ANDERSON | IN-ANDERSON-MOUNDS MALL~ REBUILD CORRODING REG STA 1395 | 2025
N-XA-11839 | N/A | N/A | REGULATOR STATION | NW | DANVILLE | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2025
N-XA-11840 | N/A | N/A | REGULATOR STATION | SE | FRANKLIN | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2025
N-X-402 | N/A | N/A | REGULATOR STATION | SE | MARTINSVILLE | IN-MARTINSVILLE-SR37/EGBERT RD~~REBUILD REG STA 40000020 DUE TO BEING IN A PIT | 2025
N-XA-11838 | N/A | N/A | REGULATOR STATION | NE | MUNCIE | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2025
N-X-1693XT | 15157320 | 18582102050215 | SHALLOW PIPE | NE | ANDERSON | IN-ANDERSON-SCATTERFIELD REPLACE 4,300' OF 10" HP STL PIPE. INSTALL 9 SERVICES | 2025
N-X-5013 | 18120401 | N/A | SHALLOW PIPE | NE | ANDERSON | IN-ANDERSON-SCATTERFIELD~ REPLACE 1500' OF 10" HP STL PIPE. INSTALL 0 SERVICES | 2025
N-X-5014 | 18120403 | N/A | SHALLOW PIPE | NE | ANDERSON | IN-ANDERSON-SCATTERFIELD~~ 5TH TO 1ST ST REPLACE 1000' OF 10" HP STL PIPE. INSTALL 0 SERVICES | 2025
N-X-5015 | 18120407 | N/A | SHALLOW PIPE | NE | ANDERSON | IN-ANDERSON-SCATTERFIELD~~ FROM 5TH TO 10TH ST REPLACE 1000' OF 10" HP STL PIPE. INSTALL 0 SERVICES | 2025
N-X-5017 | 18120409 | N/A | SHALLOW PIPE | NE | ANDERSON | IN-ANDERSON-SCATTERFIELD~~ MOUNDS TO 18TH ST REPLACE 3000' OF 10" HP STL PIPE. INSTALL 0 SERVICES | 2025
N-XA-12124 | N/A | N/A | CASINGS | SE | BEDFORD | IN-BEDFORD-RR CASING Short under abandon railroad. Retire Casing and install new 500' of 2" HDPE. NO SERVICES | 2026
N-X-17925 | N/A | N/A | EXPOSURES | NW | LAFAYETTE | IN-Lafayette-US231, north of W CR625S DIMP Project ID 474 Area - 03.30.2021 - Exposure - Tippecanoe County - Remediate 8" MP Steel Main Exposure located along US231, north of W CR625S. Max. Exposure No. L2147938. | 2026
N-X-17926 | N/A | N/A | EXPOSURES | NW | LAFAYETTE | IN-Lafayette-Near intersection of W CR625S. DIMP Project ID 475 Area - 03.30.2021 - Exposure - Tippecanoe County - Remediate 6" MP Steel Main Exposure located along US231, near intersection of W CR625S. Max. Exposure No. L2147960. | 2026
N-X-17927 | N/A | N/A | EXPOSURES | NW | LAFAYETTE | IN-Lafayette-US231, north of W CR800S DIMP Project ID 476 Area - 03.30.2021 - Exposure - Tippecanoe County - Remediate 8" MP Steel Main Exposure located along US231, north of W CR800S. Max. Exposure No. L2148049. | 2026
N-X-18410 | N/A | N/A | Exposures | NW | TERRE HAUTE | IN-Terre Haute-US40 &SR46 6" MP steel main- Creek exposure near intersection of US40 & SR46, east of intersection - Exposure - Replace approx. 500 FT of existing 6" Steel Main. | 2026
Multiple | Multiple | Multiple | INSIDE METERS | VEDIN | MULTIPLE | INSIDE METERS - relocate inside meters to exterior of structure | 2026
N-X-14103 | N/A | N/A | LEGACY PLASTIC | SE | GREENWOOD | IN-Greenwood-Countryside Derive-Part 3 Part 3: Replace 4045' of main and 107 services. DIMP Project 57 Project boundaries—Countryside Drive to the west, E Worthsville Road to the south, W Stop 18 Road to the north, and US HWY 31 to the east 0.33 miles of pre‐1974 plastic􀆟c Recommend􀆟on to target vintage plastic􀆟c. Risk targeted is Pipe, Weld, Joint Tier 2 facility􀆟es in this area are 3.41 miles of pre‐1984 plastic􀆟c and 1.02 miles of unknown install􀆟on date plastic􀆟c. Map Grid 191‐178 | 2026
N-X-17922 | N/A | N/A | LEGACY PLASTIC | NW | LAFAYETTE | IN-Lafayette-Owen St to the south DIMP Project ID 457 Area - 03.30.2021 - Vintage Plastic - Replace approx. 5,500' of 2" MP Plastic main between Owen St to the south, S 16th St to the east, N 2nd St to the west, Heath St to the north. Replace approx. 110 services. | 2026
N-X-17923 | N/A | N/A | LEGACY PLASTIC | NW | LAFAYETTE | IN-Lafayette-Kings Way Subdivision DIMP Project ID 458 Area - 03.30.2021 - Vintage Plastic - Maps 59-245 & 59-265 Replace approx. 6,000' of 2" MP Plastic main at Kings Way Subdivision off of SR38E and at Pheasant Run Subdivision off of East Brady Lane. Replace approx. 140 services. | 2026
N-X-17924 | N/A | N/A | LEGACY PLASTIC | NW | LAFAYETTE | IN-Lafayette-S 30th Street DIMP Project ID 462 Area - 03.30.2021 - Vintage Plastic - Maps 59-223 & 59-202 Replace approx. 5,000' of 2" MP Plastic main along S 30th Street, between. Kossuth and Ferry St. Replace approx. 100 services. | 2026
N-X-18302 | N/A | N/A | LEGACY PLASTIC | NW | UNIVERSAL | IN-Universal- DIMP Project ID 464 Area - 03.30.2021 - Vintage Plastic - Vermillion County Replace approx. 3,500' of 2" MP Plastic main along CR110E between CR1680S and Creek Crossing at Universal Ave to the South. Replace approx. 50 services. | 2026
N-X-12302 | N/A | N/A | LEGACY STEEL | NW | ATTICA | IN-Attica-Union-Pike Ineffectively Coated Steel - Legacy Map 130-130 - Replace approx. 5,800' of 2" MP Steel main along Union, Pike, Pine, Lithia, Perry, Bond, New, and Council St ; between Union, Pike, Pine, and Council St; just north of Pine St. Replace approx. 100 services | 2026
N-X-4001 | N/A | N/A | LEGACY STEEL | NW | ATTICA | IN-ATTICA-US231 TO ATTICA~~ IN-ATTICA-US231 TO ATTICA~~1938 HP DISTRIBUTION STL - INEFFECTIVELY COATED STEEL - REPLACE APPROX. 8,000 FT OF EXISTING 6" HP STEEL MAIN. | 2026
N-X-13205 | N/A | N/A | LEGACY STEEL | NW | AVON | IN-Avon-CR100S Ineffectively Coated Steel - Legacy Map 46-232 - Replace approx. 4,800' of 4" MP Steel main along CR100S, between N Center St and SR267 / Avon Road and along N Center St / CR625E, between CR100S and Barberry Dr. Replace approx. 60 services. | 2026
N-X-15304 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-Bloomington-Allendale Drive between Wellington Drive and Bainbridge Drive, Ineffective Coated Steel - Replace approx. 8,000' of 2" Steel and 1,350' of 4" Steel main located along Allendale Drive between Wellington Drive and Bainbridge Drive, also includes the area along Elliston Drive (Map 29-245); also includes replacing approx. 147 services. | 2026
N-X-1716 | N/A | N/A | LEGACY STEEL | SE | BLOOMINGTON | IN-Bloomington-KINGSLEY ST. KINGSLEY ST. REPLACE 8,470' OF MAIN WITH 130 SERVICES | 2026
N-X-13203 | N/A | N/A | LEGACY STEEL | NW | BROWNSBURG | IN-Brownsburg-Green Street Vintage Plastic - Legacy Map 46-133 - Green Street, between CR425 and Hyde Park and Sycamore St; between Green and York - Replace approx. 3,500' of 6" MP Plastic main . Replace approx. 36 services. | 2026
N-X-11102 | N/A | N/A | LEGACY STEEL | NW | CENTER POINT | CLAY COUNTY - SR 42 DIMP Project ID 461 Area - 03.30.2021 - Ineffectively Coated Steel - Clay County - Replace approx. 9,000' of 6" MP Steel Main along SR42 between CR200E (near Reg. Sta. #3500007B) and CR350E (near McIntyre Creek). Replace approx. 30 services. | 2026
N-XA-11753 | N/A | N/A | LEGACY STEEL | SE | COLUMBUS | MAIN CROSS ST, CONNER ST, WAYNE ST, SOUTH ST Install 3788' of 2" HDPE and 44 services. Main Cross St, Conner St, Wayne St, South St. | 2026
N-XA-12123 | N/A | N/A | LEGACY STEEL | SE | COLUMBUS | Ineffectively Coated Steel. Install 6500' of 2" HDPE and 122 services. Fairview Dr, Hollowell St, Clifty Dr, and Glendale Dr. | 2026
N-X-17917 | N/A | N/A | LEGACY STEEL | NW | DAYTON | IN-Dayton-South St Vintage Plastic - Dayton IN - Replace approx. 5,500' of 2" MP Plastic main between South St to the south, Conjunction St to the east, Jefferson St to the north, Harrison to the west. Western Replacement Area. Replace approx. 110 services. | 2026
N-X-16704 | N/A | N/A | LEGACY STEEL | NW | GREENCASTLE | IN-GREENCASTLE- Melrose Dr Vintage Plastic - DIMP Project ID 49 Area - Replace approx. 1,200' of existing 2" MP Plastic main located along Melrose Dr, between Shadowlawn and Cassada Dr; and approx. 500' of existing 2" MP Plastic main located along Cassada Dr, between Melrose and Terminus. Replace approx. 28 services. | 2026
N-X-10006 | N/A | N/A | LEGACY STEEL | SE | JEFFERSONVILLE | IN-Jeffersonville- Colonial Park Drive between 8th Street and Jonquil Drive. Ineffectively Coated Steel: Replace approx. 3,700' of 4" Steel main and approx. 86 services along Colonial Park Drive between 8th Street and Jonquil Drive. This proposed project will also provide an added system loop feed at Jonquil Drive. | 2026
N-X-17904 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-Franklin St DIMP Project ID 418 Area - 02.26.2021 - Vintage Plastic - Replace approx. 1,300' of 2" MP Plastic main along Franklin St, between S 18th St and 14th Street. Replace approx. 48 services. | 2026
N-X-17914 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE-S 18th St to the east DIMP Project ID 419 Area - 02.26.2021 - Vintage Plastic - Replace approx. 5,400' of 2" MP Plastic main between Kossuth to the south, S 18th St to the east, Heath to the north, Wabash to the west. Eastern Replacement Area. Replace approx. 120 services. | 2026
N-X-17915 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE- Greenbush St Ineffectively coated steel - Replace approx. 4,200' of 4" MP Steel main along Greenbush St, between Erie St and Sagamore Pkwy. Replace approx. 56 services. | 2026
N-X-17916 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-LAFAYETTE- Chestnut St Ineffectively coated steel - Replace approx. 1,000' of 10" MP Steel main along Chestnut St, between Wabash St and 1st St. Replace approx. 6 services. | 2026
N-X-17918 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-Lafayette-Pemberly Road Ineffectively Coated Steel - Legacy Map 59-154 - Replace approx. 3,000' of 2" MP Steel main along Pemberly Road and West Point 2 Road; between Klondike heading west to Terminus. Replace approx. 78 services. | 2026
N-X-17919 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-Lafayette-West Point 2 Road Vintage Plastic - Legacy Map 59-154 - Replace approx. 3,300' of 2" MP Plastic main along West Point 2 Road South and North; between Klondike heading west to Terminus. Replace approx. 72 services. | 2026
N-X-17920 | N/A | N/A | LEGACY STEEL | NW | LAFAYETTE | IN-Lafayette-Friendly Village Trailer Park Vintage Plastic - Legacy Map - Friendly Village Trailer Park - Bourdeaux Blvd, Devaraux Dr., Napolean, Rene - Replace approx. 6,000' of 2" MP Plastic main . Replace approx. 172 services. | 2026
N-X-10601 | N/A | N/A | LEGACY STEEL | NW | LEBANON | IN-LEBANON-Westmoor St Ineffectively coated steel - DIMP Project ID 254 - Legacy Mod Project ID 4831. Replace approx. 1,500' of existing 6" HP Steel main located along N Lebanon Street, near 2302; between. Westmoor St and West Maple Street | 2026
Multiple | Multiple | Multiple | LEGACY STEEL | VEDIN | MULTIPLE | ISOLATED SERVICES - replaced isolated services | 2026
N-XA-11854 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-ROMY STREET 10800' MAIN 10 SERVICES | 2026
N-XA-11855 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-SR 3 10400' MAIN 20 SERVICES | 2026
N-XA-11856 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-SR 3-CR 700 NORTH 10400' MAIN 10 SERVICES | 2026
N-XA-11857 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-SR 3-CR 700 NORTH 11000' MAIN 0 SERVICES | 2026
N-XA-11858 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-SR 3-CR 500 NORTH 10400' MAIN 10 SERVICES | 2026
N-XA-11859 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-CR 700 N 10400' MAIN 10 SERVICES | 2026
N-XA-11862 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-BOWMAN 8000' MAIN 40 SERVICES | 2026
N-XA-11863 | N/A | N/A | LEGACY STEEL | NE | MUNCIE | IN-Muncie-CR 200 EAST 12000' MAIN 30 SERVICES | 2026
N-XA-11860 | N/A | N/A | LEGACY STEEL | NE | PARKER CITY | IN-Parker City-SR 28 11000' MAIN 10 SERVICES | 2026
N-XA-11861 | N/A | N/A | LEGACY STEEL | NE | PARKER CITY | IN-Parker City-6TH STREET 8000' MAIN 50 SERVICES | 2026
N-X-13206 | N/A | N/A | LEGACY STEEL | NW | PLAINFIELD | IN-Plainfield-Circle St Ineffectively Coated Steel - Legacy Map 46-252 - Replace approx. 7,900' of 2" MP Steel main along Price Circle St, Price Rd, Todd Dr, Hope Dr, Rivera Dr, and Parke Dr; between CR100S (Morris St) and CR150S, just west of SR267 (Avon Ave.) Replace approx. 85 services. | 2026
N-X-13209 | N/A | N/A | LEGACY STEEL | NW | PLAINFIELD | IN-Plainfield-Elm Dr, Michael Dr, Ineffectively Coated Steel - Legacy Map 46-294 - Replace approx. 6,800' of 2" MP Steel main along Elm Dr, Michael Dr, Stephens Dr, Butler Dr, Omega Dr, and Glenda Dr; between Main St (US40) and Oliver Ave, just west of SR267. Replace approx. 96 services | 2026
N-X-13210 | N/A | N/A | LEGACY STEEL | NW | PLAINFIELD | IN-PLAINFIELD-Springcrest, Bluff Ineffectively Coated Steel - Legacy Map 46-333 - Replace approx. 7,200' of 2" MP Steel main along Springcrest, Bluff, Eldin, Almond, Terry, and Stanley ; between Stanley, Springcrest, Center St and Terry St, just east of Center St. Replace approx. 88 services | 2026
N-XA-12125 | N/A | N/A | LEGACY STEEL | SE | SHELBYVILLE | IN-SHELBYVILLE-W PENNSYLVANIA STREET REPLACE INEFFECTIVE COATED STEEL ON W PENNSYLVANIA ST, TOMPKINS ST, RIVER ST, AND N PIKE ST. RAILROAD CROSSING. INSTALL 6" HDPE AND 11 SERVICES | 2026
N-X-18403 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-Fruitridge Ave. NW Future TH MOD Project 3 - Replace INRR West Xing at Fruitridge Ave. - Located Just South of Ohio Blvd. Replace approx. 500' of exist. 6" MP Steel Main. | 2026
N-X-18404 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-Fruitridge Ave. NW Future TH MOD Project 4 - Replace INRR East Xing at Fruitridge Ave. - Located Just South of Ohio Blvd. Replace approx. 500' of exist. 8" HP Steel Main. | 2026
N-X-18407 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-Gilbert St Ineffectively coated steel - DIMP Project ID 47 Area - Replace approx. 1,200' of existing 2" MP Steel main located along Gilbert St, between Poplar Street and Crawford Street; and approx. 350' of existing 2" MP Steel main located along Oak St, between 14th and 15th Street. Replace approx. 30 services. | 2026
N-X-18408 | N/A | N/A | LEGACY STEEL | NW | TERRE HAUTE | IN-TERRE HAUTE-College and Cruft, Ineffectively coated steel - DIMP Project ID 48 Area - Map 34-181 - Replace approx. 400' of existing 2" MP Steel main located along Alleyway between College and Cruft, between 29th Street and 31st St; and approx. 1,800' of existing 2" MP Steel main located along Alley between Cruft St and Franklin, between 25th St and 31st St; and approx. 1,900' of 2" MP Steel main along Alley between Franklin and Dean, between 25th St and 31st St; and approx. 800' of 2" MP Steel main along 29th St, between Dean St and College Street. Replace approx. 62 services. | 2026
N-X-18301 | N/A | N/A | LEGACY STEEL | NW | UNIVERSAL | VERMILLION COUNTY - SR63 DIMP Project ID 463 Area - 03.30.2021 - Ineffectively Coated Steel - Vermillion County - Replace approx. 7,000' of 6" MP Steel Main along SR63 between Broullettes Creek and Trinity Road (near Reg. Sta. #37000185). Replace approx. 20 services. | 2026
N-X-17905 | N/A | N/A | LEGACY STEEL | NW | WEST POINT | IN-WEST POINT-W CR500 S Ineffectively coated steel - Replace approx. 5,000' of 10" HP Steel main located along W CR500 S, between Andrew Road and S CR600W. | 2026
Multiple | Multiple | Multiple | Obsolete Equipment | VEDIN | MULTIPLE | OBSOLETE RISERS - replace obsolete service risers | 2026
N-XA-11843 | N/A | N/A | REGULATOR STATION | NW | DANVILLE | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2026
N-XA-11836 | N/A | N/A | REGULATOR STATION | SE | FRANKLIN | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2026
N-XA-11842 | N/A | N/A | REGULATOR STATION | NE | MUNCIE | INSTALL 10 EMERGENCY INLET VALVES FOR VARIOUS REGULATOR STATIONS | 2026
N-XA-11780 | N/A | TBD | OBSOLETE EQUIPMENT | NW | LAFAYETTE | IN-LAFAYETTE-2800 CONCORD RD Rea Magnet Wire- Meter set obsolete, 2800 Concord Road. | 2024
N-XA-11781 | N/A | TBD | OBSOLETE EQUIPMENT | NW | LAFAYETTE | IN-LAFAYETTE-2309 CONCORD RD Fairfield Manufacturing - Meter set obsolete, 2309 Concord Road. | 2024

## SAH-6 (Public)
CEI North
Bare Steel and Cast Iron - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
N-1113 | 18022232 | 98785126 | BSCI | NE | RICHMOND | IN-RICHMOND-N-1113-BSCI - Est Installed Footage 8200 - Est Retired Footage 8810 - Est Svcs 138 | 2022
N-114 | 14807202 | 98784375 | BSCI | NE | ANDERSON | IN-ANDERSON-N-114-BSCI - Est Installed Footage 7355 - Est Retired Footage 6945 - Est Svcs 75 | 2022
N-1415 | 18022660 | 98784856 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1415-BSCI - Est Installed Footage 4300 - Est Retired Footage 4215 - Est Svcs 78 | 2022
N-1416 | 18352827 | 98789429 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1416-BSCI - Est Installed Footage 4080 - Est Retired Footage 4295 - Est Svcs 83 | 2022
N-1421 | 16047927 | 98785849 | BSCI | NE | MARION | IN-MARION-N-1421-BSCI - Est Installed Footage 8045 - Est Retired Footage 9005 - Est Svcs 78 | 2022
N-1422 | 16117628 | 98785880 | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-1422-BSCI - Est Installed Footage 5965 - Est Retired Footage 6565 - Est Svcs 70 | 2022
N-1430 | 16047980 | 98785844 | BSCI | NE | GAS CITY | IN-GAS CITY-N-1430-BSCI - Est Installed Footage 6400 - Est Retired Footage 5945 - Est Svcs 101 | 2022
N-1440 | 18785601 | 98789253 | BSCI | NE | SELMA | IN-SELMA-N-1440-BSCI - Est Installed Footage 5755 - Est Retired Footage 6375 - Est Svcs 41 | 2022
N-1441 | 17539005 | 98786684 | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-1441-BSCI - Est Installed Footage 7695 - Est Retired Footage 7335 - Est Svcs 68 | 2022
N-1442 | 17509172 | 98786333 | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-1442-BSCI - Est Installed Footage 3770 - Est Retired Footage 4780 - Est Svcs 74 | 2022
N-1443 | 17509198 | 98786537 | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-1443-BSCI - Est Installed Footage 7570 - Est Retired Footage 8680 - Est Svcs 124 | 2022
N-1448 | 16049055 | 98785853 | BSCI | NE | RICHMOND | IN-RICHMOND-N-1448-BSCI - Est Installed Footage 5395 - Est Retired Footage 10090 - Est Svcs 141 | 2022
N-1476 | 18062127 | 98789028 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1476-BSCI - Est Installed Footage 5565 - Est Retired Footage 5165 - Est Svcs 75 | 2022
N-1483 | 18062165 | 98789032 | BSCI | NE | PARKER CITY | IN-PARKER CITY-N-1483-BSCI - Est Installed Footage 5730 - Est Retired Footage 7515 - Est Svcs 79 | 2022
N-1484 | 18062463 | 98788982 | BSCI | NE | PARKER CITY | IN-PARKER CITY-N-1484-BSCI - Est Installed Footage 5910 - Est Retired Footage 7150 - Est Svcs 67 | 2022
N-1524 | 18062484 | 98788983 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1524-BSCI - Est Installed Footage 3305 - Est Retired Footage 5945 - Est Svcs 38 | 2022
N-1567 | 18062510 | 98788995 | BSCI | NE | REDKEY | IN-REDKEY-N-1567-BSCI - Est Installed Footage 5120 - Est Retired Footage 5290 - Est Svcs 63 | 2022
N-1568 | 18062740 | 98785748 | BSCI | NE | REDKEY | IN-REDKEY-N-1568-BSCI - Est Installed Footage 5230 - Est Retired Footage 5740 - Est Svcs 51 | 2022
N-1571 | 18062809 | 98785762 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-1571-BSCI - Est Installed Footage 4735 - Est Retired Footage 5440 - Est Svcs 63 | 2022
N-1572 | 18062929 | 98789007 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-1572-BSCI - Est Installed Footage 3555 - Est Retired Footage 4460 - Est Svcs 58 | 2022
N-1573 | 18062954 | 98789019 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-1573-BSCI - Est Installed Footage 4825 - Est Retired Footage 5135 - Est Svcs 52 | 2022
N-1590 | 18072744 | 98789189 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-1590-BSCI - Est Installed Footage 13145 - Est Retired Footage 7625 - Est Svcs 148 | 2022
N-1601 | 18072799 | 98789199 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-1601-BSCI - Est Installed Footage 18165 - Est Retired Footage 15125 - Est Svcs 261 | 2022
N-1651 | 18062983 | 98789029 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1651-BSCI - Est Installed Footage 7505 - Est Retired Footage 6770 - Est Svcs 60 | 2022
N-1653 | 18063004 | 98789035 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1653-BSCI - Est Installed Footage 2785 - Est Retired Footage 2700 - Est Svcs 12 | 2022
N-1655 | 18063034 | 98789195 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1655-BSCI - Est Installed Footage 1750 - Est Retired Footage 1990 - Est Svcs 24 | 2022
N-1670 | 17175625 | 98785392 | BSCI | NE | FRANKTON | IN-FRANKTON-N-1670-BSCI - Est Installed Footage 10310 - Est Retired Footage 11925 - Est Svcs 108 | 2022
N-1774 | 17175756 | 98785094 | BSCI | NE | CHESTERFIELD | IN-CHESTERFIELD-N-1774-BSCI - Est Installed Footage 7517 - Est Retired Footage 7302 - Est Svcs 117 | 2022
N-1780 | 17175837 | 98785116 | BSCI | NE | JONESBORO | IN-JONESBORO-N-1780-BSCI - Est Installed Footage 9325 - Est Retired Footage 9585 - Est Svcs 106 | 2022
N-1783 | 18072683 | 98789012 | BSCI | NE | RICHMOND | IN-RICHMOND-N-1783-BSCI - Est Installed Footage 8300 - Est Retired Footage 6920 - Est Svcs 149 | 2022
N-1784 | 17175862 | 98785241 | BSCI | NE | RICHMOND | IN-RICHMOND-N-1784-BSCI - Est Installed Footage 2445 - Est Retired Footage 3550 - Est Svcs 54 | 2022
N-1809 | 18063141 | 98785749 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1809-BSCI - Est Installed Footage 4765 - Est Retired Footage 4640 - Est Svcs 85 | 2022
N-1815 | 18065459 | 98789196 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1815-BSCI - Est Installed Footage 6670 - Est Retired Footage 6985 - Est Svcs 97 | 2022
N-2118 | 18065513 | 98789216 | BSCI | NE | MT. SUMMIT | IN-MT. SUMMIT-N-2118-BSCI - Est Installed Footage 525 - Est Retired Footage 385 - Est Svcs 7 | 2022
N-2145 | 18343512 | 98789641 | BSCI | NE | HUNTINGTON | IN-HUNTINGTON-N-2145-BSCI - Est Installed Footage 2320 - Est Retired Footage 3665 - Est Svcs 31 | 2022
N-2152 | 17176131 | 98785095 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-2152-BSCI - Est Installed Footage 7255 - Est Retired Footage 8715 - Est Svcs 98 | 2022
N-2154 | 17509214 | 98786538 | BSCI | NE | ANDERSON | IN-ANDERSON-N-2154-BSCI - Est Installed Footage 3360 - Est Retired Footage 3285 - Est Svcs 41 | 2022
N-2215 | 18192550 | 98785687 | BSCI | NE | ANDERSON | IN-ANDERSON-N-2215-BSCI - Est Installed Footage 3440 - Est Retired Footage 4800 - Est Svcs 46 | 2022
N-2216 | 18065775 | 98789036 | BSCI | NE | RICHMOND | IN-RICHMOND-N-2216-BSCI - Est Installed Footage 4145 - Est Retired Footage 2510 - Est Svcs 56 | 2022
N-2224 | 18066521 | 98788984 | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N-2224-BSCI - Est Installed Footage 3875 - Est Retired Footage 12065 - Est Svcs 53 | 2022
N-2226 | 18066571 | 98789010 | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N-2226-BSCI - Est Installed Footage 10575 - Est Retired Footage 5675 - Est Svcs 119 | 2022
N-2230 | 18065849 | 98789197 | BSCI | NE | RICHMOND | IN-RICHMOND-N-2230-BSCI - Est Installed Footage 4245 - Est Retired Footage 4060 - Est Svcs 73 | 2022
N-2233 | 16049538 | 98785851 | BSCI | NE | GAS CITY | IN-GAS CITY-N-2233-BSCI - Est Installed Footage 7175 - Est Retired Footage 5200 - Est Svcs 112 | 2022
N-2235 | 17177499 | 98785377 | BSCI | NE | ALBANY | IN-ALBANY-N-2235-BSCI - Est Installed Footage 3020 - Est Retired Footage 2895 - Est Svcs 43 | 2022
N-2252 | 18065972 | 98785763 | BSCI | NE | MUNCIE | IN-MUNCIE-N-2252-BSCI - Est Installed Footage 2760 - Est Retired Footage 2760 - Est Svcs 7 | 2022
N-2254 | 18066268 | 98789187 | BSCI | NE | MUNCIE | IN-MUNCIE-N-2254-BSCI - Est Installed Footage 4640 - Est Retired Footage 6165 - Est Svcs 19 | 2022
N-2310 | 18066356 | 98789217 | BSCI | NE | MUNCIE | IN-MUNCIE-N-2310-BSCI - Est Installed Footage 1220 - Est Retired Footage 1560 - Est Svcs 6 | 2022
N-2313 | 18068219 | 98789188 | BSCI | NW | ATTICA | IN-ATTICA-N-2313-BSCI - Est Installed Footage 16330 - Est Retired Footage 15550 - Est Svcs 159 | 2022
N-2314 | 18068406 | 98789218 | BSCI | NW | ATTICA | IN-ATTICA-N-2314-BSCI - Est Installed Footage 8865 - Est Retired Footage 8460 - Est Svcs 101 | 2022
N-2317 | 18068512 | 98785758 | BSCI | NW | LINDEN | IN-LINDEN-N-2317-BSCI - Est Installed Footage 7840 - Est Retired Footage 8250 - Est Svcs 120 | 2022
N-2321 | 18068539 | 98785764 | BSCI | NW | LAFAYETTE | IN-LAFAYETTE-N-2321-BSCI - Est Installed Footage 13280 - Est Retired Footage 10680 - Est Svcs 118 | 2022
N-2338 | 18068899 | 98789021 | BSCI | NW | LAFAYETTE | IN-LAFAYETTE-N-2338-BSCI - Est Installed Footage 18135 - Est Retired Footage 21830 - Est Svcs 95 | 2022
N-2340 | 18069241 | 98789219 | BSCI | NW | LAFAYETTE | IN-LAFAYETTE-N-2340-BSCI - Est Installed Footage 9590 - Est Retired Footage 9775 - Est Svcs 82 | 2022
N-2355 | 18072854 | 98785751 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2355-BSCI - Est Installed Footage 9505 - Est Retired Footage 7725 - Est Svcs 89 | 2022
N-2356 | 18072979 | 98788975 | BSCI | SE | TAYLORSVILLE | IN-TAYLORSVILLE-N-2356-BSCI - Est Installed Footage 14210 - Est Retired Footage 14075 - Est Svcs 123 | 2022
N-2359 | 18073009 | 98788979 | BSCI | SE | BEDFORD | IN-BEDFORD-N-2359-BSCI - Est Installed Footage 3680 - Est Retired Footage 3765 - Est Svcs 49 | 2022
N-2362 | 18073104 | 98789024 | BSCI | SE | BEDFORD | IN-BEDFORD-N-2362-BSCI - Est Installed Footage 2130 - Est Retired Footage 2020 - Est Svcs 23 | 2022
N-2366 | 18073129 | 98789031 | BSCI | SE | BEDFORD | IN-BEDFORD-N-2366-BSCI - Est Installed Footage 8470 - Est Retired Footage 8390 - Est Svcs 19 | 2022
N-2367 | 18073159 | 98789190 | BSCI | SE | MITCHELL | IN-MITCHELL-N-2367-BSCI - Est Installed Footage 11480 - Est Retired Footage 10755 - Est Svcs 110 | 2022
N-2368 | 18082239 | 98789209 | BSCI | SE | MITCHELL | IN-MITCHELL-N-2368-BSCI - Est Installed Footage 7120 - Est Retired Footage 7995 - Est Svcs 63 | 2022
N-2383 | 18082276 | 98789221 | BSCI | SE | MARTINSVILLE | IN-MARTINSVILLE-N-2383-BSCI - Est Installed Footage 8780 - Est Retired Footage 7265 - Est Svcs 104 | 2022
N-2387 | 18082454 | 98789183 | BSCI | SE | SEYMOUR | IN-SEYMOUR-N-2387-BSCI - Est Installed Footage 5680 - Est Retired Footage 4880 - Est Svcs 61 | 2022
N-2388 | 18082651 | 98785746 | BSCI | SE | SEYMOUR | IN-SEYMOUR-N-2388-BSCI - Est Installed Footage 3090 - Est Retired Footage 2670 - Est Svcs 34 | 2022
N-2390 | 18082739 | 98788969 | BSCI | SE | MADISON | IN-MADISON-N-2390-BSCI - Est Installed Footage 4400 - Est Retired Footage 4500 - Est Svcs 56 | 2022
N-2655 | 18263205 | 98789843 | BSCI | NW | BROWNSBURG | IN-BROWNSBURG-N-2655-BSCI - Est Installed Footage 10060 - Est Retired Footage 5300 - Est Svcs 83 | 2022
N-714 | 18069460 | 98788978 | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N-714-BSCI - Est Installed Footage 10815 - Est Retired Footage 13015 - Est Svcs 149 | 2022
N-719 | 18069475 | 98788985 | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N-719-BSCI - Est Installed Footage 5440 - Est Retired Footage 3330 - Est Svcs 89 | 2022
N-720 | 18069489 | 98788986 | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N-720-BSCI - Est Installed Footage 1325 - Est Retired Footage 3620 - Est Svcs 10 | 2022
N-721 | 18069503 | 98788996 | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N-721-BSCI - Est Installed Footage 8425 - Est Retired Footage 10770 - Est Svcs 94 | 2022
N-896 | 18066414 | 98785757 | BSCI | NE | RICHMOND | IN-RICHMOND-N-896-BSCI - Est Installed Footage 4090 - Est Retired Footage 4645 - Est Svcs 91 | 2022
N-1105 | #N/A | 98788308 | BSCI | NE | RICHMOND | IN-RICHMOND-N-1105-BSCI - Est Installed Footage 4650 - Est Retired Footage 3950 - Est Svcs 76 | 2023
N-1149 | #N/A | 98788319 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1149-BSCI - Est Installed Footage 5550 - Est Retired Footage 5550 - Est Svcs 86 | 2023
N-1388 | #N/A | 98788331 | BSCI | NE | GASTON | IN-GASTON-N-1388-BSCI - Est Installed Footage 2700 - Est Retired Footage 2700 - Est Svcs 41 | 2023
N-1389 | #N/A | 98788159 | BSCI | NE | GASTON | IN-GASTON-N-1389-BSCI - Est Installed Footage 5880 - Est Retired Footage 5880 - Est Svcs 20 | 2023
N-1390 | #N/A | 98790035 | BSCI | NE | SHIDELER | IN-SHIDELER-N-1390-BSCI - Est Installed Footage 5800 - Est Retired Footage 5800 - Est Svcs 89 | 2023
N-1394 | #N/A | 98788358 | BSCI | NE | ROYERTON | IN-ROYERTON-N-1394-BSCI - Est Installed Footage 4950 - Est Retired Footage 4950 - Est Svcs 76 | 2023
N-1398 | #N/A | 98788320 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1398-BSCI - Est Installed Footage 4050 - Est Retired Footage 4050 - Est Svcs 62 | 2023
N-1399 | #N/A | 98788364 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1399-BSCI - Est Installed Footage 4050 - Est Retired Footage 4050 - Est Svcs 75 | 2023
N-1400 | #N/A | 98788173 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1400-BSCI - Est Installed Footage 5250 - Est Retired Footage 5250 - Est Svcs 78 | 2023
N-1401 | #N/A | 98788193 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1401-BSCI - Est Installed Footage 3900 - Est Retired Footage 3900 - Est Svcs 55 | 2023
N-1412 | #N/A | 98788289 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1412-BSCI - Est Installed Footage 4500 - Est Retired Footage 4500 - Est Svcs 60 | 2023
N-1413 | #N/A | 98788343 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1413-BSCI - Est Installed Footage 2700 - Est Retired Footage 2700 - Est Svcs 40 | 2023
N-1414 | #N/A | 98788161 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1414-BSCI - Est Installed Footage 2700 - Est Retired Footage 2700 - Est Svcs 40 | 2023
N-1428 | #N/A | 98788162 | BSCI | NE | ELWOOD | IN-ELWOOD-N-1428-BSCI - Est Installed Footage 3682 - Est Retired Footage 3682 - Est Svcs 56 | 2023
N-1432 | #N/A | 98788332 | BSCI | NE | JONESBORO | IN-JONESBORO-N-1432-BSCI - Est Installed Footage 3000 - Est Retired Footage 3000 - Est Svcs 46 | 2023
N-1435 | #N/A | 98788290 | BSCI | NE | HARTFORD CITY | IN-HARTFORD CITY-N-1435-BSCI - Est Installed Footage 6400 - Est Retired Footage 6400 - Est Svcs 93 | 2023
N-1444 | #N/A | 98788194 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-1444-BSCI - Est Installed Footage 5308 - Est Retired Footage 4768 - Est Svcs 80 | 2023
N-1487 | #N/A | 98788356 | BSCI | NE | PARKER CITY | IN-PARKER CITY-N-1487-BSCI - Est Installed Footage 950 - Est Retired Footage 950 - Est Svcs 8 | 2023
N-1526 | #N/A | 98788166 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1526-BSCI - Est Installed Footage 5607 - Est Retired Footage 6157 - Est Svcs 91 | 2023
N-1545 | #N/A | 98788196 | BSCI | NE | ELWOOD | IN-ELWOOD-N-1545-BSCI - Est Installed Footage 6525 - Est Retired Footage 6525 - Est Svcs 89 | 2023
N-1546 | #N/A | 98788181 | BSCI | NE | ALEXANDRIA | IN-ALEXANDRIA-N-1546-BSCI - Est Installed Footage 1607 - Est Retired Footage 1607 - Est Svcs 24 | 2023
N-1549 | #N/A | 98788197 | BSCI | NE | ALEXANDRIA | IN-ALEXANDRIA-N-1549-BSCI - Est Installed Footage 5100 - Est Retired Footage 5100 - Est Svcs 79 | 2023
N-1550 | #N/A | 98788279 | BSCI | NE | FRANKTON | IN-FRANKTON-N-1550-BSCI - Est Installed Footage 5850 - Est Retired Footage 5850 - Est Svcs 89 | 2023
N-1574 | #N/A | 98788293 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-1574-BSCI - Est Installed Footage 5965 - Est Retired Footage 5965 - Est Svcs 92 | 2023
N-1575 | #N/A | 98788299 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-1575-BSCI - Est Installed Footage 5000 - Est Retired Footage 4640 - Est Svcs 76 | 2023
N-1640 | #N/A | 98788300 | BSCI | NE | MARKLEVILLE | IN-MARKLEVILLE-N-1640-BSCI - Est Installed Footage 4100 - Est Retired Footage 4100 - Est Svcs 64 | 2023
N-1643 | #N/A | 98788309 | BSCI | NE | MARKLEVILLE | IN-MARKLEVILLE-N-1643-BSCI - Est Installed Footage 4750 - Est Retired Footage 4750 - Est Svcs 73 | 2023
N-1644 | #N/A | 98788310 | BSCI | NE | PENDLETON | IN-PENDLETON-N-1644-BSCI - Est Installed Footage 4000 - Est Retired Footage 4000 - Est Svcs 61 | 2023
N-1645 | #N/A | 98790059 | BSCI | NE | PENDLETON | IN-PENDLETON-N-1645-BSCI - Est Installed Footage 4730 - Est Retired Footage 4730 - Est Svcs 73 | 2023
N-1648 | #N/A | 98788322 | BSCI | NE | PENDLETON | IN-PENDLETON-N-1648-BSCI - Est Installed Footage 4250 - Est Retired Footage 4250 - Est Svcs 65 | 2023
N-1650 | #N/A | 98788167 | BSCI | NE | NEW COLUMBUS | IN-NEW COLUMBUS-N-1650-BSCI - Est Installed Footage 2250 - Est Retired Footage 2250 - Est Svcs 35 | 2023
N-1656 | #N/A | 98788301 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1656-BSCI - Est Installed Footage 1600 - Est Retired Footage 1600 - Est Svcs 13 | 2023
N-1660 | #N/A | 98788359 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1660-BSCI - Est Installed Footage 3000 - Est Retired Footage 3000 - Est Svcs 45 | 2023
N-1715 | #N/A | 98789999 | BSCI | SE | HARRODSBURG | IN-HARRODSBURG-N-1715-BSCI - Est Installed Footage 9450 - Est Retired Footage 9450 - Est Svcs 87 | 2023
N-1717 | #N/A | 98788163 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1717-BSCI - Est Installed Footage 1350 - Est Retired Footage 1350 - Est Svcs 21 | 2023
N-1719 | #N/A | 98788182 | BSCI | NE | ANDERSON | IN-ANDERSON-N-1719-BSCI - Est Installed Footage 4270 - Est Retired Footage 4270 - Est Svcs 65 | 2023
N-1733 | #N/A | 98788281 | BSCI | NE | MARKLE | IN-MARKLE-N-1733-BSCI - Est Installed Footage 5755 - Est Retired Footage 5755 - Est Svcs 91 | 2023
N-1734 | #N/A | 98788302 | BSCI | NE | MARKLE | IN-MARKLE-N-1734-BSCI - Est Installed Footage 4300 - Est Retired Footage 4300 - Est Svcs 66 | 2023
N-1735 | #N/A | 98788323 | BSCI | NE | MARKLE | IN-MARKLE-N-1735-BSCI - Est Installed Footage 2650 - Est Retired Footage 2650 - Est Svcs 41 | 2023
N-1748 | #N/A | 98788336 | BSCI | NE | ELWOOD | IN-ELWOOD-N-1748-BSCI - Est Installed Footage 3640 - Est Retired Footage 3640 - Est Svcs 56 | 2023
N-1776 | #N/A | 98788337 | BSCI | NE | ELWOOD | IN-ELWOOD-N-1776-BSCI - Est Installed Footage 3895 - Est Retired Footage 3895 - Est Svcs 60 | 2023
N-1779 | #N/A | 98788344 | BSCI | NE | FRANKTON | IN-FRANKTON-N-1779-BSCI - Est Installed Footage 2600 - Est Retired Footage 2600 - Est Svcs 40 | 2023
N-1790 | #N/A | 98789875 | BSCI | NE | HARTFORD CITY | IN-HARTFORD CITY-N-1790-BSCI - Est Installed Footage 6200 - Est Retired Footage 6200 - Est Svcs 96 | 2023
N-1791 | #N/A | 98790009 | BSCI | NE | HARTFORD CITY | IN-HARTFORD CITY-N-1791-BSCI - Est Installed Footage 4870 - Est Retired Footage 4870 - Est Svcs 76 | 2023
N-1794 | #N/A | 98790013 | BSCI | NE | HUNTINGTON | IN-HUNTINGTON-N-1794-BSCI - Est Installed Footage 1450 - Est Retired Footage 1450 - Est Svcs 22 | 2023
N-1796 | #N/A | 98790014 | BSCI | NE | GASTON | IN-GASTON-N-1796-BSCI - Est Installed Footage 3850 - Est Retired Footage 3850 - Est Svcs 58 | 2023
N-1797 | #N/A | 98790027 | BSCI | NE | GASTON | IN-GASTON-N-1797-BSCI - Est Installed Footage 5280 - Est Retired Footage 5280 - Est Svcs 20 | 2023
N-1800 | #N/A | 98788135 | BSCI | NE | EATON | IN-EATON-N-1800-BSCI - Est Installed Footage 4250 - Est Retired Footage 4250 - Est Svcs 66 | 2023
N-1801 | #N/A | 98789883 | BSCI | NE | EATON | IN-EATON-N-1801-BSCI - Est Installed Footage 4650 - Est Retired Footage 4650 - Est Svcs 72 | 2023
N-1816 | #N/A | 98789888 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1816-BSCI - Est Installed Footage 3650 - Est Retired Footage 3650 - Est Svcs 53 | 2023
N-1817 | #N/A | 98789917 | BSCI | NE | ROYERTON | IN-ROYERTON-N-1817-BSCI - Est Installed Footage 4650 - Est Retired Footage 4650 - Est Svcs 72 | 2023
N-1872 | #N/A | 98789995 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1872-BSCI - Est Installed Footage 6950 - Est Retired Footage 6950 - Est Svcs 92 | 2023
N-1873 | #N/A | 98790019 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1873-BSCI - Est Installed Footage 2164 - Est Retired Footage 2164 - Est Svcs 37 | 2023
N-1925 | #N/A | 98790029 | BSCI | NE | MUNCIE | IN-MUNCIE-N-1925-BSCI - Est Installed Footage 1350 - Est Retired Footage 1350 - Est Svcs 37 | 2023
N-2112 | #N/A | 98790045 | BSCI | NE | NEW CASTLE | IN-NEW CASTLE-N-2112-BSCI - Est Installed Footage 8907 - Est Retired Footage 8907 - Est Svcs 111 | 2023
N-2114 | #N/A | 98788136 | BSCI | NE | NEW CASTLE | IN-NEW CASTLE-N-2114-BSCI - Est Installed Footage 6072 - Est Retired Footage 6072 - Est Svcs 86 | 2023
N-2115 | #N/A | 98789876 | BSCI | NE | NEW CASTLE | IN-NEW CASTLE-N-2115-BSCI - Est Installed Footage 4600 - Est Retired Footage 4600 - Est Svcs 69 | 2023
N-2116 | #N/A | 98789913 | BSCI | NE | MUNCIE | IN-MUNCIE-N-2116-BSCI - Est Installed Footage 3078 - Est Retired Footage 3078 - Est Svcs 47 | 2023
N-2141 | #N/A | 98789918 | BSCI | NE | MUNCIE | IN-MUNCIE-N-2141-BSCI - Est Installed Footage 6800 - Est Retired Footage 6200 - Est Svcs 81 | 2023
N-2146 | #N/A | 98789996 | BSCI | NE | NEW CASTLE | IN-NEW CASTLE-N-2146-BSCI - Est Installed Footage 2900 - Est Retired Footage 2900 - Est Svcs 44 | 2023
N-2151 | #N/A | 98789997 | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-2151-BSCI - Est Installed Footage 2550 - Est Retired Footage 2550 - Est Svcs 39 | 2023
N-2163 | #N/A | 98790005 | BSCI | NE | ANDERSON | IN-ANDERSON-N-2163-BSCI - Est Installed Footage 5243 - Est Retired Footage 5243 - Est Svcs 72 | 2023
N-2167 | #N/A | 98790020 | BSCI | NE | RICHMOND | IN-RICHMOND-N-2167-BSCI - Est Installed Footage 1800 - Est Retired Footage 1800 - Est Svcs 27 | 2023
N-2205 | #N/A | 98790030 | BSCI | NE | GAS CITY | IN-GAS CITY-N-2205-BSCI - Est Installed Footage 4200 - Est Retired Footage 4200 - Est Svcs 65 | 2023
N-2208 | #N/A | 98790031 | BSCI | NE | ANDERSON | IN-ANDERSON-N-2208-BSCI - Est Installed Footage 6900 - Est Retired Footage 6900 - Est Svcs 103 | 2023
N-2214 | #N/A | 98790037 | BSCI | NE | ANDERSON | IN-ANDERSON-N-2214-BSCI - Est Installed Footage 4695 - Est Retired Footage 4695 - Est Svcs 72 | 2023
N-2217 | #N/A | 98790046 | BSCI | NE | RICHMOND | IN-RICHMOND-N-2217-BSCI - Est Installed Footage 5600 - Est Retired Footage 5600 - Est Svcs 68 | 2023
N-2218 | #N/A | 98790047 | BSCI | NE | JONESBORO | IN-JONESBORO-N-2218-BSCI - Est Installed Footage 4370 - Est Retired Footage 4370 - Est Svcs 67 | 2023
N-2219 | #N/A | 98790055 | BSCI | NE | JONESBORO | IN-JONESBORO-N-2219-BSCI - Est Installed Footage 4550 - Est Retired Footage 4550 - Est Svcs 69 | 2023
N-2232 | #N/A | 98790056 | BSCI | NE | FRANKTON | IN-FRANKTON-N-2232-BSCI - Est Installed Footage 1350 - Est Retired Footage 1350 - Est Svcs 21 | 2023
N-2234 | #N/A | 98790060 | BSCI | NE | HUNTINGTON | IN-HUNTINGTON-N-2234-BSCI - Est Installed Footage 3815 - Est Retired Footage 3815 - Est Svcs 60 | 2023
N-2236 | #N/A | 98790061 | BSCI | NE | EATON | IN-EATON-N-2236-BSCI - Est Installed Footage 2050 - Est Retired Footage 2050 - Est Svcs 32 | 2023
N-2293 | #N/A | 98790022 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2293-BSCI - Est Installed Footage 3580 - Est Retired Footage 3580 - Est Svcs 60 | 2023
N-2300 | #N/A | 98785254 | BSCI | NW | ROCKVILLE | IN-ROCKVILLE-N-2300-BSCI - Est Installed Footage 6275 - Est Retired Footage 6775 - Est Svcs 97 | 2023
N-2316 | #N/A | 98790032 | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N-2316-BSCI - Est Installed Footage 7510 - Est Retired Footage 7510 - Est Svcs 49 | 2023
N-2327 | #N/A | 98790021 | BSCI | NE | MARION | IN-MARION-N-2327-BSCI - Est Installed Footage 6240 - Est Retired Footage 6240 - Est Svcs 79 | 2023
N-2328 | #N/A | 98785489 | BSCI | NW | LAFAYETTE | IN-LAFAYETTE-N-2328-BSCI - Est Installed Footage 3055 - Est Retired Footage 3065 - Est Svcs 16 | 2023
N-2349 | #N/A | 98790048 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2349-BSCI - Est Installed Footage 2270 - Est Retired Footage 2270 - Est Svcs 23 | 2023
N-2350 | #N/A | 98788141 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2350-BSCI - Est Installed Footage 3700 - Est Retired Footage 3700 - Est Svcs 0 | 2023
N-2351 | #N/A | 98789920 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2351-BSCI - Est Installed Footage 6335 - Est Retired Footage 5255 - Est Svcs 97 | 2023
N-2352 | #N/A | 98790023 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2352-BSCI - Est Installed Footage 9600 - Est Retired Footage 9600 - Est Svcs 132 | 2023
N-2353 | #N/A | 98790057 | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2353-BSCI - Est Installed Footage 2600 - Est Retired Footage 2600 - Est Svcs 35 | 2023
N-2358 | #N/A | 98790062 | BSCI | SE | BEDFORD | IN-BEDFORD-N-2358-BSCI - Est Installed Footage 6600 - Est Retired Footage 6600 - Est Svcs 65 | 2023
N-2365 | #N/A | 98789885 | BSCI | SE | BEDFORD | IN-BEDFORD-N-2365-BSCI - Est Installed Footage 5300 - Est Retired Footage 5300 - Est Svcs 20 | 2023
N-2410 | #N/A | 98788139 | BSCI | NE | SHERIDAN | IN-SHERIDAN-N-2410-BSCI - Est Installed Footage 6140 - Est Retired Footage 6140 - Est Svcs 87 | 2023
N-2513 | #N/A | 98785934 | BSCI | NW | LAFAYETTE | IN-LAFAYETTE-N-2513-BSCI - Est Installed Footage 1925 - Est Retired Footage 1740 - Est Svcs 3 | 2023
N-2514 | #N/A | 98785941 | BSCI | NW | LAFAYETTE | IN-LAFAYETTE-N-2514-BSCI - Est Installed Footage 5955 - Est Retired Footage 6265 - Est Svcs 26 | 2023
N-2549 | #N/A | 98790039 | BSCI | SE | HARRODSBURG | IN-HARRODSBURG-N-2549-BSCI - Est Installed Footage 4700 - Est Retired Footage 4700 - Est Svcs 1 | 2023
N-2550 | #N/A | 98790011 | BSCI | SE | HARRODSBURG | IN-HARRODSBURG-N-2550-BSCI - Est Installed Footage 6950 - Est Retired Footage 6950 - Est Svcs 25 | 2023
N-2566 | #N/A | 98790015 | BSCI | SE | BLOOMINGTON | IN-BLOOMINGTON-N-2566-BSCI - Est Installed Footage 6003 - Est Retired Footage 6003 - Est Svcs 8 | 2023
N-468 | #N/A | 98789909 | BSCI | NE | GAS CITY | IN-GAS CITY-N-468-BSCI - Est Installed Footage 2800 - Est Retired Footage 2800 - Est Svcs 43 | 2023
N-893 | #N/A | 98789910 | BSCI | NE | RICHMOND | IN-RICHMOND-N-893-BSCI - Est Installed Footage 6700 - Est Retired Footage 6701 - Est Svcs 93 | 2023
N-899 | #N/A | 98789919 | BSCI | NE | RICHMOND | IN-RICHMOND-N-899-BSCI - Est Installed Footage 3350 - Est Retired Footage 3700 - Est Svcs 64 | 2023
N-900 | #N/A | 98789998 | BSCI | NE | RICHMOND | IN-RICHMOND-N-900-BSCI - Est Installed Footage 5150 - Est Retired Footage 5150 - Est Svcs 76 | 2023
N-909 | #N/A | 98790007 | BSCI | NE | RICHMOND | IN-RICHMOND-N-909-BSCI - Est Installed Footage 5360 - Est Retired Footage 5360 - Est Svcs 35 | 2023
N-910 | #N/A | 98790010 | BSCI | NE | RICHMOND | IN-RICHMOND-N-910-BSCI - Est Installed Footage 3930 - Est Retired Footage 4230 - Est Svcs 82 | 2023
N-1192 | #N/A | TBD | BSCI | NE | EATON | IN-EATON-N-1192-BSCI - Est Installed Footage 3600 - Est Retired Footage 3600 - Est Svcs 56 | 2024
N-1393 | 18440435 | 21573302052214 | BSCI | NE | ALBANY | IN-ALBANY-N-1393-BSCI - Est Installed Footage 4046 - Est Retired Footage 4046 - Est Svcs 62 | 2024
N-1396 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1396-BSCI - Est Installed Footage 3125 - Est Retired Footage 3125 - Est Svcs 39 | 2024
N-1419 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1419-BSCI - Est Installed Footage 4900 - Est Retired Footage 4900 - Est Svcs 73 | 2024
N-1423 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1423-BSCI - Est Installed Footage 5100 - Est Retired Footage 5100 - Est Svcs 77 | 2024
N-1425 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1425-BSCI - Est Installed Footage 2400 - Est Retired Footage 2400 - Est Svcs 34 | 2024
N-1427 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1427-BSCI - Est Installed Footage 4550 - Est Retired Footage 4550 - Est Svcs 68 | 2024
N-1429 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1429-BSCI - Est Installed Footage 4950 - Est Retired Footage 4950 - Est Svcs 74 | 2024
N-1433 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1433-BSCI - Est Installed Footage 5876 - Est Retired Footage 5876 - Est Svcs 96 | 2024
N-1434 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1434-BSCI - Est Installed Footage 4900 - Est Retired Footage 4900 - Est Svcs 73 | 2024
N-1436 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1436-BSCI - Est Installed Footage 5633 - Est Retired Footage 6533 - Est Svcs 93 | 2024
N-1437 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1437-BSCI - Est Installed Footage 2653 - Est Retired Footage 2653 - Est Svcs 62 | 2024
N-1438 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1438-BSCI - Est Installed Footage 2500 - Est Retired Footage 2500 - Est Svcs 62 | 2024
N-1439 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1439-BSCI - Est Installed Footage 3300 - Est Retired Footage 3300 - Est Svcs 49 | 2024
N-1446 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1446-BSCI - Est Installed Footage 5450 - Est Retired Footage 3200 - Est Svcs 84 | 2024
N-1447 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1447-BSCI - Est Installed Footage 4480 - Est Retired Footage 4480 - Est Svcs 64 | 2024
N-1449 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1449-BSCI - Est Installed Footage 4400 - Est Retired Footage 4400 - Est Svcs 66 | 2024
N-1451 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1451-BSCI - Est Installed Footage 3600 - Est Retired Footage 3600 - Est Svcs 55 | 2024
N-1452 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1452-BSCI - Est Installed Footage 6000 - Est Retired Footage 6000 - Est Svcs 88 | 2024
N-1453 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1453-BSCI - Est Installed Footage 5122 - Est Retired Footage 5122 - Est Svcs 78 | 2024
N-1455 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1455-BSCI - Est Installed Footage 3200 - Est Retired Footage 3200 - Est Svcs 47 | 2024
N-1456 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1456-BSCI - Est Installed Footage 4300 - Est Retired Footage 4300 - Est Svcs 64 | 2024
N-1457 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1457-BSCI - Est Installed Footage 1200 - Est Retired Footage 1200 - Est Svcs 34 | 2024
N-1469 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1469-BSCI - Est Installed Footage 5870 - Est Retired Footage 5870 - Est Svcs 79 | 2024
N-1470 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1470-BSCI - Est Installed Footage 6400 - Est Retired Footage 6400 - Est Svcs 98 | 2024
N-1473 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1473-BSCI - Est Installed Footage 5800 - Est Retired Footage 5800 - Est Svcs 88 | 2024
N-1474 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1474-BSCI - Est Installed Footage 6650 - Est Retired Footage 6650 - Est Svcs 102 | 2024
N-1475 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1475-BSCI - Est Installed Footage 5000 - Est Retired Footage 5000 - Est Svcs 77 | 2024
N-1479 | #N/A | 21573302052225 | BSCI | NE | DALEVILLE | IN-DALEVILLE-N-1479-BSCI - Est Installed Footage 5500 - Est Retired Footage 5500 - Est Svcs 81 | 2024
N-1480 | #N/A | 21573302052226 | BSCI | NE | DALEVILLE | IN-DALEVILLE-N-1480-BSCI - Est Installed Footage 3650 - Est Retired Footage 3650 - Est Svcs 55 | 2024
N-1481 | #N/A | 21573302052227 | BSCI | NE | DALEVILLE | IN-DALEVILLE-N-1481-BSCI - Est Installed Footage 5886 - Est Retired Footage 5886 - Est Svcs 81 | 2024
N-1488 | #N/A | 21573302052229 | BSCI | NE | FARMLAND | IN-FARMLAND-N-1488-BSCI - Est Installed Footage 3930 - Est Retired Footage 3930 - Est Svcs 61 | 2024
N-1527 | #N/A | TBD | BSCI | NE | CHESTERFIELD | IN-CHESTERFIELD-N-1527-BSCI - Est Installed Footage 2500 - Est Retired Footage 2500 - Est Svcs 38 | 2024
N-1551 | #N/A | TBD | BSCI | NE | TIPTON | IN-TIPTON-N-1551-BSCI - Est Installed Footage 4515 - Est Retired Footage 4515 - Est Svcs 67 | 2024
N-1569 | #N/A | 21573302052230 | BSCI | NE | REDKEY | IN-REDKEY-N-1569-BSCI - Est Installed Footage 3300 - Est Retired Footage 3300 - Est Svcs 51 | 2024
N-1570 | #N/A | 21573302052231 | BSCI | NE | REDKEY | IN-REDKEY-N-1570-BSCI - Est Installed Footage 6326 - Est Retired Footage 6326 - Est Svcs 95 | 2024
N-1642 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1642-BSCI - Est Installed Footage 5000 - Est Retired Footage 5000 - Est Svcs 77 | 2024
N-1658 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-1658-BSCI - Est Installed Footage 2800 - Est Retired Footage 2800 - Est Svcs 43 | 2024
N-1669 | #N/A | 21583002052210 | BSCI | NE | ARCADIA | IN-ARCADIA-N-1669-BSCI - Est Installed Footage 4800 - Est Retired Footage 4800 - Est Svcs 72 | 2024
N-1723 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1723-BSCI - Est Installed Footage 3859 - Est Retired Footage 3859 - Est Svcs 54 | 2024
N-1724 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1724-BSCI - Est Installed Footage 4655 - Est Retired Footage 4655 - Est Svcs 58 | 2024
N-1725 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1725-BSCI - Est Installed Footage 5650 - Est Retired Footage 5650 - Est Svcs 72 | 2024
N-1726 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1726-BSCI - Est Installed Footage 4100 - Est Retired Footage 4100 - Est Svcs 62 | 2024
N-1727 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1727-BSCI - Est Installed Footage 4900 - Est Retired Footage 4900 - Est Svcs 69 | 2024
N-1772 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-1772-BSCI - Est Installed Footage 3863 - Est Retired Footage 3863 - Est Svcs 57 | 2024
N-1793 | #N/A | TBD | BSCI | NE | PENDLETON | IN-PENDLETON-N-1793-BSCI - Est Installed Footage 5800 - Est Retired Footage 5800 - Est Svcs 89 | 2024
N-1798 | #N/A | 21573302052238 | BSCI | NE | ALBANY | IN-ALBANY-N-1798-BSCI - Est Installed Footage 3088 - Est Retired Footage 3638 - Est Svcs 45 | 2024
N-1799 | #N/A | TBD | BSCI | NE | EATON | IN-EATON-N-1799-BSCI - Est Installed Footage 4200 - Est Retired Footage 4200 - Est Svcs 60 | 2024
N-1803 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1803-BSCI - Est Installed Footage 7118 - Est Retired Footage 7118 - Est Svcs 109 | 2024
N-1804 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1804-BSCI - Est Installed Footage 6400 - Est Retired Footage 6400 - Est Svcs 94 | 2024
N-1807 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1807-BSCI - Est Installed Footage 5950 - Est Retired Footage 5950 - Est Svcs 92 | 2024
N-1808 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1808-BSCI - Est Installed Footage 3300 - Est Retired Footage 3800 - Est Svcs 50 | 2024
N-1810 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1810-BSCI - Est Installed Footage 5269 - Est Retired Footage 5269 - Est Svcs 74 | 2024
N-1811 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1811-BSCI - Est Installed Footage 4900 - Est Retired Footage 4900 - Est Svcs 76 | 2024
N-1812 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1812-BSCI - Est Installed Footage 5000 - Est Retired Footage 6100 - Est Svcs 59 | 2024
N-1814 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-1814-BSCI - Est Installed Footage 5263 - Est Retired Footage 5263 - Est Svcs 80 | 2024
N-1818 | #N/A | TBD | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-1818-BSCI - Est Installed Footage 5100 - Est Retired Footage 5100 - Est Svcs 67 | 2024
N-1825 | #N/A | TBD | BSCI | NE | PENDLETON | IN-PENDLETON-N-1825-BSCI - Est Installed Footage 4250 - Est Retired Footage 4250 - Est Svcs 65 | 2024
N-2153 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-2153-BSCI - Est Installed Footage 3100 - Est Retired Footage 3100 - Est Svcs 49 | 2024
N-2171 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2171-BSCI - Est Installed Footage 4000 - Est Retired Footage 4000 - Est Svcs 61 | 2024
N-2174 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2174-BSCI - Est Installed Footage 3050 - Est Retired Footage 3050 - Est Svcs 35 | 2024
N-2175 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2175-BSCI - Est Installed Footage 4100 - Est Retired Footage 4100 - Est Svcs 64 | 2024
N-2179 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2179-BSCI - Est Installed Footage 2050 - Est Retired Footage 2050 - Est Svcs 36 | 2024
N-2201 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2201-BSCI - Est Installed Footage 3300 - Est Retired Footage 2500 - Est Svcs 58 | 2024
N-2204 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2204-BSCI - Est Installed Footage 3400 - Est Retired Footage 3400 - Est Svcs 52 | 2024
N-2209 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-2209-BSCI - Est Installed Footage 2900 - Est Retired Footage 2900 - Est Svcs 44 | 2024
N-2225 | #N/A | TBD | BSCI | NE | PENDLETON | IN-PENDLETON-N-2225-BSCI - Est Installed Footage 2750 - Est Retired Footage 2750 - Est Svcs 42 | 2024
N-2227 | #N/A | TBD | BSCI | NE | PENDLETON | IN-PENDLETON-N-2227-BSCI - Est Installed Footage 5850 - Est Retired Footage 5850 - Est Svcs 90 | 2024
N-2228 | #N/A | TBD | BSCI | NE | PENDLETON | IN-PENDLETON-N-2228-BSCI - Est Installed Footage 3650 - Est Retired Footage 3650 - Est Svcs 56 | 2024
N-2231 | #N/A | TBD | BSCI | NE | TIPTON | IN-TIPTON-N-2231-BSCI - Est Installed Footage 4500 - Est Retired Footage 4500 - Est Svcs 69 | 2024
N-2237 | #N/A | TBD | BSCI | NE | EATON | IN-EATON-N-2237-BSCI - Est Installed Footage 4800 - Est Retired Footage 4800 - Est Svcs 73 | 2024
N-2238 | #N/A | 21573302052254 | BSCI | NE | FARMLAND | IN-FARMLAND-N-2238-BSCI - Est Installed Footage 3550 - Est Retired Footage 3550 - Est Svcs 55 | 2024
N-2240 | #N/A | TBD | BSCI | NE | GASTON | IN-GASTON-N-2240-BSCI - Est Installed Footage 5280 - Est Retired Footage 5280 - Est Svcs 20 | 2024
N-2241 | #N/A | TBD | BSCI | NE | GASTON | IN-GASTON-N-2241-BSCI - Est Installed Footage 5280 - Est Retired Footage 5280 - Est Svcs 20 | 2024
N-2242 | #N/A | TBD | BSCI | NE | GASTON | IN-GASTON-N-2242-BSCI - Est Installed Footage 2050 - Est Retired Footage 2050 - Est Svcs 32 | 2024
N-2243 | #N/A | 21573302052255 | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-2243-BSCI - Est Installed Footage 3746 - Est Retired Footage 3746 - Est Svcs 52 | 2024
N-2244 | #N/A | 21573302052256 | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-2244-BSCI - Est Installed Footage 1820 - Est Retired Footage 1820 - Est Svcs 28 | 2024
N-2245 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2245-BSCI - Est Installed Footage 2815 - Est Retired Footage 2815 - Est Svcs 37 | 2024
N-2246 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2246-BSCI - Est Installed Footage 4142 - Est Retired Footage 4142 - Est Svcs 60 | 2024
N-2247 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2247-BSCI - Est Installed Footage 2100 - Est Retired Footage 2100 - Est Svcs 32 | 2024
N-2248 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2248-BSCI - Est Installed Footage 3905 - Est Retired Footage 3905 - Est Svcs 58 | 2024
N-2249 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2249-BSCI - Est Installed Footage 4400 - Est Retired Footage 4400 - Est Svcs 66 | 2024
N-2250 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2250-BSCI - Est Installed Footage 4900 - Est Retired Footage 4900 - Est Svcs 75 | 2024
N-2311 | #N/A | 21573302052257 | BSCI | NE | YORKTOWN | IN-YORKTOWN-N-2311-BSCI - Est Installed Footage 8600 - Est Retired Footage 8600 - Est Svcs 132 | 2024
N-2312 | #N/A | TBD | BSCI | NE | COWAN | IN-COWAN-N-2312-BSCI - Est Installed Footage 9272 - Est Retired Footage 9272 - Est Svcs 1 | 2024
N-2323 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2323-BSCI - Est Installed Footage 6017 - Est Retired Footage 6017 - Est Svcs 0 | 2024
N-2343 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-2343-BSCI - Est Installed Footage 2245 - Est Retired Footage 2245 - Est Svcs 34 | 2024
N-2346 | #N/A | TBD | BSCI | NE | PENDLETON | IN-PENDLETON-N-2346-BSCI - Est Installed Footage 4202 - Est Retired Footage 4202 - Est Svcs 65 | 2024
N-2361 | #N/A | TBD | BSCI | NE | REDKEY | IN-REDKEY-N-2361-BSCI - Est Installed Footage 4657 - Est Retired Footage 4657 - Est Svcs 72 | 2024
N-2411 | #N/A | 21583002052213 | BSCI | NE | ARCADIA | IN-ARCADIA-N-2411-BSCI - Est Installed Footage 6300 - Est Retired Footage 6300 - Est Svcs 96 | 2024
N-2412 | #N/A | TBD | BSCI | NE | NOBLESVILLE | IN-NOBLESVILLE-N-2412-BSCI - Est Installed Footage 3700 - Est Retired Footage 3700 - Est Svcs 1 | 2024
N-2547 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-2547-BSCI - Est Installed Footage 70 - Est Retired Footage 70 - Est Svcs 0 | 2024
N-469 | #N/A | TBD | BSCI | NE | MARION | IN-MARION-N-469-BSCI - Est Installed Footage 2800 - Est Retired Footage 2800 - Est Svcs 44 | 2024
N-2551 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-2551-BSCI-GIS DATA - Est Installed Footage 1738 - Est Retired Footage 1738 - Est Svcs 0 | 2025
N-2552 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-2552-BSCI-GIS DATA - Est Installed Footage 4231 - Est Retired Footage 4231 - Est Svcs 16 | 2025
N-2553 | #N/A | TBD | BSCI | NE | ANDERSON | IN-ANDERSON-N-2553-BSCI-GIS DATA - Est Installed Footage 4815 - Est Retired Footage 4941 - Est Svcs 58 | 2025
N-2554 | #N/A | TBD | BSCI | NE | ELWOOD | IN-ELWOOD-N-2554-BSCI-GIS DATA - Est Installed Footage 624 - Est Retired Footage 624 - Est Svcs 0 | 2025
N-2555 | #N/A | TBD | BSCI | NE | ELWOOD | IN-ELWOOD-N-2555-BSCI-GIS DATA - Est Installed Footage 686 - Est Retired Footage 686 - Est Svcs 3 | 2025
N-2556 | #N/A | TBD | BSCI | NE | TIPTON | IN-TIPTON-N-2556-BSCI-GIS DATA - Est Installed Footage 2553 - Est Retired Footage 2553 - Est Svcs 21 | 2025
N-2557 | #N/A | TBD | BSCI | NE | ALEXANDRIA | IN-ALEXANDRIA-N-2557-BSCI-GIS DATA - Est Installed Footage 667 - Est Retired Footage 667 - Est Svcs 6 | 2025
N-2558 | #N/A | TBD | BSCI | NE | FRANKTON | IN-FRANTON-N-2558-BSCI-GIS DATA - Est Installed Footage 277 - Est Retired Footage 277 - Est Svcs 4 | 2025
N-2559 | #N/A | TBD | BSCI | NW | CRAWFORDSVILLE | IN-CRAWFORDSVILLE-N-2559-BSCI-GIS DATA - Est Installed Footage 280 - Est Retired Footage 280 - Est Svcs 3 | 2025
N-2560 | #N/A | TBD | BSCI | NE | ELWOOD | IN-ELWOOD-N-2560-BSCI-GIS DATA - Est Installed Footage 0 - Est Retired Footage 155 - Est Svcs 0 | 2025
N-2561 | #N/A | TBD | BSCI | NE | RICHMOND | IN-RICHMOND-N-2561-BSCI-GIS DATA - Est Installed Footage 2079 - Est Retired Footage 2844 - Est Svcs 25 | 2025
N-2564 | #N/A | TBD | BSCI | NE | HUNTINGTON | IN-HUNTINGTON-N-2564 -BSCI-GIS DATA - Est Installed Footage 8620 - Est Retired Footage 8620 - Est Svcs 42 | 2025
N-2565 | #N/A | TBD | BSCI | NE | HUNTINGTON | IN-HUNTINGTON-N-2565-BSCI-GIS DATA - Est Installed Footage 3165 - Est Retired Footage 3475 - Est Svcs 19 | 2025
N-2567 | #N/A | TBD | BSCI | SE | MARTINSVILLE | IN-MARTINSVILLE-N- 2567-BSCI-GIS DATA - Est Installed Footage 480 - Est Retired Footage 480 - Est Svcs 2 | 2025
N-2568 | #N/A | TBD | BSCI | SE | GREENFIELD | IN-GREENFIELD-N-2568-BSCI-GIS DATA - Est Installed Footage 5268 - Est Retired Footage 5268 - Est Svcs 17 | 2025
N-2569 | #N/A | TBD | BSCI | SE | GREENFIELD | IN-GREENFIELD-N-2569 -BSCI-GIS DATA - Est Installed Footage 2565 - Est Retired Footage 2565 - Est Svcs 10 | 2025
N-2570 | #N/A | TBD | BSCI | SE | GREENFIELD | IN-GREENFIELD-N- 2570 -BSCI-GIS DATA - Est Installed Footage 3912 - Est Retired Footage 3912 - Est Svcs 25 | 2025
N-2571 | #N/A | TBD | BSCI | SE | GREENFIELD | IN-GREENFIELD-N- 2571-BSCI-GIS DATA - Est Installed Footage 3767 - Est Retired Footage 3767 - Est Svcs 13 | 2025
N-2572 | #N/A | TBD | BSCI | SE | GREENFIELD | IN-GREENFIELD-N- 2572 -BSCI-GIS DATA - Est Installed Footage 2473 - Est Retired Footage 2473 - Est Svcs 5 | 2025
N-2573 | #N/A | TBD | BSCI | SE | GREENFIELD | IN-GREENFIELD-N-2573-BSCI-GIS DATA - Est Installed Footage 2432 - Est Retired Footage 2432 - Est Svcs 7 | 2025
N-2574 | #N/A | TBD | BSCI | SE | FORTVILLE | IN-FORTVILLE-N-2574-BSCI-GIS DATA - Est Installed Footage 3416 - Est Retired Footage 3416 - Est Svcs 21 | 2025
N-2575 | #N/A | TBD | BSCI | SE | NEW ALBANY | IN-NEW ALBANY-N-2575-BSCI-GIS DATA - Est Installed Footage 222 - Est Retired Footage 222 - Est Svcs 0 | 2025
N-2576 | #N/A | TBD | BSCI | NW | FRANKFORT | IN-FRANKFORT-N-2576-BSCI-GIS DATA - Est Installed Footage 25281 - Est Retired Footage 25281 - Est Svcs 17 | 2025
N-2577 | #N/A | TBD | BSCI | NW | CLOVERDALE | IN-CLOVERDALE-N-2577-BSCI-GIS DATA - Est Installed Footage 6820 - Est Retired Footage 6820 - Est Svcs 1 | 2025
N-2578 | #N/A | TBD | BSCI | NW | POLAND | IN-POLAND-N-2578-BSCI-GIS DATA - Est Installed Footage 2609 - Est Retired Footage 2609 - Est Svcs 2 | 2025
N-2579 | #N/A | TBD | BSCI | NE | MARION | IN-MARION-N- 2579 -BSCI-GIS DATA - Est Installed Footage 450 - Est Retired Footage 450 - Est Svcs 0 | 2025
N-2580 | #N/A | TBD | BSCI | NE | MARION | IN-MARION-N- 2580 -BSCI-GIS DATA - Est Installed Footage 5371 - Est Retired Footage 5371 - Est Svcs 33 | 2025
N-2581 | #N/A | TBD | BSCI | NE | GAS CITY | IN-GAS CITY-N-2581-BSCI-GIS DATA - Est Installed Footage 1245 - Est Retired Footage 1245 - Est Svcs 21 | 2025
N-2582 | #N/A | TBD | BSCI | NE | JONESBORO | IN-JONESBORO-N-2582 -BSCI-GIS DATA - Est Installed Footage 1194 - Est Retired Footage 1194 - Est Svcs 25 | 2025
N-2583 | #N/A | TBD | BSCI | NE | HARTFORD CITY | IN-HARTFORD CITY-N-2583 -BSCI-GIS DATA - Est Installed Footage 129 - Est Retired Footage 129 - Est Svcs 1 | 2025
N-2584 | #N/A | TBD | BSCI | SE | BEDFORD | IN-BEDFORD-N-2584 -BSCI-GIS DATA - Est Installed Footage 3200 - Est Retired Footage 3200 - Est Svcs 34 | 2025
N-2585 | #N/A | TBD | BSCI | NE | NOBLESVILLE | IN-NOBLESVILLE-N-2585-BSCI-GIS DATA - Est Installed Footage 120 - Est Retired Footage 236 - Est Svcs 1 | 2025
N-2586 | #N/A | TBD | BSCI | NE | ARCADIA | IN-ARCADIA-N-2586-BSCI-GIS DATA - Est Installed Footage 1228 - Est Retired Footage 1228 - Est Svcs 9 | 2025
N-2589 | #N/A | TBD | BSCI | SE | MITCHELL | IN-MITCHELL-N-2589-BSCI-GIS DATA - Est Installed Footage 4510 - Est Retired Footage 4510 - Est Svcs 0 | 2025
N-2590 | #N/A | TBD | BSCI | SE | BLOOMINGTON | IN-BLOOMINGTON-N-2590-BSCI-GIS DATA - Est Installed Footage 680 - Est Retired Footage 680 - Est Svcs 0 | 2025
N-2591 | #N/A | TBD | BSCI | SE | GREENFIELD | IN-GREENFIELD-N-2591 -BSCI-GIS DATA - Est Installed Footage 621 - Est Retired Footage 621 - Est Svcs 15 | 2025
N-2592 | #N/A | TBD | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2592-BSCI-GIS DATA - Est Installed Footage 3362 - Est Retired Footage 3362 - Est Svcs 16 | 2025
N-2593 | #N/A | TBD | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2593-BSCI-GIS DATA - Est Installed Footage 1603 - Est Retired Footage 1603 - Est Svcs 35 | 2025
N-2594 | #N/A | TBD | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2594-BSCI-GIS DATA - Est Installed Footage 3032 - Est Retired Footage 3032 - Est Svcs 46 | 2025
N-2595 | #N/A | TBD | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2595-BSCI-GIS DATA - Est Installed Footage 307 - Est Retired Footage 307 - Est Svcs 5 | 2025
N-2596 | #N/A | TBD | BSCI | SE | EDINBURGH | IN-EDINBURGH-N-2696-BSCI-GIS DATA - Est Installed Footage 250 - Est Retired Footage 250 - Est Svcs 5 | 2025
N-2597 | #N/A | TBD | BSCI | SE | GREENSBURG | IN-GREENSBURG-N-2597 -BSCI-GIS DATA - Est Installed Footage 743 - Est Retired Footage 743 - Est Svcs 0 | 2025
N-2598 | #N/A | TBD | BSCI | SE | RUSHVILLE | IN-RUSHVILLE-N-2598-BSCI-GIS DATA - Est Installed Footage 2283 - Est Retired Footage 2283 - Est Svcs 0 | 2025
N-2599 | #N/A | TBD | BSCI | SE | RUSHVILLE | IN-RUSHVILLE-N2599-BSCI-GIS DATA - Est Installed Footage 1465 - Est Retired Footage 1465 - Est Svcs 0 | 2025
N-2600 | #N/A | TBD | BSCI | SE | KNIGHTSTOWN | IN-KNIGHTSTOWN-N-2600 -BSCI-GIS DATA - Est Installed Footage 1360 - Est Retired Footage 1360 - Est Svcs 13 | 2025
N-2601 | #N/A | TBD | BSCI | SE | RUSHVILLE | IN-RUSHVILLE-N-2601-BSCI-GIS DATA - Est Installed Footage 2338 - Est Retired Footage 2338 - Est Svcs 0 | 2025
N-2602 | #N/A | TBD | BSCI | SE | KNIGHTSTOWN | IN-KNIGHTSTOWN-N-2602-BSCI-GIS DATA - Est Installed Footage 1455 - Est Retired Footage 1455 - Est Svcs 9 | 2025
N-2603 | #N/A | TBD | BSCI | SE | CAMBRIDGE CITY | IN-CAMBRIDGE CITY-N-2603-BSCI-GIS DATA - Est Installed Footage 288 - Est Retired Footage 288 - Est Svcs 1 | 2025
N-2604 | #N/A | TBD | BSCI | SE | RUSHVILLE | IN-RUSHVILLE-N2604-BSCI-GIS DATA - Est Installed Footage 385 - Est Retired Footage 385 - Est Svcs 1 | 2025
N-2605 | #N/A | TBD | BSCI | SE | COLUMBUS | IN-COLUMBUS-N-2605-BSCI-GIS DATA - Est Installed Footage 2407 - Est Retired Footage 2407 - Est Svcs 0 | 2025
N-2606 | #N/A | TBD | BSCI | NW | LAFAYETTE | IN-LAFAYETTE-N-2606-BSCI-GIS DATA - Est Installed Footage 2806 - Est Retired Footage 3116 - Est Svcs 18 | 2025
N-2608 | #N/A | TBD | BSCI | NW | LEBANON | IN-LEBANON-N- 2608 -BSCI-GIS DATA - Est Installed Footage 5302 - Est Retired Footage 5302 - Est Svcs 7 | 2025
N-2609 | #N/A | TBD | BSCI | NW | LEBANON | IN-LEBANON-N- 2609 -BSCI-GIS DATA - Est Installed Footage 1144 - Est Retired Footage 1144 - Est Svcs 17 | 2025
N-2611 | #N/A | TBD | BSCI | NW | DANVILLE | IN-DANVILLE-N-2611-BSCI-GIS DATA - Est Installed Footage 460 - Est Retired Footage 460 - Est Svcs 0 | 2025
N-2612 | #N/A | TBD | BSCI | NE | PARKER CITY | IN-PARKER CITY-N-2612-BSCI-GIS DATA - Est Installed Footage 380 - Est Retired Footage 380 - Est Svcs 5 | 2025
N-2613 | #N/A | TBD | BSCI | NE | DUNKIRK | IN-DUNKIRK-N-2613-BSCI-GIS DATA - Est Installed Footage 677 - Est Retired Footage 677 - Est Svcs 6 | 2025
N-2614 | #N/A | TBD | BSCI | NE | REDKEY | IN-REDKEY-N-2614-BSCI-GIS DATA - Est Installed Footage 1300 - Est Retired Footage 1300 - Est Svcs 15 | 2025
N-2615 | #N/A | TBD | BSCI | NE | DALEVILLE | IN-DALEVILLE-N-2615-BSCI-GIS DATA - Est Installed Footage 752 - Est Retired Footage 752 - Est Svcs 10 | 2025
N-2616 | #N/A | TBD | BSCI | NE | EATON | IN-EATON-N-2616-BSCI-GIS DATA - Est Installed Footage 288 - Est Retired Footage 288 - Est Svcs 4 | 2025
N-2617 | #N/A | TBD | BSCI | NE | ALBANY | IN-ALBANY-N-2617-BSCI-GIS DATA - Est Installed Footage 435 - Est Retired Footage 435 - Est Svcs 3 | 2025
N-2618 | #N/A | TBD | BSCI | NE | FARMLAND | IN-FARMLAND-N-2618-BSCI-GIS DATA - Est Installed Footage 431 - Est Retired Footage 431 - Est Svcs 7 | 2025
N-2620 | #N/A | TBD | BSCI | NW | FRANKFORT | IN-FRANFORT-N-2620-BSCI-GIS DATA - Est Installed Footage 495 - Est Retired Footage 494 - Est Svcs 0 | 2025
N-2621 | #N/A | TBD | BSCI | NW | GREENCASTLE | IN-GREENCASTLE-N-2621-BSCI-GIS DATA - Est Installed Footage 241 - Est Retired Footage 241 - Est Svcs 0 | 2025
N-2623 | #N/A | TBD | BSCI | NW | LEBANON | IN-LEBANON-N- 2623 -BSCI-GIS DATA - Est Installed Footage 377 - Est Retired Footage 377 - Est Svcs 0 | 2025
N-2624 | #N/A | TBD | BSCI | NW | ROCKVILLE | IN-ROCKVILLE-N-2624-BSCI-GIS DATA - Est Installed Footage 159 - Est Retired Footage 158 - Est Svcs 0 | 2025
N-2625 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2625-BSCI-GIS DATA - Est Installed Footage 3507 - Est Retired Footage 7714 - Est Svcs 21 | 2025
N-2626 | #N/A | TBD | BSCI | NW | TERRE HAUTE | IN-TERRE HAUTE-N2626-BSCI-GIS DATA - Est Installed Footage 199 - Est Retired Footage 199 - Est Svcs 0 | 2025
N-2627 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2627-BSCI-GIS DATA - Est Installed Footage 7971 - Est Retired Footage 7971 - Est Svcs 90 | 2025
N-2628 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2628-BSCI-GIS DATA - Est Installed Footage 5063 - Est Retired Footage 5063 - Est Svcs 56 | 2025
N-2629 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2629-BSCI-GIS DATA - Est Installed Footage 3579 - Est Retired Footage 6628 - Est Svcs 89 | 2025
N-2630 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2630-BSCI-GIS DATA - Est Installed Footage 4375 - Est Retired Footage 4375 - Est Svcs 46 | 2025
N-2631 | #N/A | TBD | BSCI | NE | MUNCIE | IN-MUNCIE-N-2631-BSCI-GIS DATA - Est Installed Footage 1843 - Est Retired Footage 1843 - Est Svcs 24 | 2025
N-2634 | #N/A | TBD | BSCI | NE | NEW CASTLE | IN-NEW CASTLE-N-2634-BSCI-GIS DATA - Est Installed Footage 6295 - Est Retired Footage 6295 - Est Svcs 62 | 2025
N-2635 | #N/A | TBD | BSCI | NE | NEW CASTLE | IN-NEW CASTLE-N-2635-BSCI-GIS DATA - Est Installed Footage 6126 - Est Retired Footage 5666 - Est Svcs 25 | 2025
N-2636 | #N/A | TBD | BSCI | NE | NEW CASTLE | IN-NEW CASTLE-N-2636-BSCI-GIS DATA - Est Installed Footage 5577 - Est Retired Footage 5577 - Est Svcs 57 | 2025

## SAH-7 (Public)
CEI North
Storage Modernization - Compliance Project
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
S-0311 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Construct access road to UHD-024 A.B.C. #1 | 2022
S-0312 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Construct access road to UHD-027 Fulford #1 | 2022
S-0344 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Construct access road to UND-052 Hansen #1 | 2022
S-0262 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Construct access road to WOT-015 Ponto #2 | 2022
S-0218 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-004 Couch #1 | 2022
S-0213 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-007 Schlosser #3 | 2022
S-0212 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-008 Garvey #6 | 2022
S-0370 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-016 Nabb #9 | 2022
S-0386 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-003 Miller #1 | 2022
S-0209 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-015 Ponto #2 | 2022
S-0384 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-037 Watson #1 | 2022
S-0385 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-039 M.Ponto #5 | 2022
S-0216 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD-030 Champlin #1 | 2022
S-0217 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD-051 Huffman #1 | 2022
S-0219 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-036 Smith #5 | 2022
S-0214 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-040 Young #3 | 2022
S-0215 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-079 Ward #5 | 2022
S-0220 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-080 Nehrt #6 | 2022
S-0221 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-083 Little League #1 | 2022
S-0308 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Installation of fluid level monitoring devices to report aquifer water levels | 2022
S-0242 | N/A | TBD | EQUIPMENT | SE | HINDUSTAN | Replace Wellhead on UHD-050 Hardin #1 for well logging. | 2022
S-0243 | N/A | TBD | EQUIPMENT | SE | HINDUSTAN | Replace Wellhead on UHD-051 Huffman #2 for well logging. | 2022
S-0225 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-047 DeMolay #1 for well logging. | 2022
S-0226 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-048 Peterson #2 for well logging. | 2022
S-0227 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-049 Mundy #1 for well logging. | 2022
S-0231 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-053 Hammond #1 for well logging. | 2022
S-0125 | N/A | TBD | EQUIPMENT | NW | WOLCOTT | Replace Wellhead on WOT-043 P. Mathew #4 for well logging. | 2022
S-0126 | N/A | TBD | EQUIPMENT | NW | WOLCOTT | Replace Wellhead on WOT-047 Goss #11 for well logging. | 2022
S-0203 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SE | SELLERSBURG | Install bottomhole pressure monitoring equipment in SEK-015 Friend#03 | 2022
S-0202 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | NW | HINDUSTAN | Install bottomhole pressure monitoring equipment in UHD-024 A.B.C.#01 | 2022
S-0204 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SE | UNIONVILLE | Install bottomhole pressure monitoring equipment in UND-014 Kenrich#01 | 2022
S-0392 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SE | HINDUSTAN | IN-Hindustan Storage Field -Replace old orifice measurement equipment with Ultrasonic flow meters | 2022
S-0024 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Utilize WOT-026 IGC#01 for gas observation purposes | 2022
S-0255 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | HINDUSTAN | Replace Wellhead on UHD-055 Huntington #1 for well logging. | 2022
S-0256 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | HINDUSTAN | Replace Wellhead on UHD-058 Huntington #2 for well logging. | 2022
S-0356 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-008 SCHLOSSER #3 for well logging. | 2022
S-0357 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-009 GARVEY #6 for well logging. | 2022
S-0222 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | UNIONVILLE | Replace Wellhead on UND-052 Hansen #1 for well logging. | 2022
S-0375 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | WOT-022 P. Matthew#02 Transmission Connection | 2022
S-0376 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Replace Wellhead on WOT-027 Matthew #1 for well logging. | 2022
S-0014 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Drilling of new vertical observation well - SEK022-OBS#01 | 2022
S-0012 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | UNIONVILLE | Unionville B observation drill and complete to monitor field pressures and gas migration | 2022
S-0013 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | HINDUSTAN | Drill observation well parallel to UHD-Fulford#01 to monitor communication between Unionville and Hindustan. | 2022
S-0015 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | HINDUSTAN | Drill observation well north of UHD-058 Huntington#01 (UHD-OBS#01) to monitor for gas migration North of field. | 2022
S-0316 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Construct access road to UHD-041 Musgrave #1 | 2023
S-0317 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Construct access road to UHD-044 Brough #1 | 2023
S-0346 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Construct access road to UHD-Huntington#01 and Huntington#02 | 2023
S-0318 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Construct access road to UND-066 Gross#01 | 2023
S-0390 | N/A | TBD | EMERGENCY RESPONSE | NW | Wolcott | Construct access road to WOT-003 Miller#01 | 2023
S-0391 | N/A | TBD | EMERGENCY RESPONSE | NW | Wolcott | Construct access road to WOT-014 Goss#06 | 2023
S-0192 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-009 Garvey #7 | 2023
S-0191 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-010 Couch #5 | 2023
S-0193 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricade around UND-021 Smith #2 | 2023
S-0380 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-006 Goss #2 | 2023
S-0381 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-023 F. Ponto #1 | 2023
S-0382 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-029 IGC #2 | 2023
S-0383 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-036 IGC #6 | 2023
S-0199 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD -044 Brough #1 | 2023
S-0200 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install barricades around UHD-055 Huntington #1 | 2023
S-0194 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-023 J. Skirvin #1 | 2023
S-0195 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND-047 DeMolay #1 | 2023
S-0196 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-054 Davis #1 | 2023
S-0197 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-068 Ward #4 | 2023
S-0198 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-082 Smith #7 | 2023
S-0201 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades UHD-058 Huntington #2 | 2023
S-0232 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-056 F. Skirvin #2 for well logging. | 2023
S-0233 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-057 F. Skirvin #3 for well logging. | 2023
S-0127 | N/A | TBD | EQUIPMENT | NW | WOLCOTT | Replace Wellhead on WOT-23 F. Ponto #1 for well logging. | 2023
S-0372 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SE | UNIONVILLE | Install Remote Pressure Monitoring - flow rate and casing pressure on 48 injection/withdrawal wells and 15 observation wells. | 2023
S-0373 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | UNIONVILLE | Ward #04 Drip Addition | 2023
S-0358 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-004 COUCH #1 for well logging. | 2023
S-0389 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-009 GARVEY # 7 for well logging. | 2023
S-0360 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-010 COUCH #5 for well logging. | 2023
S-0254 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | UNIONVILLE | Replace Wellhead on UND-002 Brown #2 for well logging. | 2023
S-0008 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Drilling of new vertical observation well - WOT-OBS#01 to monitor field pressures and gas migration | 2023
S-0377 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Replace Wellhead on WOT-028 Goss #8 for well logging. | 2023
S-0378 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Replace Wellhead on WOT-029 IGC #2 for well logging. | 2023
S-0005 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | UNIONVILLE | Transmission connection to Horizontal well #1 | 2023
S-0371 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | UNIONVILLE | Drill & Complete Unionville Horizontal Well #1. Replace field capacity lost through remediation (plugging) of old wells with defects | 2023
S-0264 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Construct access road to UND-032 Headley #1 | 2024
S-0265 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Construct access road to UND-049 Mundy #1 | 2024
S-0266 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Construct access road to UND-063 Bruce #1 | 2024
S-0157 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-002 Garvey #1 | 2024
S-0156 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-012 Garvey #8 | 2024
S-0155 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-013 Schlosser #4 | 2024
S-0184 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD-045 Musgrave #4 | 2024
S-0185 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD-046 Musgrave #5 | 2024
S-0186 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD-050 Hardin #1 | 2024
S-0180 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND - 053 Hammond #1 | 2024
S-0181 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND - 056F. Skirvin #2 | 2024
S-0183 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND - 081 Smith #6 | 2024
S-0182 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND- 060 Christy #3 | 2024
S-0173 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-002 Brown #2 | 2024
S-0174 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-007 Ealy #1 | 2024
S-0175 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-010 Hite #1 | 2024
S-0176 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-012 A. Neal #1 | 2024
S-0177 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-037 O. Young #1 | 2024
S-0178 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-038 O Young #2 | 2024
S-0179 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND-048 Peterson #2 | 2024
S-0238 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-059 Peterson #3 for well logging. | 2024
S-0239 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-060 Christy #3 for well logging. | 2024
S-0240 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-063 Bruce #1 for well logging. | 2024
S-0241 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-065 Christy #4 for well logging. | 2024
S-0023 | N/A | TBD | PRESSURE MONITORING / SCADA / RTU | SE | SELLERSBURG | Install surface remote pressure monitoring on 12 injection/withdrawal wells and 6 observation wells | 2024
S-0158 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | SEK-021 IGC#01 recomplete higher into formation to utilize for observation purposes. Today, the well doesn't trend with the field and is providing little value. | 2024
S-0361 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-002 GARVEY #1 for well logging. | 2024
S-0362 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-006 COUCH #2 for well logging. | 2024
S-0363 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-012 GARVEY #8 for well logging. | 2024
S-0364 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-013 SCHLOSSER #4 for well logging. | 2024
S-0379 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Replace Wellhead on WOT-031 IGC #3 for well logging. | 2024
S-0009 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Drilling of new vertical observation well - WOT-OBS#02 to monitor field pressures and gas migration | 2024
S-0010 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Drilling of new vertical observation well - WOT-OBS#03 to monitor field pressures and gas migration | 2024
S-0016 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Drilling of new vertical observation well - SEK023-OBS#02 to monitor field pressures and gas migration | 2024
S-0267 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Construct access road to UND-007 Ealy #1 | 2025
S-0268 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Construct access road to UND-016 Robertson #1 | 2025
S-0369 | N/A | TBD | EMERGENCY RESPONSE | SE | SELLERSBURG | Install barricade around SEK-15 Friend #3 | 2025
S-0171 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD-042 Musgrave #2 | 2025
S-0172 | N/A | TBD | EMERGENCY RESPONSE | SE | HINDUSTAN | Install Barricades around UHD-043 Musgrave #3 | 2025
S-0165 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND - 052 Hansen #1 | 2025
S-0167 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND - 059 Peterson #3 | 2025
S-0168 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND - 067 Richards #2 | 2025
S-0169 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND - 071 Bates #2 | 2025
S-0170 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND - 072 DeMolay #2 | 2025
S-0166 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND- 057 F. Skirvin #3 | 2025
S-0159 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-003 J. Young #1 | 2025
S-0160 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-004 Peterson #1 | 2025
S-0161 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-029 Smith #4 | 2025
S-0162 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-031 Skirvin #1 (Silurian) | 2025
S-0163 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND-032 Headley #1 (Silurian) | 2025
S-0164 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-034 Fleener #1 (Silurian) | 2025
S-0246 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-066 Gross#01 for well logging. | 2025
S-0247 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-067 Richards #2 for well logging. | 2025
S-0248 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-069 Christy #6 for well logging. | 2025
S-0249 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-070 H. Young #1 for well logging. | 2025
S-0250 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-071 Bates #2 for well logging. | 2025
S-0251 | N/A | TBD | EQUIPMENT | SE | UNIONVILLE | Replace Wellhead on UND-072 DeMolay #2 for well logging. | 2025
S-0374 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Seismic survey & processing of 10-mile x 10-mile region. | 2025
S-0365 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-011 COUCH #6 for well logging. | 2025
S-0366 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-014 SCHLOSSER #5 for well logging. | 2025
S-0011 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | NW | WOLCOTT | Drilling of new vertical observation well - WOT-OBS#04 to monitor field pressures and gas migration | 2025
S-0321 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-047 Goss #11 | 2026
S-0322 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-051 Bahler #1 | 2026
S-0323 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-052 Anker #4 | 2026
S-0324 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-053 Fulkerson #4 | 2026
S-0325 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-056 Trachsel #1 | 2026
S-0326 | N/A | TBD | EMERGENCY RESPONSE | NW | WOLCOTT | Install barricade around WOT-057 Trachsel #2 | 2026
S-0151 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND - 062 Peterson | 2026
S-0152 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND - 063 Bruce #1 | 2026
S-0153 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND - 065 Christy #4 | 2026
S-0154 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND- 069 Christy #6 | 2026
S-0147 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-006 Barrow #1 | 2026
S-0148 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install barricades around UND-013 F. Young #1 | 2026
S-0149 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-018 J. Headley #1 (Silurian) | 2026
S-0150 | N/A | TBD | EMERGENCY RESPONSE | SE | UNIONVILLE | Install Barricades around UND-049 Mundy #1 | 2026
S-0367 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-016 FRIEND #3 for well logging. | 2026
S-0368 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | SELLERSBURG | Replace Wellhead on SEK-018 COUCH #8 for well logging. | 2026
S-0017 | N/A | TBD | WELL CONSTRUCTION / REMEDIATION | SE | UNIONVILLE | Drilling of new observation well to replace the plugged UND-017 Otis Young#01 to monitor field pressures and gas migration | 2026

## SAH-8 (Public)
CEI North Bare Steel / Cast Iron Replacement Program
As of December 31, 2020
Group # | PowerPlant Project Number | Operating Center | City | Main Type (Mat'l) | Estimated Install Footage - Mains | Estimated Retire Footage - Mains | Estimated Project Services | Estimated Project Cost | ACTUAL Main Footage Installed | ACTUAL Main Footage Retired [H] | ACTUAL Project Services Replaced or Tied-In [E] | ACTUAL Service Footage Installed | ACTUAL Project Services Retired [C] | ACTUAL Service Footage Retired [D] | Actual Project Investment Cost [A] | [13 empty] | Project Status [B] | CSIA Recovery [K]
[15 empty] | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | Total
1 | 08582152700 | Anderson | Anderson | Bare Steel | 2500 | 8473 | 90 |  | 2413 | 7599 | 42 | 92 | 3 | 92 | [14 empty] | posted to CPR | Excluded from CSIA
[F] | 08582152010 | Anderson | Anderson | Bare Steel | n/a | n/a | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | [14 empty] | posted to CPR | Excluded from CSIA
2 | 08582152701 | Anderson | Anderson | Bare Steel | 6089 | 6720 | 98 |  | 5884 | 6777 | 40 | 2942 | 0 | 2938 | [14 empty] | posted to CPR | Excluded from CSIA
3 | 08582152703 | Anderson | Anderson | Bare Steel | 2860 | 2468 | 33 |  | 2923 | 2409 | 31 | 2015 | 1 | 2080 | [14 empty] | posted to CPR | Excluded from CSIA
4 | 08582152702 | Anderson | Anderson | Bare Steel | 5980 | 5778 | 67 |  | 6113 | 4926 | 60 | 1853 | 2 | 1150 | [14 empty] | posted to CPR | Excluded from CSIA
5 | 08574152706 | Marion | Jonesboro | Bare Steel | 3995 | 4170 | 69 |  | 4191 | 4238 | 74 | 1864 | 0 | 1562 | [14 empty] | posted to CPR | Excluded from CSIA
6 | 08574152707 | Marion | Hartford City | Bare Steel | 3245 | 3135 | 38 |  | 3295 | 3236 | 38 | 1986 | 1 | 1710 | [14 empty] | posted to CPR | Excluded from CSIA
7 | 08582152704 | Anderson | Anderson | Bare Steel | 5805 | 6870 | 109 |  | 5329 | 6996 | 98 | 4953 | 4 | 2701 | [14 empty] | posted to CPR | Excluded from CSIA
8 | 08582152705 | Anderson | Anderson | Bare Steel | 9995 | 11665 | 168 |  | 9206 | 12071 | 153 | 6277 | 2 | 3875 | [14 empty] | posted to CPR | Excluded from CSIA | `
9 | 08582152706 | Anderson | Anderson | Bare Steel | 1270 | 1320 | 34 |  | 1317 | 1325 | 34 | 1178 | 3 | 373 | [14 empty] | posted to CPR | Excluded from CSIA
9 | 08582152708 | Anderson | Anderson | Bare Steel | 0 | 675 | 4 |  | 0 | 675 | 25 | 128 | 0 | 13 | [14 empty] | posted to CPR | Excluded from CSIA
9 | 08582152709 | Anderson | Anderson | Bare Steel | 1510 | 1557 | 30 |  | 1549 | 1557 | 27 | 906 | 0 | 836 | [14 empty] | posted to CPR | Excluded from CSIA
9 | 08582152710 | Anderson | Anderson | Bare Steel | 1260 | 2492 | 32 |  | 1232 | 904 | 26 | 1070 | 0 | 1538 | [14 empty] | posted to CPR | Excluded from CSIA
9 | 08582152711 | Anderson | Anderson | Bare Steel | 970 | 1055 | 31 |  | 996 | 1020 | 25 | 1344 | 0 | 326 | [14 empty] | posted to CPR | Excluded from CSIA
10 | 08574152703 | Marion | Marion | Bare Steel | 6820 | 6930 | 113 |  | 7025 | 5366 | 95 | 3103 | 19 | 3933 | [14 empty] | posted to CPR | Excluded from CSIA
11 | 08574152701 | Marion | Marion | Bare Steel | 4200 | 4055 | 93 |  | 5500 | 4848 | 115 | 4533 | 4 | 5503 | [14 empty] | posted to CPR | Excluded from CSIA
12 | 08574152702 | Marion | Marion | Bare Steel | 4790 | 6210 | 48 |  | 3735 | 6812 | 38 | 1322 | 0 | 1518 | [14 empty] | posted to CPR | Excluded from CSIA
13 | 08574152700 | Marion | Marion | Bare Steel | 4840 | 5225 | 66 |  | 4784 | 4595 | 54 | 997 | 16 | 1854 | [14 empty] | posted to CPR | Excluded from CSIA
14 | 08574152704 | Marion | Marion | Bare Steel | 8430 | 7630 | 97 |  | 9338 | 7353 | 97 | 4331 | 17 | 5431 | [14 empty] | posted to CPR | Excluded from CSIA
15 | 08574152705 | Marion | Marion | Bare Steel | 1205 | 970 | 24 |  | 1224 | 0 | 20 | 707 | 2 | 876 | [14 empty] | posted to CPR | Excluded from CSIA
15 | 08574152714 | Marion | Marion | Bare Steel | 720 | 660 | 8 |  | 739 | 720 | 8 | 209 | 0 | 221 | [14 empty] | posted to CPR | Excluded from CSIA
15 | 08574152715 | Marion | Marion | Bare Steel | 1290 | 1425 | 16 |  | 1671 | 0 | 16 | 260 | 0 | 513 | [14 empty] | posted to CPR | Excluded from CSIA
16 | 08573352700 | Muncie | Muncie | Bare Steel | 5045 | 6310 | 130 |  | 5017 | 5590 | 108 | 2922 | 7 | 1018 | [14 empty] | posted to CPR | Excluded from CSIA
17 | 08573352701 | Muncie | Muncie | Bare Steel | 5295 | 5585 | 89 |  | 5358 | 5784 | 63 | 1631 | 15 | 1654 | [14 empty] | posted to CPR | Excluded from CSIA
18 | 08573352702 | Muncie | Muncie | Bare Steel | 8095 | 11996 | 141 |  | 8636 | 12489 | 120 | 1667 | 16 | 1315 | [14 empty] | posted to CPR | Excluded from CSIA
19 | 08573352703 | Muncie | Muncie | Bare Steel | 10965 | 15505 | 182 |  | 10745 | 16317 | 146 | 5915 | 20 | 3555 | [14 empty] | posted to CPR | Excluded from CSIA
20 | 08582152707 | Anderson | Pendleton | Bare Steel | 280 | 280 | 1 |  | 284 | 348 | 1 | 1 | 0 | 1 | [14 empty] | posted to CPR | Excluded from CSIA
21 | 08595052700 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 8610 | 8460 | 98 |  | 9143 | 8860 | 93 | 5253 | 3 | 3873 | [14 empty] | posted to CPR | Excluded from CSIA
22 | 08595452700 | Lebanon | Zionsville | Bare Steel | 0 | 400 | 2 |  | 0 | 341 | 6 | 178 | 0 | 109 | [14 empty] | posted to CPR | Excluded from CSIA
23 | 08595452701 | Lebanon | Lebanon | Bare Steel | 1300 | 1620 | 23 |  | 1370 | 1182 | 29 | 443 | 1 | 335 | [14 empty] | posted to CPR | Excluded from CSIA
24 | 08592052800 | Clarksville | New Albany | Cast Iron | 1505 | 1475 | 18 |  | 1480 | 1319 | 18 | 16 | 0 | 16 | [14 empty] | posted to CPR | Excluded from CSIA
25 | 08574152708 | Marion | Fairmount | Bare Steel | 185 | 190 | 3 |  | 173 | 156 | 3 | 117 | 0 | 131 | [14 empty] | posted to CPR | Excluded from CSIA
26 | 08574152709 | Marion | Marion | Bare Steel | 4530 | 4740 | 36 |  | 4519 | 6035 | 38 | 1449 | 0 | 1357 | [14 empty] | posted to CPR | Excluded from CSIA
27 | 08595052701 | Terre Haute | Terre Haute | Bare Steel | 5410 | 6200 | 153 |  | 5675 | 6206 | 148 | 13628 | 1 | 10352 | [14 empty] | posted to CPR | Excluded from CSIA
28 | 08583452700 | Elwood | Elwood | Bare Steel | 2765 | 2750 | 77 |  | 3006 | 3005 | 65 | 1676 | 3 | 1833 | [14 empty] | posted to CPR | Excluded from CSIA
29 | 08574152710 | Marion | Marion | Bare Steel | 5235 | 4790 | 43 |  | 5119 | 4789 | 18 | 1940 | 1 | 1870 | [14 empty] | posted to CPR | Excluded from CSIA
30 | 08582152712 | Anderson | Anderson | Bare Steel | 8085 | 8400 | 159 |  | 8062 | 6687 | 152 | 3830 | 4 | 1900 | [14 empty] | posted to CPR | Excluded from CSIA
31 | 08582152713 | Anderson | Anderson | Bare Steel | 7490 | 7840 | 143 |  | 7042 | 8134 | 140 | 6146 | 3 | 3903 | [14 empty] | posted to CPR | Excluded from CSIA
32 | 08582152714 | Anderson | Anderson | Bare Steel | 6580 | 10390 | 168 |  | 6573 | 7678 | 146 | 7350 | 19 | 4782 | [14 empty] | posted to CPR | Excluded from CSIA
33 | 08573352704 | Muncie | Muncie | Bare Steel | 1660 | 1760 | 23 |  | 1650 | 1850 | 25 | 430 | 0 | 455 | [14 empty] | posted to CPR | Excluded from CSIA
34 | 08574152711 | Marion | Marion | Bare Steel | 5155 | 4575 | 79 |  | 5224 | 5281 | 88 | 3522 | 8 | 4207 | [14 empty] | posted to CPR | Excluded from CSIA
35 | 08574152712 | Marion | Marion/Fairmont/Jonesboro | Bare Steel | 7995 | 7095 | 111 |  | 8869 | 8877 | 129 | 4479 | 9 | 5179 | [14 empty] | posted to CPR | Excluded from CSIA
36 | 09575252523 | New Castle | New Castle | Bare Steel | 6185 | 9320 | 96 |  | 6376 | 8998 | 92 | 5365 | 4 | 4746 | [14 empty] | posted to CPR | Excluded from CSIA
37 | 09574152523 | Marion | Marion | Bare Steel | 5005 | 10175 | 63 |  | 4895 | 10475 | 41 | 1931 | 12 | 1749 | [14 empty] | posted to CPR | Excluded from CSIA
38 | 08595552523 | Lafayette | Lafayette | Bare Steel | 8374 | 8451 | 94 |  | 8381 | 8100 | 90 | 4428 | 0 | 2797 | [14 empty] | posted to CPR | Excluded from CSIA
39 | 09595552526 | Lafayette | Lafayette | Bare Steel | 7362 | 7522 | 85 |  | 6043 | 7714 | 55 | 2189 | 0 | 1786 | [14 empty] | posted to CPR | Excluded from CSIA
40 | 09575252525 | New Castle | Hagerstown | Bare Steel | 5075 | 6175 | 88 |  | 5331 | 5933 | 74 | 2878 | 8 | 3232 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
41 | 08583352526 | Greenfield | Greenfield | Bare Steel | 7641 | 8631 | 142 |  | 10235 | 10763 | 168 | 9233 | 4 | 7228 | [14 empty] | posted to CPR | Excluded from CSIA
42 | 09575152523 | Richmond | Richmond | Bare Steel | 9207 | 10866 | 185 |  | 8734 | 11269 | 164 | 10455 | 18 | 11698 | [14 empty] | posted to CPR | Excluded from CSIA
43 | 09582152527 | Anderson | Pendleton | Bare Steel | 11292 | 17877 | 62 |  | 9901 | 14987 | 54 | 2218 | 0 | 2192 | [14 empty] | posted to CPR | Excluded from CSIA
44 | 08574152540 | Marion | Marion | Bare Steel | 11570 | 14493 | 203 |  | 12849 | 15123 | 240 | 11009 | 19 | 11202 | [14 empty] | posted to CPR | Excluded from CSIA
45 | 09573352523 | Muncie | Muncie | Bare Steel | 9950 | 11515 | 170 |  | 9889 | 11272 | 126 | 3095 | 44 | 4491 | [14 empty] | posted to CPR | Excluded from CSIA
46 | 09573352526 | Muncie | Muncie | Bare Steel | 4788 | 8352 | 52 |  | 4846 | 8360 | 47 | 1714 | 3 | 1907 | [14 empty] | posted to CPR | Excluded from CSIA
47 | 09573352527 | Muncie | Muncie | Bare Steel | 7362 | 8696 | 108 |  | 6381 | 8428 | 94 | 3295 | 9 | 4219 | [14 empty] | posted to CPR | Excluded from CSIA
48 | 08573352529 | Muncie | Muncie | Bare Steel / Plastic | 7962 | 8056 | 125 |  | 7254 | 8637 | 91 | 2900 | 15 | 4031 | [14 empty] | posted to CPR | Excluded from CSIA
49 | 08573352530 | Muncie | Muncie | Bare Steel | 6647 | 6553 | 128 |  | 6393 | 6753 | 91 | 2603 | 26 | 3507 | [14 empty] | posted to CPR | Excluded from CSIA
50 | 09583452525 | Elwood | Elwood | Bare Steel | 9615 | 10160 | 115 |  | 9437 | 8595 | 120 | 5661 | 6 | 6612 | [14 empty] | posted to CPR | Excluded from CSIA
51 | 09583452526 | Elwood | Elwood | Bare Steel | 7700 | 8570 | 106 |  | 8004 | 9010 | 90 | 6560 | 3 | 3707 | [14 empty] | posted to CPR | Excluded from CSIA
52 | 08595052526 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 7255 | 7940 | 176 |  | 9890 | 9610 | 162 | 18277 | 0 | 12866 | [14 empty] | posted to CPR | Excluded from CSIA
53 | 09595052523 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 9200 | 8730 | 124 |  | 4665 | 4355 | 66 | 6826 | 0 | 4569 | [14 empty] | posted to CPR | Excluded from CSIA
54 | 09595052530 | Terre Haute | Terre Haute | Bare Steel | 4436 | 7990 | 178 |  | 4765 | 4967 | 125 | 12312 | 15 | 23659 | [14 empty] | posted to CPR | Excluded from CSIA
55 | 09595052526 | Terre Haute | Dana, Rockville | Bare Steel | 1600 | 3120 | 27 |  | 1569 | 1569 | 25 | 3092 | 0 | 1688 | [14 empty] | posted to CPR | Excluded from CSIA
56 | 09592852523 | Seymour | Seymour | Bare Steel | 7195 | 6880 | 96 |  | 7733 | 7734 | 62 | 5873 | 1 | 6326 | [14 empty] | posted to CPR | Excluded from CSIA
57 | 09595552527 | Lafayette | Lafayette | Bare Steel / Cast Iron | 404 | 1765 | 10 |  | 398 | 1765 | 1 | 153 | 0 | 104 | [14 empty] | posted to CPR | Excluded from CSIA
58 | 09592052523 | Clarksville | Clarksville | Bare Steel / Cast Iron | 4055 | 4285 | 108 |  | 6615 | 4425 | 104 | 2937 | 0 | 3741 | [14 empty] | posted to CPR | Excluded from CSIA
59 | 09592052525 | Clarksville | Clarksville | Bare Steel / Cast Iron | 9076 | 10135 | 233 |  | 13530 | 11011 | 257 | 8447 | 3 | 10251 | [14 empty] | posted to CPR | Excluded from CSIA
61 | 09592652523 | Columbus | Columbus | Bare Steel | 645 | 624 | 13 |  | 638 | 638 | 13 | 898 | 0 | 821 | [14 empty] | posted to CPR | Excluded from CSIA
62 | 09583352523 | Greenfield | Fortville | Bare Steel | 6775 | 5181 | 6 |  | 2296 | 8611 | 33 | 1638 | 0 | 2040 | [14 empty] | posted to CPR | Excluded from CSIA
63 | 09574152527 | Marion | Fairmount | Bare Steel | 3154 | 2791 | 28 |  | 2888 | 2563 | 18 | 390 | 3 | 824 | [14 empty] | posted to CPR | Excluded from CSIA
64 | 09595752523 | Frankfort | Frankfort | Bare Steel | 7019 | 7173 | 121 |  | 7348 | 7788 | 163 | 7129 | 6 | 6607 | [14 empty] | posted to CPR | Excluded from CSIA
65 | 09582152525 | Anderson | Anderson | Bare Steel | 5981 | 6422 | 107 |  | 5840 | 6410 | 103 | 5788 | 2 | 4421 | [14 empty] | posted to CPR | Excluded from CSIA
66 | 09574252523 | Huntington | Huntington | Bare Steel | 17865 | 14445 | 231 |  | 19185 | 8750 | 235 | 13099 | 12 | 14653 | [14 empty] | posted to CPR | Excluded from CSIA
67 | 09574152526 | Marion | Marion | Bare Steel | 6972 | 8004 | 69 |  | 6414 | 9831 | 59 | 3159 | 9 | 4031 | [14 empty] | posted to CPR | Excluded from CSIA
68 | 09574152525 | Marion | Marion | Bare Steel | 3490 | 5682 | 22 |  | 5670 | 6427 | 81 | 1807 | 5 | 2016 | [14 empty] | posted to CPR | Excluded from CSIA
69 | 09574152528 | Marion | Marion | Bare Steel | 5650 | 8935 | 73 |  | 4118 | 8935 | 56 | 2711 | 10 | 2162 | [14 empty] | posted to CPR | Excluded from CSIA
70 | 09582152531 | Anderson | Anderson | Bare Steel | 3192 | 3290 | 66 |  | 3194 | 3496 | 63 | 3000 | 2 | 2445 | [14 empty] | posted to CPR | Excluded from CSIA
71 | 09582152529 | Anderson | Anderson | Bare Steel | 6651 | 9471 | 135 |  | 6460 | 8485 | 117 | 7795 | 11 | 7062 | [14 empty] | posted to CPR | Excluded from CSIA
72 | 09582152528 | Anderson | Anderson | Bare Steel | 8975 | 8873 | 204 |  | 8373 | 8833 | 116 | 4932 | 22 | 5087 | [14 empty] | posted to CPR | Excluded from CSIA
73 | 08582152540 | Anderson | Anderson | Bare Steel | 10373 | 13693 | 227 |  | 10799 | 14039 | 230 | 8817 | 8 | 7950 | [14 empty] | posted to CPR | Excluded from CSIA
74 | 09582152523 | Anderson | Anderson | Bare Steel | 5965 | 6057 | 88 |  | 5595 | 6528 | 74 | 3454 | 12 | 4068 | [14 empty] | posted to CPR | Excluded from CSIA
75 | 09592752525 | Greensburg | Greensburg | Bare Steel | 1708 | 1586 | 13 |  | 1831 | 1586 | 9 | 190 | 0 | 62 | [14 empty] | posted to CPR | Excluded from CSIA
76 | 08583352525 | Greenfield | Greenfield | Bare Steel | 570 | 6420 | 0 |  | 645 | 6500 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | Excluded from CSIA
77 | 09583252523 | Shelbyville | Shelbyville | Bare Steel | 5150 | 4450 | 74 |  | 5070 | 4137 | 69 | 2286 | 0 | 2359 | [14 empty] | posted to CPR | Excluded from CSIA
78 | 09582152530 | Anderson | Anderson | Bare Steel | 4720 | 5987 | 73 |  | 4805 | 5833 | 86 | 2314 | 8 | 1932 | [14 empty] | posted to CPR | Excluded from CSIA
79 | 09595052529 | Terre Haute | Dana | Bare Steel / Plastic | 6121 | 4711 | 15 |  | 6024 | 4390 | 9 | 930 | 1 | 1229 | [14 empty] | posted to CPR | Excluded from CSIA
80 | 09582152532 | Anderson | Anderson | Bare Steel | 4253 | 4219 | 91 |  | 7893 | 7589 | 109 | 6567 | 19 | 6902 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
81 [G] | 09582152526 | Anderson | Anderson | Bare Steel | 0 | 1968 | 5 |  | 0 | 1968 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | Excluded from CSIA
82 | 09592452528 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 5760 | 7130 | 132 |  | 6198 | 7130 | 123 | 6285 | 1 | 6459 | [14 empty] | posted to CPR | Excluded from CSIA
83 | 09595352523 | Danville | Danville | Bare Steel | 500 | 500 | 5 |  | 1075 | 1075 | 8 | 408 | 6 | 392 | [14 empty] | posted to CPR | Excluded from CSIA
84 | 09592452525 | Bloomington | Bloomington | Bare Steel / Cast Iron | 7571 | 5529 | 139 |  | 7961 | 7674 | 125 | 10671 | 1 | 9532 | [14 empty] | posted to CPR | Excluded from CSIA
85 | 09592452526 | Bloomington | Bloomington | Bare Steel / Cast Iron | 2930 | 8060 | 48 |  | 3028 | 8660 | 48 | 4325 | 0 | 3959 | [14 empty] | posted to CPR | Excluded from CSIA
86 | 09592452527 | Bloomington | Bloomington | Bare Steel | 4142 | 4202 | 38 |  | 3600 | 4202 | 36 | 2310 | 0 | 2174 | [14 empty] | posted to CPR | Excluded from CSIA
87 | 09582152533 | Anderson | Anderson | Bare Steel / Plastic | 3805 | 4185 | 40 |  | 3738 | 4185 | 30 | 1322 | 8 | 1442 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
88 | 09592052527 | Clarksville | Clarksville | Bare Steel / Cast Iron / Plastic | 2822 | 4657 | 59 |  | 4247 | 4825 | 68 | 1248 | 0 | 2135 | [14 empty] | posted to CPR | Excluded from CSIA
89 | 09592052528 | Clarksville | Clarksville | Bare Steel / Cast Iron | 3020 | 4035 | 58 |  | 2888 | 4035 | 55 | 3212 | 1 | 3393 | [14 empty] | posted to CPR | Excluded from CSIA
90 | 13595002052220 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 3600 | 4875 | 67 |  | 3546 | 4897 | 52 | 3659 | 0 | 3665 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
91 | 09595052531 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 7947 | 11240 | 225 |  | 8070 | 11207 | 229 | 23498 | 2 | 17780 | [14 empty] | posted to CPR | Excluded from CSIA
92 | 12595902052210 | Rockville | Dana | Bare Steel | 5648 | 5572 | 57 |  | 6827 | 6738 | 42 | 2751 | 6 | 3322 | [14 empty] | posted to CPR | Excluded from CSIA
93 | 10595402052210 | Lebanon | Lebanon | Bare Steel | 6995 | 6790 | 112 |  | 7163 | 7085 | 112 | 4724 | 1 | 5181 | [14 empty] | posted to CPR | Excluded from CSIA
94 | 10595402052212 | Lebanon | Lebanon | Bare Steel / Cast Iron | 5065 | 5285 | 87 |  | 5851 | 5655 | 97 | 2995 | 3 | 3574 | [14 empty] | posted to CPR | Excluded from CSIA
95 | 12595702052213 | Frankfort | Frankfort | Bare Steel / Cast Iron | 8130 | 5010 | 106 |  | 8426 | 4755 | 110 | 4678 | 0 | 6882 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
96 | 14595502052226 | Frankfort | Frankfort | Bare Steel / Cast Iron / Plastic | 9025 | 7425 | 125 |  | 11898 | 7315 | 124 | 6709 | 0 | 9293 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
98 | 09595552528 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 5190 | 7275 | 128 |  | 5290 | 7272 | 128 | 5766 | 3 | 4040 | [14 empty] | posted to CPR | Excluded from CSIA
99 | 11595502052212 | Lafayette | Lafayette | Bare Steel | 6745 | 6580 | 178 |  | 6557 | 6580 | 174 | 11193 | 2 | 9328 | [14 empty] | posted to CPR | Excluded from CSIA
100 | 11595502052210 | Lafayette | Lafayette | Bare Steel / Cast Iron | 2265 | 2220 | 45 |  | 2065 | 2215 | 43 | 2965 | 0 | 2622 | [14 empty] | posted to CPR | Excluded from CSIA
101 | 14595502052210 | Lafayette | Frankfort | Bare Steel / Cast Iron | 7740 | 5775 | 102 |  | 6597 | 5775 | 91 | 5454 | 1 | 6363 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
102 | 11595502052213 | Lafayette | Lafayette | Cast Iron | 9457 | 8815 | 162 |  | 8827 | 9314 | 147 | 10629 | 0 | 10413 | [14 empty] | posted to CPR | Excluded from CSIA
103 | 09574102052523 | Marion | Marion | Bare Steel / Plastic | 6310 | 8267 | 94 |  | 6082 | 7992 | 69 | 1481 | 13 | 1663 | [14 empty] | posted to CPR | Excluded from CSIA
104 | 14574102052212 | Marion | Marion | Bare Steel / Plastic | 4900 | 7690 | 54 |  | 6118 | 6330 | 54 | 4983 | 0 | 3666 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
105 | 11575202052214 | New Castle | New Castle | Bare Steel | 4980 | 9670 | 45 |  | 4502 | 9706 | 40 | 3770 | 1 | 4807 | [14 empty] | posted to CPR | Excluded from CSIA
106 | 11574102052213 | Marion | Marion | Bare Steel | 4386 | 6278 | 80 |  | 3863 | 5212 | 71 | 4550 | 2 | 4115 | [14 empty] | posted to CPR | Excluded from CSIA
107 | 15595002052210 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 8265 | 10020 | 106 |  | 9524 | 10020 | 92 | 5911 | 12 | 6204 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
108 | 17595002052215 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 5055 | 6396 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
109 | 12595002052222 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 1604 | 2134 | 12 |  | 1351 | 3200 | 9 | 466 | 0 | 516 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
110 | 17595002052216 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 5550 | 4198 | 101 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
111 | 12582102052213 | Anderson | Anderson | Bare Steel / Cast Iron | 2061 | 2121 | 42 |  | 2529 | 2121 | 34 | 2009 | 4 | 2262 | [14 empty] | posted to CPR | Excluded from CSIA
112 | 12595002052220 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 3506 | 5046 | 31 |  | 3584 | 4756 | 19 | 787 | 2 | 1111 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
115 | 15582102052212 | Anderson | Anderson | Bare Steel / Plastic | 6910 | 7001 | 143 |  | 6539 | 7003 | 144 | 7770 | 1 | 7445 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
116 | 12582102052215 | Anderson | Anderson | Bare Steel | 6595 | 8085 | 122 |  | 6645 | 8085 | 84 | 5127 | 26 | 5670 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
118 | 10583402052210 | Elwood | Elwood | Bare Steel | 7905 | 9085 | 167 |  | 8288 | 9072 | 156 | 9908 | 13 | 8044 | [14 empty] | posted to CPR | Excluded from CSIA
119 | 11583402052210 | Elwood | Elwood | Bare Steel | 11530 | 13504 | 170 |  | 10091 | 12285 | 138 | 10178 | 19 | 10164 | [14 empty] | posted to CPR | Excluded from CSIA
120 | 16582102052214 | Anderson | Elwood | Bare Steel / Plastic | 2455 | 2615 | 21 |  | 2465 | 2615 | 0 | 1402 | 1 | 1415 | [14 empty] | completed | CSIA - COMPLIANCE
121 | 16582102052213 | Anderson | Elwood | Bare Steel / Plastic | 3590 | 4360 | 45 |  | 3685 | 4360 | 0 | 2979 | 7 | 2674 | [14 empty] | completed | CSIA - COMPLIANCE
122 | 10592802052210 | Seymour | Seymour | Bare Steel / Cast Iron | 7625 | 8240 | 128 |  | 8292 | 8240 | 98 | 4226 | 12 | 5190 | [14 empty] | posted to CPR | Excluded from CSIA
123 | 13573302052214 | Muncie | Muncie | Bare Steel | 8005 | 9830 | 104 |  | 8016 | 9830 | 87 | 3821 | 12 | 3369 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
124 | 12583402052210 | Elwood | Elwood | Bare Steel | 6064 | 6805 | 109 |  | 5853 | 7371 | 93 | 5559 | 14 | 5668 | [14 empty] | posted to CPR | Excluded from CSIA
125 | 13575102052213 | Muncie | Richmond | Bare Steel / Plastic | 4765 | 4915 | 149 |  | 4730 | 4643 | 124 | 6418 | 25 | 8099 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
126 | 12573302052210 | Muncie | Muncie | Bare Steel | 8599 | 13967 | 197 |  | 8889 | 14349 | 160 | 9137 | 34 | 10954 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
127 | 12583302052210 | Greenfield | Fortville | Bare Steel | 4727 | 5400 | 80 |  | 4723 | 6540 | 74 | 4537 | 4 | 2936 | [14 empty] | posted to CPR | Excluded from CSIA
129 | 12595002052218 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 5550 | 7305 | 61 |  | 5784 | 8485 | 45 | 3422 | 3 | 2132 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
130 | 17595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 4145 | 5055 | 36 |  | 9008 | 8248 | 92 | 4158 | 5 | 5524 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
131 | 10573302052210 | Muncie | Muncie | Bare Steel | 3300 | 5300 | 50 |  | 3244 | 5300 | 48 | 1940 | 0 | 2249 | [14 empty] | posted to CPR | Excluded from CSIA
132 | 12595002052219 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 3721 | 4791 | 36 |  | 2858 | 5070 | 26 | 1685 | 4 | 1745 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
133 | 09592052529 | Clarksville | Clarksville | Bare Steel / Cast Iron / Plastic | 2263 | 3078 | 34 |  | 2270 | 3481 | 26 | 949 | 2 | 3126 | [14 empty] | posted to CPR | Excluded from CSIA
134 | 12595002052210 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 2671 | 8163 | 28 |  | 2258 | 8458 | 12 | 484 | 0 | 480 | [14 empty] | posted to CPR | Excluded from CSIA
136 | 14573302052222 | Muncie | Hagerstown | Bare Steel / Plastic | 7945 | 7275 | 130 |  | 7412 | 7275 | 107 | 6261 | 8 | 5300 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
137 | 12583402052212 | Madison | Elwood | Bare Steel | 4879 | 5606 | 104 |  | 5094 | 5641 | 92 | 6913 | 5 | 7074 | [14 empty] | posted to CPR | Excluded from CSIA
138 | 10592002052210 | Jeffersonville | Jeffersonville | Bare Steel / Cast Iron | 5515 | 6670 | 108 |  | 9574 | 7520 | 116 | 7131 | 0 | 8450 | [14 empty] | posted to CPR | Excluded from CSIA
139 | 10592002052212 | Jeffersonville | Jeffersonville | Bare Steel / Cast Iron | 11065 | 9130 | 196 |  | 11808 | 9130 | 191 | 5572 | 1 | 8472 | [14 empty] | posted to CPR | Excluded from CSIA
140 | 11592902052212 | Martinsville | Martinsville | Bare Steel | 4465 | 5035 | 67 |  | 5417 | 5975 | 71 | 4923 | 4 | 4759 | [14 empty] | posted to CPR | Excluded from CSIA
141 | 09595552529 | Lafayette | Lafayette | Bare Steel / Plastic | 4396 | 4787 | 17 |  | 4394 | 4390 | 14 | 1671 | 1 | 959 | [14 empty] | posted to CPR | Excluded from CSIA
142 | 09582152534 | Anderson | Anderson | Bare Steel / Plastic | 2480 | 5455 | 97 |  | 2198 | 2784 | 50 | 2138 | 4 | 2127 | [14 empty] | posted to CPR | Excluded from CSIA
143 | 15574102052212 | Marion | Marion | Bare Steel / Plastic | 3860 | 4060 | 48 |  | 3599 | 4060 | 38 | 2899 | . | 2506 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
145 | 09582102052523 | Anderson | Anderson | Bare Steel / Plastic | 3710 | 5135 | 62 |  | 3418 | 4687 | 57 | 1859 | 7 | 2580 | [14 empty] | completed | Excluded from CSIA
146 | 09582102052525 | Anderson | Anderson | Bare Steel / Plastic | 7219 | 8290 | 143 |  | 8597 | 8695 | 144 | 6634 | 8 | 5696 | [14 empty] | completed | Excluded from CSIA
147 | 09595002052523 | Terre Haute | Terre Haute | Cast Iron | 5066 | 3919 | 109 |  | 5294 | 3919 | 100 | 9951 | 7 | 7281 | [14 empty] | posted to CPR | Excluded from CSIA
148 | 09595002052525 | Terre Haute | Terre Haute | Cast Iron | 3522 | 1207 | 78 |  | 3755 | 1052 | 74 | 7053 | 1 | 6082 | [14 empty] | posted to CPR | Excluded from CSIA
149 | 09595002052526 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 3586 | 4304 | 116 |  | 3436 | 4424 | 111 | 11727 | 2 | 8468 | [14 empty] | posted to CPR | Excluded from CSIA
150 | 13595002052213 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 6430 | 8145 | 176 |  | 6657 | 8145 | 178 | 17009 | 1 | 13838 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
151 | 16595002052210 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 9860 | 9830 | 213 |  | 9860 | 9830 | 187 | 9104 | 6 | 12171 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
152 | 10592402052210 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 4465 | 4850 | 62 |  | 4630 | 5020 | 62 | 5551 | 0 | 3792 | [14 empty] | posted to CPR | Excluded from CSIA
153 | 12574102052216 | Marion | Marion | Bare Steel | 6081 | 6358 | 91 |  | 6367 | 6335 | 95 | 5829 | 5 | 5839 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
154 | 12574102052215 | Marion | Marion | Bare Steel / Cast Iron / Plastic | 5540 | 9320 | 96 |  | 6316 | 9320 | 91 | 4331 | 0 | 3612 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
155 | 11574102052214 | Marion | Marion | Bare Steel | 7232 | 9453 | 126 |  | 6399 | 15757 | 107 | 7449 | 7 | 7802 | [14 empty] | posted to CPR | Excluded from CSIA
156 | 11574102052215 | Marion | Marion | Bare Steel | 1064 | 6353 | 30 |  | 1102 | 1002 | 21 | 1667 | 5 | 1558 | [14 empty] | posted to CPR | Excluded from CSIA
157 | 09592002052523 | Clarksville | Clarksville | Bare Steel / Cast Iron | 7745 | 5010 | 109 |  | 8177 | 4850 | 102 | 2775 | 1 | 4669 | [14 empty] | posted to CPR | Excluded from CSIA
158 | 09592002052525 | Clarksville | Clarksville | Bare Steel / Plastic | 2790 | 2790 | 61 |  | 4722 | 2738 | 64 | 830 | 0 | 1638 | [14 empty] | posted to CPR | Excluded from CSIA
159 | 09592002052526 | Clarksville | Clarksville | Bare Steel / Cast Iron / Plastic | 1525 | 1705 | 31 |  | 2328 | 2110 | 32 | 947 | 0 | 1629 | [14 empty] | posted to CPR | Excluded from CSIA
160 | 10595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 6185 | 2280 | 58 |  | 6109 | 2280 | 64 | 6340 | 1 | 4581 | [14 empty] | completed | Excluded from CSIA
161 | 09595402052523 | Lebanon | Zionsville | Bare Steel / Plastic | 4720 | 4620 | 86 |  | 4682 | 4620 | 88 | 3188 | 0 | 6696 | [14 empty] | posted to CPR | Excluded from CSIA
162 | 10595002052011 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 540 | 730 | 0 |  | 535 | 716 | 1 | 35 | 0 | 43 | [14 empty] | posted to CPR | Excluded from CSIA
200 | 14573302052212 | Muncie | Muncie | Bare Steel / Plastic | 6470 | 7515 | 82 |  | 5870 | 7078 | 81 | 4343 | 1 | 4022 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
201 | 17573302052213 | Muncie | Muncie | Bare Steel / Plastic | 4205 | 4575 | 29 |  | 5124 | 5200 | 20 | 1256 | 0 | 1041 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
202 | 16573302052212 | Muncie | Muncie | Bare Steel / Plastic | 1440 | 4755 | 38 |  | 1497 | 4755 | 33 | 1925 | 2 | 1747 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
203 | 15573302052212 | Muncie | Muncie | Bare Steel / Plastic | 6520 | 5545 | 125 |  | 6500 | 5545 | 124 | 8532 | 4 | 6557 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
211 | 14582102052212 | Anderson | Anderson | Bare Steel / Plastic | 5185 | 6635 | 60 |  | 5007 | 2780 | 55 | 3469 | 6 | 3304 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
212 | 13582102052210 | Anderson | Anderson | Bare Steel / Plastic | 4570 | 3930 | 55 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
285 | 17592402052219 | Bloomington | Bloomington | Bare Steel / Plastic | 3335 | 3280 | 17 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
287 | 12582102052216 | Anderson | Anderson | Bare Steel | 3364 | 6044 | 90 |  | 4004 | 6044 | 76 | 3719 | 22 | 4128 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
288 | 12592402052212 | Bloomington | Bloomington | Bare Steel / Cast Iron | 3827 | 4572 | 66 |  | 4062 | 4184 | 56 | 3206 | 0 | 2535 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
289 | 10583302052210 | Greenfield | Fortville | Bare Steel | 325 | 440 | 12 |  | 270 | 425 | 11 | 393 | 1 | 357 | [14 empty] | posted to CPR | Excluded from CSIA
290 | 12592402052214 | Bloomington | Bloomington | Bare Steel / Cast Iron | 3185 | 4230 | 22 |  | 2664 | 3929 | 17 | 1289 | 0 | 721 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
303 | 17573302052221 | Muncie | Muncie | Bare Steel / Plastic | 0 | 3121 | 0 |  | 3191 | 3120 | 7 | 2019 | 0 | 2830 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
381 | 17582102052220 | Anderson | Anderson | Plastic | 4960 | 6944 | 114 |  | 4440 | 6940 | 18 | 6479 | 0 | 6209 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
382 | 17582102052221 | Anderson | Anderson | Plastic | 5410 | 8743 | 98 |  | 6285 | 9685 | 6 | 4662 | 0 | 4821 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
385 | 11592402052210 | Bloomington | Bloomington | Bare Steel / Cast Iron | 471 | 1833 | 4 |  | 549 | 1832 | 3 | 278 | 0 | 137 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
386 | 10592002052213 | New Albany | New Albany | Bare Steel / Cast Iron | 6440 | 5405 | 75 |  | 5664 | 5405 | 75 | 1270 | 0 | 1979 | [14 empty] | posted to CPR | Excluded from CSIA
387 | 17595302052210 | Danville | Danville | Bare Steel / Plastic | 4560 | 4445 | 53 |  | 4507 | 4615 | 51 | 2854 | 1 | 2833 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
389 | 15583302052215 | Greenfield | Greenfield | Bare Steel / Plastic | 2675 | 2955 | 43 |  | 2445 | 2820 | 38 | 3891 | 1 | 2390 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
390 | 10595502052210 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 3090 | 4215 | 42 |  | 3065 | 4200 | 32 | 1518 | 1 | 1422 | [14 empty] | posted to CPR | Excluded from CSIA
391 | 12595502052210 | Layfayette | Lafayette | Bare Steel / Cast Iron | 9070 | 9465 | 110 |  | 8909 | 6456 | 111 | 9735 | 0 | 9845 | [14 empty] | posted to CPR | Excluded from CSIA
392 | 15595502052219 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 7813 | 4520 | 68 |  | 7813 | 4520 | 66 | 4253 | 2 | 5662 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
393 | 13595502052210 | Lafayette | Lafayette | Bare Steel / Cast Iron | 3370 | 6135 | 58 |  | 2855 | 6135 | 19 | 1171 | 0 | 1061 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
394 | 14595502052215 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 10300 | 7250 | 109 |  | 10315 | 7055 | 106 | 6225 | 1 | 8394 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
395 | 14595502052227 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 11880 | 7765 | 154 |  | 12154 | 7325 | 152 | 6783 | 0 | 8401 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
397 | 11595402052212 | Lebanon | Lebanon | Bare Steel / Cast Iron | 6734 | 4733 | 82 |  | 6893 | 4863 | 78 | 4531 | 6 | 5001 | [14 empty] | posted to CPR | Excluded from CSIA
398 | 12574102052210 | Marion | Marion | Bare Steel | 1966 | 2555 | 31 |  | 2160 | 2555 | 27 | 1557 | 5 | 1966 | [14 empty] | posted to CPR | Excluded from CSIA
399 | 13574102052215 | Marion | marion | Bare Steel / Plastic | 5130 | 4860 | 20 |  | 4393 | 4855 | 17 | 719 | 1 | 1103 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
402 | 12573302052212 | Muncie | Muncie | Bare Steel | 7788 | 7235 | 102 |  | 7607 | 7376 | 74 | 5203 | 18 | 4566 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
403 | 14573302052213 | Muncie | Muncie | Bare Steel / Plastic | 6590 | 6525 | 128 |  | 5934 | 5765 | 145 | 6850 | 10 | 7246 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
404 | 16573302052215 | Muncie | Muncie | Bare Steel | 4345 | 7139 | 57 |  | 3920 | 7135 | 39 | 3099 | 2 | 1689 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
404 | 17573302052222 | Muncie | Muncie | Plastic | 2890 | 7340 | 45 |  | 3920 | 7135 | 2 | 3099 |  | 1689 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
406 | 12573302052215 | Muncie | Muncie | Bare Steel / Cast Iron / Plastic | 6145 | 8125 | 105 |  | 6292 | 8405 | 121 | 6826 | 6 | 6673 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
407 | 11573302052213 | Muncie | Muncie | Bare Steel | 2260 | 3242 | 38 |  | 2514 | 4183 | 35 | 1617 | 3 | 1671 | [14 empty] | posted to CPR | Excluded from CSIA
408 | 11573302052212 | Muncie | Muncie | Bare Steel | 3537 | 4920 | 50 |  | 3302 | 5009 | 38 | 1593 | 6 | 2120 | [14 empty] | posted to CPR | Excluded from CSIA
409 | 12573302052216 | Muncie | Muncie | Bare Steel | 2610 | 2920 | 74 |  | 2317 | 2803 | 68 | 3851 | 5 | 3939 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
410 | 13573302052210 | Muncie | Muncie | Bare Steel | 6849 | 8240 | 117 |  | 6666 | 8240 | 98 | 5806 | 3 | 5136 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
411 | 15573302052213 | Muncie | Muncie | Bare Steel / Plastic | 5625 | 4240 | 62 |  | 5612 | 4240 | 84 | 4745 | 4 | 5207 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
412 | 14573302052223 | Muncie | Muncie | Bare Steel / Cast Iron | 2205 | 4020 | 53 |  | 2027 | 4940 | 23 | 1615 | 2 | 1245 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
413 | 11573302052210 | Muncie | Muncie | Bare Steel | 4247 | 5686 | 79 |  | 4016 | 6650 | 68 | 3341 | 8 | 4250 | [14 empty] | posted to CPR | Excluded from CSIA
415 | 11573302052214 | Muncie | Muncie | Bare Steel | 2673 | 3559 | 43 |  | 3015 | 3629 | 37 | 1655 | 5 | 2032 | [14 empty] | posted to CPR | Excluded from CSIA
416 | 13595002052217 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 0 | 995 | 6 |  | 0 | 995 | 1 | 97 | 0 | 135 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
417 | 17583302052210 | Greenfield | Rushville | Bare Steel / Plastic | 7600 | 6140 | 98 |  | 7302 | 4739 | 92 | 4175 | 2 | 5635 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
418 | 14583302052217 | Rushville | Rushville | Bare Steel / Plastic | 2395 | 2565 | 43 |  | 3058 | 3234 | 50 | 2893 | 3 | 2670 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
419 | 14583302052218 | Rushville | Rushville | Bare Steel / Plastic | 2610 | 3130 | 51 |  | 3118 | 3225 | 47 | 2759 | 2 | 2899 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
420 | 10592702052210 | Greensburg | Greensburg | Bare Steel / Cast Iron / Plastic | 616 | 666 | 8 |  | 645 | 616 | 4 | 201 | 0 | 114 | [14 empty] | posted to CPR | Excluded from CSIA
426 | 11575302052210 | Rushville | Rushville | Bare Steel | 7015 | 7015 | 12 |  | 6763 | 6815 | 4 | 527 | 0 | 529 | [14 empty] | posted to CPR | Excluded from CSIA
427 | 11575302052212 | Rushville | Rushville | Bare Steel | 4025 | 4015 | 2 |  | 4226 | 4223 | 0 | 0 | 1 | 25 | [14 empty] | posted to CPR | Excluded from CSIA
428 | 13595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 940 | 4545 | 11 |  | 1070 | 4545 | 7 | 303 | 1 | 398 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
429 | 10592702052212 | Greensburg | Greensburg | Bare Steel / Plastic | 3725 | 3865 | 65 |  | 3567 | 3794 | 58 | 1845 | 0 | 1341 | [14 empty] | posted to CPR | Excluded from CSIA
430 | 12575302052210 | Rushville | Rushville | Bare Steel | 5670 | 5705 | 5 |  | 7121 | 6775 | 8 | 1241 | 0 | 897 | [14 empty] | posted to CPR | Excluded from CSIA
431 | 11592702052212 | Greensburg | Greensburg | Bare Steel | 1900 | 1990 | 45 |  | 1902 | 1990 | 44 | 1288 | 1 | 911 | [14 empty] | posted to CPR | Excluded from CSIA
432 | 10592702052213 | Greensburg | Greensburg | Bare Steel / Plastic | 3025 | 3650 | 40 |  | 2776 | 3615 | 38 | 770 | 0 | 887 | [14 empty] | posted to CPR | Excluded from CSIA
433 | 11592702052210 | Greensburg | Greensburg | Bare Steel | 2549 | 3170 | 65 |  | 2672 | 3170 | 45 | 620 | 0 | 472 | [14 empty] | posted to CPR | Excluded from CSIA
434 | 13583302052210 | Greenfield | Greenfield | Bare Steel | 8410 | 6780 | 122 |  | 8914 | 9142 | 124 | 11530 | 3 | 8596 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
435 | 16583302052215 | Greenfield | Greenfield | Bare Steel / Plastic | 6190 | 6455 | 125 |  | 7844 | 6798 | 107 | 7484 | 2 | 8008 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
439 | 12575102052212 | Muncie | Richmond | Wrought Iron | 6420 | 11023 | 161 |  | 6429 | 11308 | 131 | 8073 | 19 | 8398 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
442 | 11575202052215 | New Castle | New Castle | Bare Steel | 6531 | 6357 | 92 |  | 6317 | 6284 | 73 | 5529 | 8 | 6238 | [14 empty] | posted to CPR | Excluded from CSIA
443 | 13583302052212 | Greenfield | Greenfield | Bare Steel / Plastic | 4360 | 6230 | 55 |  | 4751 | 6230 | 55 | 3220 | 0 | 3101 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
458 | 10595502052212 | Lafayette | Lafayette | Bare Steel / Cast Iron | 2395 | 4750 | 31 |  | 2857 | 4725 | 27 | 1999 | 4 | 1877 | [14 empty] | posted to CPR | Excluded from CSIA
461 | 12574202052210 | Huntington | Huntington | Bare Steel / Cast Iron | 5485 | 3260 | 106 |  | 5865 | 5067 | 90 | 4907 | 5 | 3158 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
463 | 14574102052222 | Marion | Huntington | Bare Steel / Plastic | 4730 | 5155 | 69 |  | 4718 | 4685 | 67 | 4026 | 1 | 4118 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
464 | 14574102052216 | Marion | Huntington | Bare Steel / Plastic | 5500 | 6600 | 109 |  | 5268 | 6600 | 106 | 8484 | 2 | 6792 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
465 | 14574102052214 | Marion | Huntington | Bare Steel / Plastic | 1320 | 4185 | 29 |  | 1028 | 4185 | 29 | 1917 | 0 | 1312 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
466 | 14574102052217 | Huntington | Huntington | Bare Steel / Plastic | 3310 | 8710 | 71 |  | 3292 | 8710 | 64 | 3782 | 5 | 3606 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
470 | 12574102052217 | Marion | Fairmount | Bare Steel | 4760 | 6145 | 83 |  | 4776 | 6145 | 60 | 3811 | 4 | 3888 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
471 | 13574102052212 | Marion | Fairmount | Bare Steel / Cast Iron / Plastic | 10435 | 10935 | 137 |  | 10414 | 10935 | 123 | 9030 | 11 | 7075 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
472 | 13574102052214 | Marion | Fairmount | Bare Steel / Plastic | 5695 | 6300 | 75 |  | 4864 | 6300 | 63 | 3571 | 2 | 2828 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
473 | 14574102052215 | Marion | Fairmount | Bare Steel | 5055 | 5185 | 83 |  | 5010 | 5160 | 81 | 4737 | 6 | 5085 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
474 | 16574102052210 | Marion | Fairmount | Bare Steel / Cast Iron / Plastic | 1935 | 3685 | 30 |  | 1769 | 3360 | 28 | 1474 | 2 | 1442 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
475 | 13574102052216 | Marion | Hartford City | Bare Steel / Plastic | 3385 | 2875 | 47 |  | 3289 | 2875 | 39 | 2313 | 4 | 2734 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
476 | 14574102052219 | Marion | Hartford City | Bare Steel | 3170 | 3980 | 42 |  | 2984 | 3980 | 2846 | 1474 | 16 | 2053 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
477 | 14574102052220 | Marion | Hartford City | Bare Steel / Plastic | 5305 | 6745 | 78 |  | 5091 | 6745 | 75 | 3650 | 13 | 3981 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
478 | 13574102052210 | Marion | Marion | Bare Steel | 2020 | 3225 | 51 |  | 1680 | 4760 | 71 | 5192 | 15 | 5485 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
479 | 17583302052212 | Greenfield | Rushville | Bare Steel / Plastic | 8380 | 5770 | 88 |  | 8347 | 5655 | 80 | 3564 | 1 | 4656 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
480 | 11595202052210 | Greencastle | Greencastle | Bare Steel | 3127 | 4376 | 53 |  | 3646 | 4376 | 44 | 3355 | 2 | 2317 | [14 empty] | posted to CPR | Excluded from CSIA
486 | 11595402052213 | Lebanon | Lebanon | Bare Steel | 4068 | 4549 | 68 |  | 4213 | 4316 | 62 | 3823 | 2 | 4694 | [14 empty] | posted to CPR | Excluded from CSIA
487 | 11595402052210 | Lebanon | Lebanon | Bare Steel / Cast Iron | 11700 | 11100 | 172 |  | 12444 | 10845 | 170 | 8982 | 1 | 10764 | [14 empty] | posted to CPR | Excluded from CSIA
488 | 10583202052210 | Shelbyville | Shelbyville | Bare Steel / Cast Iron | 5050 | 5880 | 154 |  | 5702 | 5114 | 149 | 6709 | 0 | 6414 | [14 empty] | posted to CPR | Excluded from CSIA
489 | 11583202052214 | Shelbyville | Shelbyville | Bare Steel / Cast Iron / Plastic | 7162 | 8472 | 186 |  | 6805 | 8564 | 165 | 9140 | 15 | 9684 | [14 empty] | posted to CPR | Excluded from CSIA
490 | 11583202052212 | Shelbyville | Shelbyville | Cast Iron | 4474 | 2473 | 87 |  | 4565 | 3104 | 74 | 4891 | 0 | 4702 | [14 empty] | posted to CPR | Excluded from CSIA
491 | 11583202052213 | Shelbyville | Shelbyville | Bare Steel | 2390 | 1440 | 54 |  | 2190 | 611 | 45 | 3174 | 1 | 3057 | [14 empty] | posted to CPR | Excluded from CSIA
492 | 11583202052210 | Shelbyville | Shelbyville | Bare Steel / Cast Iron | 4891 | 7596 | 87 |  | 5349 | 8373 | 89 | 3418 | 0 | 3490 | [14 empty] | posted to CPR | Excluded from CSIA
493 | 14592402052216 | Martinsville | Martinsville | Bare Steel / Plastic | 4335 | 4715 | 65 |  | 4411 | 4900 | 65 | 4681 | 0 | 3929 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
494 | 12595702052210 | Frankfort | Frankfort | Bare Steel / Cast Iron | 4697 | 4613 | 80 |  | 4671 | 4613 | 76 | 5289 | 2 | 5849 | [14 empty] | posted to CPR | Excluded from CSIA
495 | 12595702052214 | Frankfort | Frankfort | Bare Steel / Cast Iron | 12500 | 6510 | 114 |  | 12583 | 5957 | 112 | 5806 | 4 | 8785 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
496 | 10592502052210 | Bedford | Bedford | Bare Steel / Cast Iron | 4440 | 5340 | 114 |  | 5541 | 6087 | 108 | 5871 | 1 | 4552 | [14 empty] | posted to CPR | Excluded from CSIA
497 | 11595902052212 | Rockville | Rockville | Bare Steel | 9089 | 9638 | 107 |  | 11490 | 12921 | 114 | 11594 | 1 | 10784 | [14 empty] | posted to CPR | Excluded from CSIA
499 | 10595302052210 | Danville | Danville | Bare Steel / Plastic | 4940 | 5470 | 86 |  | 5240 | 5470 | 76 | 2838 | 0 | 2316 | [14 empty] | posted to CPR | Excluded from CSIA
500 | 10595302052212 | Danville | Danville | Bare Steel / Plastic | 1925 | 2285 | 37 |  | 2116 | 2285 | 31 | 401 | 0 | 240 | [14 empty] | posted to CPR | Excluded from CSIA
501 | 11595302052210 | Brownsburg | Brownsburg | Bare Steel | 3417 | 5166 | 84 |  | 3416 | 5166 | 103 | 6446 | 0 | 5764 | [14 empty] | posted to CPR | Excluded from CSIA
502 | 11592002052210 | Jeffersonville | Jeffersonville | Bare Steel / Cast Iron / Plastic | 1792 | 2235 | 24 |  | 1826 | 2272 | 23 | 602 | 0 | 839 | [14 empty] | posted to CPR | Excluded from CSIA
503 | 10573302052212 | Muncie | Muncie | Bare Steel | 2995 | 2785 | 65 |  | 3664 | 4530 | 84 | 6437 | 8 | 6718 | [14 empty] | posted to CPR | Excluded from CSIA
507 | 17583302052217 | Greenfield | Dublin | Bare Steel / Plastic | 6175 | 6843 | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
508 | 17583302052216 | Greenfield | Dublin | Bare Steel / Plastic | 2685 | 2844 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
509 | 16583302052216 | Greenfield | Dublin | Bare Steel / Plastic | 2560 | 3225 | 23 |  | 2846 | 3082 | 26 | 1387 | 2 | 1528 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
510 | 10592002052214 | New Albany | New Albany | Bare Steel / Cast Iron | 7965 | 4925 | 107 |  | 6435 | 4965 | 104 | 3938 | 1 | 4482 | [14 empty] | posted to CPR | Excluded from CSIA
516 | 11595302052212 | Danville | Danville | Bare Steel | 7343 | 7498 | 128 |  | 7274 | 7498 | 128 | 11397 | 2 | 10370 | [14 empty] | posted to CPR | Excluded from CSIA
517 | 11595302052213 | Danville | Danville | Bare Steel | 7252 | 6943 | 100 |  | 8261 | 7135 | 133 | 5598 | 4 | 4630 | [14 empty] | posted to CPR | Excluded from CSIA
518 | 11592002052215 | Clarksville | Jeffersonville | Bare Steel / Cast Iron | 11800 | 9035 | 173 |  | 11429 | 9320 | 173 | 6932 | 5 | 8409 | [14 empty] | posted to CPR | Excluded from CSIA
519 | 11592002052216 | Jeffersonville | Jeffersonville | Cast Iron | 2010 | 2910 | 11 |  | 2371 | 2930 | 9 | 226 | 0 | 221 | [14 empty] | posted to CPR | Excluded from CSIA
547 | 11595002052210 | Terre Haute | Terre Haute | Cast Iron | 7145 | 6475 | 168 |  | 7763 | 6475 | 164 | 14092 | 10 | 11914 | [14 empty] | posted to CPR | Excluded from CSIA
548 | 11592002052214 | Jeffersonville | Jeffersonville | Cast Iron | 4207 | 3590 | 50 |  | 4008 | 3590 | 49 | 1985 | 0 | 2995 | [14 empty] | posted to CPR | Excluded from CSIA
549 | 13592002052212 | Clarksville | New Albany | Bare Steel / Cast Iron | 1811 | 1989 | 13 |  | 1737 | 1989 | 8 | 354 | 1 | 530 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
550 | 11592002052212 | New Albany | New Albany | Cast Iron | 8164 | 6449 | 127 |  | 9130 | 6551 | 116 | 4192 | 4 | 6952 | [14 empty] | posted to CPR | Excluded from CSIA
551 | 13595002052210 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 8010 | 4780 | 118 |  | 8022 | 4780 | 109 | 4368 | 6 | 7430 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
553 | 11574102052210 | Marion | Marion | Bare Steel | 1432 | 644 | 9 |  | 1420 | 682 | 7 | 357 | 1 | 362 | [14 empty] | posted to CPR | Excluded from CSIA
554 | 11595002052212 | Terre Haute | Terre Haute | Cast Iron | 4925 | 4360 | 117 |  | 5998 | 5010 | 124 | 9214 | 3 | 6475 | [14 empty] | posted to CPR | Excluded from CSIA
556 | 15595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 8285 | 9210 | 220 |  | 8871 | 10385 | 236 | 9740 | 6 | 10075 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
557 | 13595002052215 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 7635 | 7680 | 124 |  | 7635 | 7680 | 187 | 10284 | 6 | 12300 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
558 | 13595002052216 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 5070 | 4655 | 84 |  | 5276 | 4655 | 74 | 4612 | 4 | 4726 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
560 | 11575102052212 | Richmond | Richmond | Bare Steel | 4045 | 4065 | 95 |  | 5653 | 4265 | 78 | 2546 | 15 | 5099 | [14 empty] | posted to CPR | Excluded from CSIA
561 | 11575102052210 | Richmond | Richmond | Bare Steel | 4989 | 5703 | 73 |  | 4392 | 6280 | 66 | 3052 | 3 | 3651 | [14 empty] | posted to CPR | Excluded from CSIA
562 | 12595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 4192 | 8318 | 11 |  | 4153 | 7698 | 9 | 567 | 0 | 405 | [14 empty] | posted to CPR | Excluded from CSIA
563 | 12595002052221 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 7675 | 7995 | 96 |  | 7490 | 8229 | 58 | 3809 | 14 | 4631 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
564 | 13595002052218 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 6665 | 12780 | 97 |  | 5920 | 13740 | 57 | 4459 | 12 | 5134 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
565 | 14595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 7495 | 6600 | 129 |  | 8114 | 6300 | 129 | 8219 | 0 | 9959 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
566 | 19595002052217 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 5365 | 1818 | 2706 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
568 | 12595502052212 | Lafayette | Lafayette | Bare Steel / Cast Iron | 7953 | 9951 | 151 |  | 7592 | 9951 | 132 | 7814 | 0 | 7553 | [14 empty] | posted to CPR | Excluded from CSIA
569 | 11582102052213 | Anderson | Anderson | Bare Steel | 6993 | 8413 | 106 |  | 6786 | 8440 | 76 | 3155 | 11 | 4086 | [14 empty] | posted to CPR | Excluded from CSIA
570 | 12575202052213 | New Castle | New Castle | Bare Steel | 5995 | 6840 | 56 |  | 6234 | 7829 | 85 | 8203 | 1 | 7311 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
571 | 12575202052210 | New Castle | New Castle | Bare Steel / Cast Iron | 6605 | 7417 | 97 |  | 6358 | 7462 | 84 | 7802 | 9 | 8592 | [14 empty] | posted to CPR | Excluded from CSIA
572 | 12575202052212 | New Castle | New Castle | Bare Steel / Cast Iron / Plastic | 8270 | 9120 | 114 |  | 8605 | 9120 | 131 | 9654 | 1 | 9870 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
573 | 15592402052219 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 6955 | 7465 | 127 |  | 7765 | 7465 | 53 | 3312 | 0 | 3084 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
574 | 12595802052210 | Crawfordsville | Crawfordsville | Bare Steel / Cast Iron | 5285 | 8050 | 106 |  | 4833 | 8120 | 105 | 6905 | 1 | 6886 | [14 empty] | posted to CPR | Excluded from CSIA
575 | 12595802052213 | Crawfordsville | Crawfordsville | Bare Steel / Cast Iron | 9860 | 9958 | 140 |  | 9759 | 9958 | 140 | 7354 | 7 | 8356 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
576 | 11595802052210 | Crawfordsville | Crawfordsville | Bare Steel | 4848 | 5077 | 54 |  | 3548 | 5073 | 45 | 2505 | 3 | 2710 | [14 empty] | posted to CPR | Excluded from CSIA
577 | 14595802052212 | Crawfordsville | Crawfordsville | Bare Steel / Cast Iron / Plastic | 7475 | 7450 | 143 |  | 8389 | 8275 | 145 | 9577 | 4 | 10092 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
578 | 14595302052216 | Crawfordsville | Crawfordsville | Bare Steel / Cast Iron / Plastic | 4705 | 5530 | 96 |  | 4705 | 5815 | 97 | 6679 | 0 | 6301 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
579 | 14595302052213 | Danville | Crawfordsville | Bare Steel / Cast Iron / Plastic | 4835 | 5410 | 70 |  | 6080 | 5410 | 67 | 3941 | 1 | 4591 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
580 | 12595802052212 | Crawfordsville | Crawfordsville | Bare Steel / Cast Iron | 5500 | 5585 | 89 |  | 5585 | 7050 | 87 | 4793 | 3 | 4958 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
581 | 11592402052212 | Bloomington | Bloomington | Bare Steel | 6128 | 5878 | 86 |  | 7442 | 6160 | 83 | 5395 | 3 | 4689 | [14 empty] | posted to CPR | Excluded from CSIA
582 | 12592402052213 | Bloomington | Bloomington | Bare Steel / Cast Iron | 4175 | 4320 | 73 |  | 5118 | 5615 | 78 | 3492 | 1 | 3170 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
583 | 14592402052212 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 7170 | 6655 | 108 |  | 6991 | 6782 | 94 | 4605 | 1 | 4200 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
584 | 14592402052213 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 4835 | 6300 | 68 |  | 4739 | 5952 | 66 | 2444 | 1 | 2345 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
585 | 16592402052210 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 2505 | 5273 | 44 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
586 | 15592402052213 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 5460 | 6557 | 99 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
587 | 11582102052210 | Anderson | Anderson | Bare Steel | 7851 | 8137 | 101 |  | 7878 | 8137 | 96 | 5095 | 8 | 5061 | [14 empty] | posted to CPR | Excluded from CSIA
588 | 17582102052223 | Anderson | Anderson | Bare Steel / Cast Iron / Plastic | 4740 | 8134 | 63 |  | 5119 | 8130 | -57 | 5377 | 0 | 3095 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
589 | 17582102052213 | Anderson | Anderson | Bare Steel / Plastic | 7220 | 5760 | 141 |  | 7090 | 5760 | 143 | 6208 | 0 | 7968 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
590 | 11582102052214 | Anderson | Anderson | Bare Steel | 6005 | 6375 | 106 |  | 6324 | 6375 | 68 | 5498 | 26 | 6283 | [14 empty] | posted to CPR | Excluded from CSIA
591 | 11574102052216 | Marion | Marion | Bare Steel | 4919 | 5025 | 67 |  | 5474 | 5645 | 60 | 3654 | 11 | 4526 | [14 empty] | posted to CPR | Excluded from CSIA
592 | 12574102052212 | Marion | Marion | Bare Steel | 5370 | 4000 | 106 |  | 7110 | 5340 | 119 | 7895 | 14 | 7793 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
593 | 12574102052214 | Marion | Marion | Bare Steel / Plastic | 2520 | 6295 | 29 |  | 2381 | 6295 | 31 | 1712 | 15 | 2185 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
594 | 14582102052216 | Anderson | Alexandria | Bare Steel | 5665 | 5620 | 68 |  | 5644 | 5620 | 116 | 5685 | 13 | 5800 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
598 | 12573302052217 | Muncie | Muncie | Bare Steel | 10800 | 11768 | 198 |  | 10778 | 11331 | 178 | 9114 | 35 | 10475 | [14 empty] | posted to CPR | Excluded from CSIA
599 | 14573302052224 | Muncie | Muncie | Bare Steel / Plastic | 5414 | 6501 | 95 |  | 4979 | 6480 | 82 | 4247 | 15 | 3913 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
600 | 12573302052213 | Muncie | Muncie | Bare Steel | 7451 | 7585 | 89 |  | 6591 | 7932 | 71 | 3398 | 12 | 4070 | [14 empty] | posted to CPR | Excluded from CSIA
601 | 11582102052212 | Anderson | Anderson | Bare Steel | 1910 | 2545 | 18 |  | 2316 | 2481 | 2269 | 22 | 3 | 1151 | [14 empty] | posted to CPR | Excluded from CSIA
602 | 11583202052215 | New Albany | New Albany | Cast Iron | 6840 | 7225 | 72 |  | 6950 | 6065 | 63 | 2041 | 7 | 3713 | [14 empty] | posted to CPR | Excluded from CSIA
603 | 11592002052217 | New Albany | New Albany | Cast Iron | 7579 | 5840 | 71 |  | 7325 | 6542 | 84 | 3207 | 3 | 4983 | [14 empty] | posted to CPR | Excluded from CSIA
604 | 13592002052210 | Clarksville | New Albany | Bare Steel / Cast Iron | 6625 | 4740 | 62 |  | 7215 | 4740 | 42 | 1754 | 5 | 2761 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
605 | 12592002052214 | Clarksville | New Albany | Bare Steel / Cast Iron | 6386 | 14801 | 61 |  | 6326 | 14242 | 56 | 1981 | 0 | 2102 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
606 | 12592002052210 | Clarksville | New Albany | Bare Steel / Cast Iron | 8845 | 2675 | 112 |  | 9782 | 2805 | 115 | 5501 | 2 | 6490 | [14 empty] | posted to CPR | Excluded from CSIA
607 | 12592002052215 | Clarksville | Clarksville | Bare Steel / Cast Iron | 3280 | 2000 | 41 |  | 3779 | 3030 | 45 | 1554 | 4 | 1608 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
608 | 14592002052212 | Clarksville | Clarksville | Bare Steel / Cast Iron | 8894 | 6430 | 96 |  | 9015 | 6430 | 82 | 2978 | 5300 | 8 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
609 | 14592002052213 | Clarksville | Clarksville | Bare Steel / Cast Iron | 6990 | 3336 | 95 |  | 7184 | 3322 | 89 | 3167 | 5 | 6321 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
610 | 12582102052214 | Anderson | Anderson | Bare Steel / Cast Iron / Plastic | 8740 | 13085 | 198 |  | 8492 | 13085 | 166 | 9008 | 48 | 10140 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
611 | 13573302052212 | Muncie | Muncie | Bare Steel | 2920 | 5105 | 43 |  | 2076 | 5020 | 31 | 1474 | 11 | 1591 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
614 | 12583402052214 | Anderson | Tipton | Bare Steel | 4843 | 5229 | 77 |  | 4522 | 5229 | 61 | 4739 | 2 | 4268 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
616 | 15592602052212 | Columbus | Columbus | Plastic | 3695 | 5882 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
617 | 11592502052210 | Bedford | Bedford | Cast Iron | 7934 | 8124 | 159 |  | 7890 | 8272 | 159 | 13661 | 6 | 13703 | [14 empty] | posted to CPR | Excluded from CSIA
618 | 17595502052210 | Lafayette | Lafayette | Bare Steel / Cast Iron | 6835 | 5265 | 111 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
629 | 12595002052213 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 5870 | 4340 | 95 |  | 6088 | 4355 | 87 | 7530 | 2 | 6677 | [14 empty] | posted to CPR | Excluded from CSIA
630 | 12595502052213 | Lafayette | Lafayette | Bare Steel / Cast Iron | 8650 | 8978 | 131 |  | 8788 | 6995 | 129 | 7021 | 0 | 9027 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
631 | 12595502052215 | Lafayette | Lafayette | Bare Steel / Cast Iron | 10040 | 6895 | 161 |  | 10108 | 6895 | 157 | 8752 | 1 | 7979 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
632 | 12592702052212 | Greensburg | Greensburg | Bare Steel | 8505 | 7605 | 115 |  | 8152 | 7698 | 114 | 9047 | 0 | 8804 | [14 empty] | posted to CPR | Excluded from CSIA
633 | 14592402052217 | Bedford | Bedford | Bare Steel / Cast Iron / Plastic | 6005 | 6265 | 113 |  | 8190 | 6265 | 74 | 7117 | 1 | 5335 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
637 | 12592502052214 | Bedford | Bedford | Bare Steel / Cast Iron | 4270 | 5520 | 116 |  | 5804 | 5562 | 115 | 5853 | 2 | 4761 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
638 | 14592402052218 | Bedford | Bedford | Bare Steel / Cast Iron / Plastic | 5475 | 5960 | 68 |  | 5427 | 5938 | 51 | 2846 | 1 | 2557 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
639 | 12592502052213 | Bedford | Bedford | Bare Steel / Cast Iron | 5055 | 5810 | 90 |  | 5697 | 5790 | 82 | 4452 | 1 | 4290 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
640 | 14592402052214 | Bloomington | Bedford | Bare Steel / Cast Iron / Plastic | 5290 | 8540 | 87 |  | 4936 | 7108 | 79 | 4884 | 0 | 5689 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
641 | 12592502052210 | Bedford | Bedford | Bare Steel / Cast Iron | 4894 | 8188 | 76 |  | 5405 | 8320 | 72 | 5223 | 0 | 4279 | [14 empty] | posted to CPR | Excluded from CSIA
642 | 14592402052215 | Bloomington | Bedford | Bare Steel / Cast Iron / Plastic | 5030 | 5095 | 47 |  | 6282 | 5073 | 40 | 2974 | 0 | 2859 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
643 | 15592402052214 | Bloomington | Bedford | Bare Steel / Cast Iron / Plastic | 2365 | 4450 | 16 |  | 2075 | 3705 | 13 | 818 | 4 | 634 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
644 | 15592602052213 | Columbus | Columbus | Plastic | 4385 | 5210 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
645 | 12592602052214 | Columbus | Columbus | Bare Steel / Cast Iron | 7001 | 6352 | 107 |  | 7102 | 6336 | 109 | 7626 | 0 | 8580 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
646 | 15592602052214 | Columbus | Columbus | Bare Steel / Cast Iron / Plastic | 8260 | 5925 | 90 |  | 8157 | 5925 | 89 | 5577 | 1 | 5992 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
647 | 13592602052212 | Columbus | Columbus | Bare Steel / Cast Iron | 6808 | 6303 | 143 |  | 11611 | 6292 | 131 | 5254 | 3 | 6147 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
648 | 12592602052213 | Columbus | Columbus | Bare Steel / Cast Iron | 5635 | 6531 | 150 |  | 5865 | 6531 | 151 | 8031 | 1 | 7410 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
649 | 17592602052210 | Columbus | Columbus | Bare Steel / Cast Iron / Plastic | 8390 | 7520 | 100 |  | 9076 | 7520 | 102 | 4073 | 0 | 5805 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
650 | 15592602052215 | Columbus | Columbus | Bare Steel / Cast Iron / Plastic | 2105 | 2670 | 53 |  | 3602 | 2699 | 53 | 2072 | 5 | 2996 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
651 | 17592602052220 | Columbus | Columbus | Bare Steel / Cast Iron / Plastic | 4760 | 5395 | 61 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
652 | 12592602052212 | Columbus | Columbus | Bare Steel / Cast Iron | 3186 | 3736 | 101 |  | 3206 | 3736 | 97 | 5867 | 4 | 5966 | [14 empty] | posted to CPR | Excluded from CSIA
653 | 12592602052210 | Columbus | Columbus | Bare Steel / Cast Iron | 3299 | 3190 | 100 |  | 4592 | 3751 | 98 | 4625 | 4 | 2952 | [14 empty] | posted to CPR | Excluded from CSIA
657 | 14595502052216 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 4955 | 3905 | 60 |  | 4842 | 2965 | 62 | 3604 | 0 | 4123 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
658 | 14595502052217 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 4940 | 4860 | 95 |  | 5642 | 4020 | 93 | 6056 | 0 | 6348 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
659 | 14595502052224 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 9085 | 5750 | 88 |  | 9085 | 5750 | 101 | 4179 | 0 | 6143 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
660 | 12595702052212 | Frankfort | Frankfort | Bare Steel / Cast Iron | 8025 | 4885 | 85 |  | 8275 | 5117 | 91 | 3686 | 0 | 5652 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
661 | 17595002052214 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 2540 | 6665 | 26 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
662 | 13595002052219 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 3565 | 7010 | 142 |  | 3676 | 7294 | 125 | 11850 | 13 | 9218 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
663 | 15595002052214 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 4145 | 5245 | 90 |  | 4355 | 5245 | 84 | 4527 | 7 | 5133 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
664 | 15592402052215 | Bloomington | Martinsville | Bare Steel / Plastic | 3405 | 4800 | 55 |  | 3522 | 4346 | 50 | 3167 | 3 | 2866 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
665 | 18595002052214 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 8930 | 5752 | 97 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
666 | 19595002052218 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 4920 | 2659 | 2166 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
667 | 18595002052215 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 10485 | 6055 | 163 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
668 | 18595002052216 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 9095 | 1983 | 96 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
669 | 18595002052217 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 7495 | 5968 | 108 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
670 | 19595002052219 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 6620 | 11035 | 2730 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
671 | 19595002052220 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 4740 | 5917 | 4085 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
672 | 14595502052218 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 7345 | 5240 | 96 |  | 6247 | 5240 | 89 | 4277 | 0 | 5111 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
673 | 15595502052215 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 3505 | 4455 | 53 |  | 3509 | 4455 | 48 | 2419 | 1 | 3160 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
674 | 14595502052219 | Lafayette | Lafayette | Bare Steel / Cast Iron | 8535 | 4235 | 124 |  | 8585 | 4235 | 124 | 5636 | 1 | 7132 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
675 | 12595502052216 | Lafayette | Lafayette | Bare Steel / Cast Iron | 2157 | 2469 | 16 |  | 1835 | 2469 | 7 | 490 | 1 | 528 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
676 | 14595502052220 | Lafayette | West Lafayette | Bare Steel / Cast Iron / Plastic | 12635 | 9175 | 160 |  | 13196 | 9175 | 164 | 7246 | 0 | 10275 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
677 | 13595502052212 | Lafayette | West Lafayette | Bare Steel / Cast Iron / Plastic | 12130 | 9500 | 149 |  | 11662 | 9460 | 143 | 6682 | 1 | 9434 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
678 | 15595502052216 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 13090 | 8435 | 184 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
679 | 15595502052217 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 8880 | 5645 | 119 |  | 9190 | 5645 | 118 | 5006 | 0 | 7221 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
680 | 13595502052213 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 8545 | 5615 | 130 |  | 8745 | 6315 | 130 | 6285 | 0 | 6084 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
682 | 14595502052221 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 11620 | 9975 | 148 |  | 11813 | 9975 | 148 | 6526 | 1 | 7756 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
683 | 14595502052222 | Lafayette | Lafayette | Bare Steel / Cast Iron | 10155 | 5775 | 114 |  | 10122 | 5775 | 112 | 5302 | 0 | 7321 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
684 | 15595502052218 | Lafayette | Lafayette | Bare Steel / Cast Iron / Plastic | 6055 | 6600 | 60 |  | 5954 | 6600 | 60 | 4670 | 0 | 3743 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
685 | 14595502052223 | Lafayette | Lafayette | Bare Steel / Cast Iron | 9340 | 4015 | 118 |  | 9438 | 4535 | 117 | 4622 | 1 | 6768 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
710 | 17595002052219 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 2520 | 1091 | 72 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
711 | 19595002052221 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 3660 | 5417 | 3541 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
712 | 17595002052220 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 4800 | 2783 | 65 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
713 | 17595002052221 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 9260 | 6443 | 133 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
715 | 12595002052214 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 4535 | 4360 | 145 |  | 5266 | 4360 | 98 | 7635 | 17 | 7654 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
716 | 20595002052210 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 2595 | 5975 | 1717 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
717 | 19595002052222 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 8295 | 5328 | 4731 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
718 | 17595002052222 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 5380 | 6445 | 142 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
722 | 15592402052216 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 5180 | 5350 | 67 |  | 5218 | 5350 | 73 | 5922 | 0 | 3066 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
723 | 15592402052217 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 3140 | 4475 | 45 |  | 2600 | 4475 | 35 | 2120 | 0 | 1644 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
724 | 15592402052218 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 2845 | 4735 | 37 |  | 1886 | 4570 | 26 | 1850 | 0 | 1446 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
725 | 13592402052210 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 4170 | 3465 | 66 |  | 4075 | 3470 | 79 | 6236 | 0 | 1265 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
812 | 12582102052217 | Anderson | Anderson | Bare Steel | 2440 | 125 | 56 |  | 2891 | 0 | 59 | 2967 | 13 | 3794 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
818 [J] | 11592002051213 | Jeffersonville | Jeffersonville | Bare Steel / Cast Iron | 2469 | 1421 | 49 |  | 2474 | 1421 | 49 | 625 | 0 | 585 | [14 empty] | #N/A | Excluded from CSIA
842 | 17592402052220 | Bloomington | Martinsville | Bare Steel / Cast Iron / Plastic | 11545 | 10422 | 146 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
847 | 12592402052210 | Bloomington | Bloomington | Cast Iron | 1400 | 1200 | 11 |  | 1290 | 1200 | 12 | 951 | 0 | 637 | [14 empty] | posted to CPR | Excluded from CSIA
853 | 15582102052215 | Anderson | Anderson | Bare Steel / Plastic | 4900 | 5255 | 55 |  | 4867 | 5100 | 54 | 2863 | 14 | 2848 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
859 | 12592702052210 | Greensburg | Greensburg | Bare Steel | 3845 | 3773 | 72 |  | 3149 | 3979 | 63 | 3081 | 0 | 3263 | [14 empty] | posted to CPR | Excluded from CSIA
860 [G] | 12582102052212 | Anderson | Anderson | Bare Steel | 0 | 1200 | 18 |  | 0 | 1123 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | Excluded from CSIA
861 | 12583302052213 | Greenfield | Fortville | Bare Steel | 4815 | 5090 | 79 |  | 4377 | 5163 | 62 | 3118 | 0 | 4810 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
864 | 15582102052217 | Anderson | Alexandria | Bare Steel / Plastic | 5410 | 5375 | 67 |  | 5775 | 5375 | 64 | 4571 | 2 | 3651 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
865 | 12595902052212 | Rockville | Rockville | Bare Steel | 3617 | 3578 | 67 |  | 3481 | 3578 | 56 | 3923 | 1 | 4031 | [14 empty] | posted to CPR | Excluded from CSIA
866 | 19582102052224 | Anderson | Alexandria | Bare Steel / Plastic | 2975 | 4813 | 2150 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
867 | 18582102052210 | Anderson | Alexandria | Bare Steel / Plastic | 4060 | 8845 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
868 | 20582102052212 | Anderson | Alexandria | Bare Steel / Plastic | 5195 | 4783 | 4015 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
869 | 17582102052212 | Anderson | Alexandria | Bare Steel / Cast Iron / Plastic | 4645 | 8155 | 48 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
870 | 20582102052213 | Anderson | Alexandria | Bare Steel / Plastic | 3415 | 3639 | 1617 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
871 | 16582102052215 | Anderson | Alexandria | Bare Steel / Plastic | 5505 | 5960 | 59 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
872 | 15582102052218 | Anderson | Elwood | Bare Steel / Plastic | 3680 | 4525 | 42 |  | 3431 | 4525 | 39 | 2893 | 6 | 3278 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
873 | 12583402052216 | Elwood | Elwood | Bare Steel | 5140 | 5015 | 86 |  | 4857 | 5015 | 78 | 5637 | 5 | 4709 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
874 | 12583402052213 | Elwood | Elwood | Bare Steel | 5655 | 5500 | 100 |  | 4807 | 5090 | 83 | 4937 | 7 | 4839 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
875 | 14582102052217 | Elwood | Elwood | Bare Steel | 2905 | 4540 | 61 |  | 3021 | 4540 | 47 | 3297 | 9 | 3062 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
876 | 14582102052213 | Anderson | Elwood | Bare Steel | 4910 | 5915 | 49 |  | 4517 | 5205 | 45 | 3015 | 6 | 3815 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
877 | 15582102052219 | Anderson | Elwood | Bare Steel / Plastic | 2970 | 6280 | 15 |  | 2877 | 6280 | 16 | 768 | 1 | 736 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
878 | 12592302052210 | Madison | Madison | Bare Steel | 7007 | 6635 | 107 |  | 7296 | 6530 | 77 | 6294 | 25 | 5681 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
880 | 17575102052214 | Richmond | Richmond | Plastic | 2370 | 2537 | 54 |  | 2395 | 2535 | 10 | 2745 | 0 | 2397 | [14 empty] | completed | CSIA - COMPLIANCE
884 | 14573302052214 | Muncie | Richmond | Bare Steel / Cast Iron / Plastic | 7130 | 9075 | 146 |  | 7243 | 9295 | 135 | 6298 | 6 | 5821 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
887 | 14573302052215 | Muncie | Richmond | Bare Steel / Cast Iron / Plastic | 8660 | 7555 | 163 |  | 8364 | 7497 | 130 | 4479 | 16 | 6479 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
888 | 15575102052212 | Richmond | Richmond | Bare Steel / Cast Iron / Plastic | 7365 | 7560 | 145 |  | 7358 | 8243 | 143 | 9370 | 5 | 9716 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
892 | 17575102052215 | Richmond | Richmond | Plastic | 8395 | 6244 | 104 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
897 | 18575102052218 | Richmond | Richmond | Bare Steel / Plastic | 6885 | 5600 | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
898 | 18575102052214 | Richmond | Richmond | Bare Steel / Plastic | 7060 | 5534 | 87 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
903 | 16575102052210 | Richmond | Richmond | Bare Steel / Plastic | 4845 | 3380 | 34 |  | 5101 | 2150 | 5 | 1063 | 0 | 1293 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
912 | 12595002052217 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 4485 | 3550 | 78 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
926 | 13573302052213 | Muncie | Muncie | Bare Steel / Plastic | 2830 | 7395 | 39 |  | 3141 | 7395 | 41 | 2423 | 5 | 2129 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
945 | 13592402052212 | Bloomington | Bloomington | Bare Steel / Cast Iron / Plastic | 7950 | 9810 | 105 |  | 8462 | 9843 | 115 | 8646 | 6719 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
947 | 12583302052212 | Greenfield | Greenfield | Bare Steel | 6920 | 11300 | 123 |  | 7764 | 11794 | 113 | 7454 | 3 | 6867 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
954 | 13592002052214 | Clarksville | Jeffersonville | Bare Steel / Cast Iron / Plastic | 6835 | 4326 | 95 |  | 7467 | 0 | 87 | 4218 | 1 | 5471 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
955 | 12592002052213 | Clarksville | Jeffersonville | Bare Steel / Cast Iron | 3910 | 4501 | 83 |  | 4076 | 1290 | 64 | 4729 | 4 | 2063 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
991 | 14582102052214 | Anderson | Anderson | Bare Steel / Plastic | 3320 | 3978 | 42 |  | 3341 | 3975 | 40 | 2368 | 12 | 3006 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
993 | 18582102052224 | Anderson | Anderson | Bare Steel / Plastic | 2595 | 4791 | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
992 | 17582102052215 | Anderson | Anderson | Bare Steel | 3950 | 3628 | 31 |  | 3741 | 5450 | 28 | 1548 | 9 | 2737 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
994 | 18582102052225 | Anderson | Anderson | Bare Steel / Cast Iron / Plastic | 4725 | 6973 | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
995 | 16582102052220 | Anderson | Anderson | Bare Steel / Plastic | 1950 | 7820 | 17 |  | 1708 | 7820 | 12 | 807 | 7 | 1123 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1000 | 12575102052210 | Richmond | Richmond | Bare Steel / Cast Iron | 8395 | 9395 | 108 |  | 9577 | 9919 | 137 | 6361 | 20 | 7017 | [14 empty] | posted to CPR | Excluded from CSIA
1107 | 18575102052216 | Richmond | Richmond | Bare Steel / Plastic | 5390 | 4683 | 25 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1022 | 12583402052215 | Anderson | Tipton | Bare Steel | 6575 | 8210 | 109 |  | 6830 | 9120 | 90 | 6662 | 4 | 5677 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1035 | 12583302052214 | Greenfield | Greenfield | Bare Steel | 5525 | 5180 | 66 |  | 4928 | 5402 | 66 | 5572 | 4 | 4259 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1037 | 12592802052210 | Seymour | Seymour | Bare Steel / Plastic | 7795 | 13 | 74 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1038 | 12595402052210 | Lebanon | Zionsville | Bare Steel | 7510 | 8980 | 120 |  | 8117 | 9825 | 130 | 8372 | 1 | 7159 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1040 | 12595402052212 | Lebanon | Zionsville | Bare Steel | 6705 | 9265 | 148 |  | 8626 | 10785 | 139 | 7202 | 2 | 6699 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1041 | 14595302052210 | Danville | Lebanon | Bare Steel / Plastic | 4045 | 4505 | 62 |  | 4421 | 4505 | 62 | 4354 | 1 | 4680 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1042 | 14595302052212 | Danville | Lebanon | Bare Steel / Plastic | 8990 | 8390 | 123 |  | 8429 | 8390 | 123 | 8525 | 0 | 8089 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1043 | 14595302052214 | Lebanon | Lebanon | Bare Steel / Plastic | 3440 | 3280 | 18 |  | 3154 | 3280 | 17 | 938 | 0 | 945 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1050 | 12592002052216 | Clarksville | New Albany | Bare Steel | 2622 | 2510 | 27 |  | 2703 | 2510 | 23 | 958 | 4 | 1186 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1057 | 20583002052210 | Noblesville | Noblesville | Bare Steel / Plastic | 4790 | 6691 | 1877 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1058 | 13575102052210 | Muncie | Richmond | Bare Steel | 4740 | 3795 | 114 |  | 4905 | 4151 | 118 | 7548 | 3 | 6890 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1080 | 14582102052215 | Anderson | Tipton | Bare Steel / Plastic | 6620 | 8090 | 106 |  | 6948 | 8090 | 102 | 6015 | 13 | 5817 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1081 | 14583402052210 | Elwood | Tipton | Bare Steel / Cast Iron / Plastic | 6875 | 6565 | 106 |  | 7044 | 7035 | 106 | 6722 | 0 | 5724 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1082 | 17582102052216 | Anderson | Tipton | Plastic | 6755 | 6867 | 69 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
1083 | 17582102052214 | Anderson | Tipton | Bare Steel / Cast Iron / Plastic | 5580 | 6110 | 77 |  | 5450 | 6110 | 75 | 4803 | 3 | 7275 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1084 | 17582102052217 | Anderson | Tipton | Plastic | 4945 | 6718 | 62 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1085 | 17573302052212 | Muncie | Hagerstown | Bare Steel | 6075 | 7570 | 90 |  | 6049 | 7570 | 84 | 4672 | 2 | 5134 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1086 | 17573302052214 | Muncie | Hagerstown | Plastic | 4215 | 7026 | 50 |  | 4221 | 7025 | 0 | 3678 | 0 | 2961 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1087 | 14574102052223 | Marion | Huntington | Bare Steel / Plastic | 4010 | 4240 | 66 |  | 4010 | 4240 | 62 | 3927 | 1 | 3664 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1088 | 17574102052210 | Marian | Huntington | Plastic | 5685 | 6752 | 68 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1089 | 15574102052210 | Marion | Huntington | Bare Steel / Plastic | 5500 | 5615 | 88 |  | 5953 | 5615 | 101 | 3685 | 17 | 3337 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1090 | 14595502052212 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 4270 | 6145 | 82 |  | 4364 | 6145 | 83 | 4299 | 1 | 4026 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1091 | 16595702052210 | Frankfort | Frankfort | Bare Steel / Cast Iron / Plastic | 4625 | 4735 | 75 |  | 4587 | 4735 | 77 | 4517 | 1 | 5634 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1092 | 15595502052210 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 4535 | 2770 | 46 |  | 4483 | 2770 | 43 | 1851 | 2 | 2479 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1093 | 14595502052213 | Lafayette | Frankfort | Bare Steel / Plastic | 10090 | 9080 | 91 |  | 9350 | 9080 | 87 | 3940 | 1 | 3843 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1094 | 15595502052212 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 11445 | 10975 | 166 |  | 11590 | 11134 | 168 | 9070 | 1 | 9556 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1095 | 14595502052225 | Frankfort | Frankfort | Bare Steel / Cast Iron / Plastic | 4945 | 5855 | 135 |  | 4886 | 7105 | 130 | 9891 | 2 | 10021 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1096 | 15595502052213 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 13715 | 8970 | 173 |  | 13254 | 8970 | 173 | 7900 | 0 | 11170 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1097 | 15595502052214 | Lafayette | Frankfort | Plastic | 3795 | 5941 | 59 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1098 | 18582102052214 | Anderson | Anderson | Bare Steel / Plastic | 4465 | 6490 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1099 | 18582102052215 | Anderson | Anderson | Bare Steel / Plastic | 5460 | 6687 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1100 | 18575102052215 | Richmond | Richmond | Bare Steel / Plastic | 2095 | 2691 | 2262 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1101 | 18582102052222 | Anderson | Anderson | Bare Steel / Plastic | 2490 | 3648 | 27 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1102 | 15582102052210 | Anderson | Anderson | Bare Steel / Plastic | 6495 | 8555 | 85 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1104 | 18575102052210 | Richmond | Richmond | Bare Steel / Cast Iron / Plastic | 2100 | 3851 | 1093 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1106 | 16575102052212 | Richmond | Richmond | Bare Steel / Plastic | 4165 | 4270 | 50 |  | 4303 | 4097 | 53 | 1851 | 13 | 1882 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1112 | 13575102052214 | Muncie | Richmond | Bare Steel / Cast Iron / Plastic | 26110 | 31585 | 0 |  | 31962 | 31715 | 444 | 35782 | 78 | 26913 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1114 | 17575102052210 | Richmond | Richmond | Bare Steel / Plastic | 7200 | 4480 | 123 |  | 6935 | 4470 | 87 | 1841 | 22 | 1140 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1115 | 17575102052212 | Richmond | Richmond | Plastic | 7170 | 11161 | 134 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1116 | 13595502052214 | Layfayette | Lafayette | Bare Steel | 3100 | 3235 | 9 |  | 3220 | 3235 | 9 | 813 | 0 | 1087 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1125 | 14595302052215 | Lebanon | Zionsville | Bare Steel / Plastic | 5770 | 3765 | 81 |  | 6460 | 4042 | 87 | 3702 | 0 | 3582 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1148 | 15573302052210 | Muncie | Muncie | Bare Steel / Plastic | 5275 | 9625 | 47 |  | 5382 | 9625 | 46 | 1811 | 8 | 1769 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1154 | 18583502052212 | Franklin | Martinsville | Bare Steel / Plastic | 4740 | 2361 | 47 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1156 | 17592402052213 | Bloomington | Martinsville | Bare Steel | 2820 | 3661 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1157 | 14592402052210 | Bloomington | Martinsville | Bare Steel | 7270 | 7655 | 0 |  | 7347 | 7415 | 102 | 6798 | 2 | 7380 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1158 | 17592402052214 | Bloomington | Martinsville | Bare Steel / Plastic | 6400 | 6555 | 82 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1159 | 15592402052210 | Bloomington | Martinsville | Bare Steel / Plastic | 5820 | 6110 | 76 |  | 6308 | 6495 | 77 | 4774 | 10 | 5232 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1160 | 14583302052213 | Greenfield | Greenfield | Bare Steel / Plastic | 8725 | 10085 | 0 |  | 9415 | 9892 | 181 | 9770 | 7 | 9797 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1161 | 14583302052210 | Greenfield | Greenfield | Bare Steel | 5065 | 5680 | 74 |  | 5037 | 6628 | 64 | 2958 | 5 | 3221 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1162 | 13592602052210 | Columbus | Columbus | Bare Steel / Cast Iron / Plastic | 4700 | 7157 | 101 |  | 5532 | 7157 | 105 | 9250 | 0 | 6975 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1163 | 16592602052210 | Columbus | Columbus | Bare Steel / Plastic | 3030 | 2990 | 44 |  | 3624 | 3447 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1164 | 17583302052221 | Greenfield | Knightstown | Bare Steel | 1890 | 1900 | 34 |  | 1903 | 1900 | 34 | 2207 | 0 | 2127 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1165 | 17583302052214 | Greenfield | Knightstown | Plastic | 6475 | 6776 | 106 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1167 | 14583302052221 | Greenfield | Knightstown | Bare Steel / Plastic | 5785 | 6075 | 85 |  | 6401 | 6817 | 88 | 4744 | 2 | 4733 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1168 | 14583302052212 | Greenfield | Knightstown | Bare Steel / Plastic | 5095 | 6075 | 165 |  | 4783 | 5585 | 80 | 4668 | 0 | 4835 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1169 | 15583302052213 | Greenfield | Knightstown | Bare Steel / Plastic | 2390 | 5185 | 47 |  | 2221 | 5970 | 47 | 2385 | 0 | 2631 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1170 | 17583302052215 | Greenfield | Knightstown | Plastic | 5165 | 6770 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1172 | 15583302052216 | Greenfield | Cambridge City | Bare Steel | 6300 | 6800 | 66 |  | 6723 | 6144 | 68 | 3844 | 2 | 3836 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1337 | 13582102052212 | Anderson | Anderson | Bare Steel / Cast Iron | 470 | 1695 | 6 |  | 598 | 1695 | 4 | 202 | 0 | 145 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1392 | 16573302052213 | Muncie | New Albany | Bare Steel / Plastic | 7110 | 7510 | 73 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1395 | 19592602052210 | Columbus | Columbus | Bare Steel / Plastic | 6575 | 7671 | 6165 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1402 | 18573302052210 | Muncie | Muncie | Bare Steel / Plastic | 7910 | 7791 | 115 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
1403 | 17573302052215 | Muncie | Muncie | Plastic | 7560 | 7941 | 119 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
1404 | 14573302052210 | Muncie | Muncie | Bare Steel / Plastic | 6655 | 8025 | 108 |  | 6945 | 8001 | 110 | 7994 | 15 | 5747 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1405 | 18573302052212 | Muncie | Muncie | Bare Steel / Plastic | 8560 | 12018 | 51 |  | 8881 | 13005 | 0 | 70 | 84 | 5394 | [14 empty] | completed | CSIA - COMPLIANCE
1422 | 18573302052227 | Muncie | Yorktown | Bare Steel / Plastic | 5965 | 6574 | 4238 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1426 | 14574102052213 | Marion | Marion | Bare Steel / Plastic | 3170 | 3525 | 32 |  | 2831 | 3560 | 31 | 1788 | 4 | 1975 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1430 | 18574102052212 | Marion | Gas City | Bare Steel / Plastic | 6400 | 5958 | 90 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1431 | 18574102052213 | Marion | Marion | Bare Steel / Plastic | 5515 | 5376 | 48 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1442 | 20573302052210 | Muncie | Yorktown | Bare Steel / Plastic | 3770 | 4786 | 3112 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1443 | 20573302052212 | Muncie | Yorktown | Bare Steel / Plastic | 7570 | 8682 | 5197 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1448 | 18575102052217 | Richmond | Richmond | Bare Steel / Plastic | 5395 | 10095 | 117 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1450 | 17573302052224 | Muncie | Muncie | Plastic | 3330 | 3238 | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1454 | 18573302052213 | Muncie | Muncie | Bare Steel / Plastic | 7180 | 7077 | 73 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1458 | 17573302052216 | Muncie | Parker City | Plastic | 2310 | 2484 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1467 | 18573302052214 | Muncie | Muncie | Bare Steel / Plastic | 6070 | 6014 | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1471 | 16573302052210 | Muncie | Muncie | Bare Steel / Plastic | 3915 | 3945 | 35 |  | 3850 | 3945 | 28 | 2086 | 34-28 | 2678 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1472 | 19573302052212 | Muncie | Muncie | Bare Steel / Plastic | 5460 | 5493 | 4964 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1485 | 17573302052223 | Muncie | Parker City | Plastic | 5025 | 5292 | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
1501 | 13582102052213 | Anderson | Anderson | Bare Steel | 62 | 160 | 2 |  | 62 | 160 | 2 | 188 | 1 | 67 | [14 empty] | posted to CPR | Excluded from CSIA
1509 | 13575102052212 | Muncie | Richmond | Bare Steel / Plastic | 2375 | 2025 | 62 |  | 2929 | 2430 | 71 | 4703 | 10 | 5600 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1512 | 15592402052212 | Bloomington | Bedford | Bare Steel / Plastic | 8615 | 7245 | 56 |  | 7558 | 6510 | 42 | 2890 | 0 | 2802 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1513 | 13574102052217 | Marion | Marion | Bare Steel / Plastic | 1180 | 1190 | 2 |  | 1244 | 1290 | 2 | 12 | 2 | 6 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1518 | 13574102052213 | Marion | Marion | Bare Steel | 30 | 15 | 0 |  | 29 | 29 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | Excluded from CSIA
1519 | 14595002052213 | Greencastle | Greencastle | Bare Steel / Plastic | 1315 | 1445 | 20 |  | 1348 | 1445 | 16 | 888 | 0 | 885 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1522 | 17592402052210 | Bloomington | Bedford | Bare Steel / Plastic | 4450 | 4325 | 51 |  | 4173 | 4360 | 0 | 2638 | 0 | 3013 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1523 | 18592402052212 | Bloomington | Mitchell | Bare Steel / Plastic | 4140 | 4150 | 19 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1150 | 15583302052212 | Greenfield | Rushville | Bare Steel / Plastic | 4215 | 4840 | 97 |  | 4793 | 4467 | 95 | 4292 | 3 | 5328 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1532 | 17595302052213 | Danville | Danville | Bare Steel / Plastic | 4880 | 5034 | 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
1151 | 18583502052210 | Franklin | Martinsville | Bare Steel / Plastic | 3685 | 2460 | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1552 | 18595302052210 | Danville | Lebanon | Bare Steel / Plastic | 820 | 747 | 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
1553 | 14595502052214 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 2905 | 2980 | 35 |  | 2584 | 2980 | 39 | 2566 | 1 | 2655 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1555 | 18595502052210 | Lafayette | Frankfort | Bare Steel / Plastic | 9676 | 8464 | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1557 | 14582102052210 | Anderson | Anderson | Bare Steel | 4380 | 9425 | 86 |  | 4113 | 9260 | 90 | 5155 | 9 | 4070 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1558 | 18573302052215 | Muncie | New Albany | Bare Steel / Plastic | 4945 | 6283 | 56 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
1564 | 14575302052210 | Greenfield | Knightstown | Bare Steel | 2800 | 2800 | 30 |  | 2890 | 2571 | 37 | 2493 | 1 | 2562 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1566 | 16573302052217 | Muncie | New Albany | Bare Steel | 6035 | 5005 | 98 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1576 | 19573302052214 | Muncie | Dunkirk | Bare Steel / Cast Iron / Plastic | 5755 | 8919 | 3676 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1581 | 17592602052215 | Columbus | Columbus | Bare Steel / Plastic | 7230 | 5290 | 104 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1585 | 19592602052212 | Columbus | Columbus | Bare Steel / Plastic | 7245 | 3697 | 3500 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1594 | 20592602052210 | Columbus | Columbus | Bare Steel / Plastic | 6435 | 6316 | 49 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1600 | 17592602052213 | Columbus | Columbus | Bare Steel / Plastic | 6545 | 4980 | 94 |  | 7719 | 5865 | 134 | 5512 | 0 | 6365 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1602 | 15592602052210 | Columbus | Columbus | Bare Steel / Plastic | 9435 | 6335 | 133 |  | 9258 | 6131 | 129 | 4597 | 5 | 6886 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1612 | 17592602052216 | Columbus | Columbus | Bare Steel / Plastic | 6750 | 5186 | 3470 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
1618 | 19592602052213 | Columbus | Columbus | Bare Steel / Plastic | 7240 | 4671 | 3670 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1619 | 19592602052214 | Columbus | Columbus | Bare Steel / Plastic | 2325 | 2388 | 3020 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1624 | 19592602052215 | Columbus | Taylorsville | Bare Steel / Plastic | 890 | 782 | 610 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1638 | 17592602052212 | Columbus | Columbus | Bare Steel / Plastic | 5300 | 3700 | 63 |  | 5380 | 3700 | 7 | 3163 | 0 | 3699 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1639 | 19592602052216 | Columbus | Columbus | Bare Steel / Plastic | 7595 | 5511 | 4595 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1646 | 19582102052213 | Anderson | Pendleton | Bare Steel / Plastic | 2855 | 6618 | 1155 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1647 | 19582102052214 | Anderson | Pendleton | Bare Steel / Plastic | 3435 | 3454 | 861 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1654 | 16582102052212 | Anderson | Anderson | Bare Steel / Plastic | 8050 | 7335 | 98 |  | 8175 | 7335 | 99 | 6640 | 9 | 5959 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1657 | 19582102052215 | Anderson | Anderson | Bare Steel / Plastic | 4880 | 7585 | 5250 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1663 | 14595802052210 | Danville | Crawfordsville | Bare Steel | 1030 | 945 | 20 |  | 1000 | 1045 | 19 | 565 | 1 | 1183 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1670 | 19582102052216 | Anderson | Frankfort | Bare Steel / Plastic | 10310 | 11935 | 5318 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1173 | 16583302052210 | Greenfield | Cambridge City | Bare Steel | 1650 | 1865 | 35 |  | 1650 | 1865 | 37 | 1971 | 2 | 2180 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1713 | 17592402052215 | Bloomington | Bloomington | Bare Steel / Plastic | 4895 | 5261 | 37 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1718 | 19582102052217 | Anderson | Anderson | Bare Steel / Plastic | 6435 | 6656 | 3496 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1728 | 18574102052214 | Marion | Marion | Bare Steel / Plastic | 4475 | 6947 | 3596 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1730 | 18574102052215 | Marion | Marion | Bare Steel / Plastic | 2960 | 2657 | 11 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
1774 | 19582102052219 | Anderson | Chesterfield | Bare Steel / Plastic | 7340 | 7313 | 7246 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1775 | 15582102052216 | Anderson | Elwood | Bare Steel / Plastic | 2200 | 2550 | 16 |  | 1902 | 2195 | 17 | 1284 | 1 | 1287 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1777 | 19582102052220 | Anderson | Alexandria | Bare Steel / Plastic | 2680 | 2356 | 2570 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1768 | 17582102052219 | Anderson | Anderson | Plastic | 7115 | 5230 | 108 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1769 | 18582102052213 | Anderson | Anderson | Bare Steel / Plastic | 1530 | 3523 | 27 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1771 | 19582102052218 | Anderson | Anderson | Bare Steel / Plastic | 3725 | 4267 | 2030 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1780 | 19574102052212 | Marion | Jonesboro | Bare Steel / Plastic | 9325 | 9598 | 4762 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1781 | 18574102052216 | Marion | Gas City | Bare Steel / Plastic | 5515 | 3972 | 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
1784 | 19575102052210 | Richmond | Richmond | Bare Steel / Plastic | 2445 | 2951 | 3825 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
1785 | 15575102052210 | Richmond | Richmond | Bare Steel / Plastic | 7100 | 6740 | 84 |  | 7118 | 5936 | 83 | 3904 | 0 | 4459 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1788 | 18575102052212 | Richmond | Richmond | Bare Steel / Plastic | 7475 | 7236 | 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1802 | 16573302052214 | Muncie | Eaton | Bare Steel / Plastic | 4325 | 4560 | 55 |  | 4375 | 4320 | 56 | 3229 | 2 | 3424 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1805 | 18573302052221 | Muncie | Muncie | Bare Steel / Plastic | 5180 | 5060 | 71 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1806 | 19573302052215 | Muncie | Muncie | Bare Steel / Plastic | 3260 | 3965 | 2184 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1813 | 19573302052216 | Muncie | Muncie | Bare Steel / Plastic | 2210 | 1816 | 1570 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
1844 | 15595202052213 | Greencastle | Greencastle | Bare Steel / Plastic | 5135 | 4905 | 39 |  | 4883 | 4905 | 37 | 2092 | 2 | 2167 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1870 | 15583302052214 | Greenfield | Rushville | Bare Steel / Plastic | 8220 | 8210 | 4 |  | 8961 | 8995 | 3 | 374 | 0 | 178 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1882 | 14595302052217 | Danville | Danville | Bare Steel | 215 | 100 | 5 |  | 236 | 245 | 5 | 538 | 0 | 526 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1896 | 15595202052210 | Greencastle | Greencastle | Bare Steel / Plastic | 4755 | 3985 | 54 |  | 4371 | 3910 | 46 | 2952 | 0 | 2874 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1935 | 14592002052214 | Clarksville | Jeffersonville | Bare Steel / Cast Iron | 1185 | 2320 | 11 |  | 1026 | 2320 | 8 | 261 | 0 | 515 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1957 | 15582102052214 | Anderson | Anderson | Bare Steel / Plastic | 6247 | 13125 | 143 |  | 6647 | 13125 | 134 | 9614 | 20 | 8771 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1958 | 15582102052213 | Anderson | Elwood | Bare Steel / Plastic | 4510 | 5495 | 41 |  | 4481 | 5495 | 38 | 1700 | 7 | 2186 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1926 | 14592402052219 | Bloomington | Bloomington | Cast Iron | 200 | 150 | 3 |  | 134 | 139 | 3 | 194 | 0 | 240 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
1990 | 17595502052213 | Lafayette | Lafayette | Bare Steel / Plastic | 2650 | 2758 | 7 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2019 | 17575102052213 | Richmond | Richmond | Plastic | 5560 | 5594 | 83 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2024 | 19574102052210 | Marion | Hartford City | Bare Steel / Plastic | 13460 | 11301 | 115 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2050 | 16592002052210 | Clarksville | New Albany | Bare Steel / Plastic | 6275 | 6955 | 73 |  | 6269 | 6955 | 53 | 4678 | 2 | 3754 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2051 | 17592002052210 | Clarksville | Clarksville | Bare Steel / Plastic | 4600 | 4390 | 91 |  | 6690 | 4390 | 92 | 3609 | 0 | 3336 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2052 | 17592002052212 | Clarksville | Clarksville | Bare Steel | 6285 | 3504 | 96 |  | 6436 | 3158 | 93 | 2793 | 2 | 3111 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2053 | 18592002052212 | Clarksville | Clarksville | Bare Steel / Plastic | 8110 | 5272 | 87 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2054 | 16592002052212 | Clarksville | Clarksville | Bare Steel / Plastic | 5450 | 5665 | 92 |  | 5373 | 4465 | 76 | 5413 | 1 | 5314 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2055 | 16592002052213 | Clarksville | Jeffersonville | Bare Steel / Plastic | 5305 | 4769 | 102 |  | 5028 | 4765 | 102 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2067 | 15575102052214 | Richmond | Richmond | Bare Steel / Plastic | 7355 | 5495 | 74 |  | 7273 | 5915 | 72 | 4440 | 0 | 4446 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2068 | 15575102052215 | Richmond | Richmond | Bare Steel / Plastic | 4165 | 3640 | 53 |  | 4160 | 2942 | 56 | 3395 | 0 | 3461 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2069 | 15573302052214 | Muncie | Muncie | Bare Steel / Plastic | 4440 | 4905 | 54 |  | 4182 | 4905 | 52 | 3438 | 9 | 2516 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2071 | 15575302052212 | Rushville | Rushville | Bare Steel / Plastic | 4260 | 5370 | 96 |  | 3948 | 5255 | 92 | 6524 | 3 | 7353 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2072 | 15575302052210 | Rushville | Knightstown | Bare Steel / Plastic | 3125 | 4565 | 60 |  | 2881 | 4565 | 66 | 4702 | 2 | 5303 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2077 | 18595302052212 | Danville | Brownsburg | Bare Steel / Plastic | 9860 | 10880 | 96 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
2087 | 17583302052218 | Greenfield | Knightstown | Bare Steel | 6115 | 6175 | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2091 | 16583302052212 | Greenfield | Greenfield | Bare Steel / Plastic | 6775 | 7595 | 103 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2092 | 16583302052213 | Greenfield | Greenfield | Plastic | 6580 | 2343 | 44 |  | 5743 | 2240 | 1 | 4074 | 0 | 3583 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2093 | 16583302052214 | Greenfield | Greenfield | Plastic | 5515 | 6240 | 85 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2096 | 16595502052210 | Lafayette | Lafayette | Bare Steel / Cast Iron | 2385 | 1335 | 28 |  | 2463 | 1335 | 28 | 1107 | 0 | 1436 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2097 | 17595002052213 | Terre Haute | Greencastle | Bare Steel / Plastic | 5790 | 6745 | 34 |  | 5719 | 6745 | 29 | 2415 | 0 | 2677 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2108 | 16582102052210 | Anderson | Anderson | Bare Steel / Plastic | 200 | 200 | 0 |  | 358 | 358 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2117 | 16573302052216 | Muncie | Muncie | Bare Steel / Plastic | 3410 | 2629 | 18 |  | 3174 | 2806 | 17 | 1873 | 0 | 1005 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2119 | 17595302052217 | Danville | Crawfordsville | Bare Steel / Plastic | 4535 | 4340 | 41 |  | 4838 | 4354 | 43 | 4703 | 1 | 3643 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2126 | 16582102052216 | Anderson | Anderson | Bare Steel / Cast Iron / Plastic | 2760 | 2935 | 52 |  | 2693 | 2935 | 32 | 2123 | 6 | 2361 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2128 | 16583302052217 | Greenfield | Greenfield | Bare Steel | 6270 | 4185 | 111 |  | 9451 | 0 | 108 | 6169 | 0 | 6249 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2133 | 16583302052218 | Greenfield | Greenfield | Bare Steel / Plastic | 5260 | 5280 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2135 | 18592002052210 | Clarksville | Jeffersonville | Bare Steel / Plastic | 4245 | 4058 | 0 |  | 4274 | 4055 | 0 | 1917 | 0 | 795 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2138 | 16592402052212 | Bloomington | Martinsville | Bare Steel / Plastic | 3935 | 3735 | 45 |  | 2903 | 2345 | 45 | 3561 | 4 | 4628 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2139 | 17595502052214 | Lafayette | Frankfort | Bare Steel / Cast Iron / Plastic | 3465 | 2887 | 0 |  | 3500 | 3505 | 0 | 1678 | 0 | 2278 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2140 | 17592402052216 | Bloomington | Martinsville | Bare Steel / Plastic | 5330 | 5509 | 100 |  | 9573 | 5505 | 0 | 1 | 4385 | 6313 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2142 | 17573302052217 | Muncie | Muncie | Bare Steel / Plastic | 0 | 3807 | 0 |  | 1898 | 3842 | 0 | 1736 | 0 | 1617 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2143 | 18582102052223 | Anderson | Anderson | Bare Steel / Plastic | 8425 | 7637 | 76 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
2144 | 18595002052210 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 5210 | 3833 | 1772 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2147 | 17573302052218 | Muncie | Hagerstown | Plastic | 3655 | 3175 | 47 |  | 3582 | 3170 | 50 | 3464 | 0 | 2580 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2148 | 17573302052210 | Muncie | Hagerstown | Bare Steel / Plastic | 3050 | 3380 | 55 |  | 3164 | 3380 | 47 | 1961 | 0 | 1993 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2149 | 18595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 5910 | 4557 | 70 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
2150 | 18573302052223 | Muncie | Muncie | Bare Steel / Plastic | 4880 | 4996 | 34 |  | 4658 | 4945 | 0 | 32 | 38 | 2251 | [14 empty] | completed | CSIA - COMPLIANCE
2154 | 20582102052210 | Anderson | Anderson | Bare Steel / Plastic | 3360 | 3290 | 1736 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2155 | 18574102052217 | Marion | Marion | Bare Steel / Plastic | 2300 | 2335 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
2157 | 19582102052221 | Anderson | Alexandria | Bare Steel / Plastic | 5325 | 6248 | 4352 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2158 | 18583502052213 | Franklin | Martinsville | Bare Steel / Plastic | 6400 | 6316 | 83 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2159 | 18583502052214 | Franklin | Martinsville | Bare Steel / Plastic | 4350 | 3960 | 3420 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2160 | 17592402052217 | Bloomington | Martinsville | Bare Steel | 4005 | 4264 | 58 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2162 | 18583302052210 | Greenfield | Knightstown | Bare Steel / Plastic | 4940 | 6892 | 43 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2164 | 19582102052222 | Anderson | Anderson | Bare Steel / Cast Iron / Plastic | 3160 | 5161 | 1031 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2165 | 17573302052219 | Muncie | Muncie | Plastic | 4520 | 3947 | 56 |  | 4493 | 2780 | 0 | 4737 | 0 | 3874 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2166 | 17573302052220 | Muncie | Muncie | Plastic | 2775 | 773 | 36 |  | 2808 | 2795 |  | 2387 |  | 2589 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2168 | 17592602052217 | Columbus | Columbus | Bare Steel / Plastic | 4735 | 4173 | 76 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2180 | 16573302052218 | Muncie | Eaton | Bare Steel / Plastic | 3025 | 3155 | 41 |  | 3008 | 3150 | 35 | 1818 | 6 | 2266 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2181 | 16573302052219 | Muncie | Muncie | Bare Steel / Plastic | 4880 | 4850 | 51 |  | 6279 | 5450 | 46 | 3543 | 6 | 1139 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2182 | 16575102052213 | Richmond | Richmond | Bare Steel | 3750 | 4665 | 39 |  | 4261 | 4934 | 36 | 1129 | 6 | 1433 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2184 | 16575102052214 | Richmond | Richmond | Bare Steel / Plastic | 1680 | 2910 | 35 |  | 1707 | 2948 | 38 | 1336 | 0 | 1321 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2187 | 18592002052213 | Clarksville | Clarksville | Bare Steel / Plastic | 4375 | 2398 | 41 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2188 | 18592002052214 | Clarksville | Clarksville | Bare Steel / Plastic | 4660 | 3430 | 55 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2189 | 16574102052212 | Marion | Huntington | Bare Steel | 2520 | 2605 | 45 |  | 2756 | 2545 | 44 | 3918 | 0 | 2369 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2191 | 16582102052218 | Anderson | Elwood | Bare Steel | 3865 | 5540 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2193 | 16582102052219 | Anderson | Elwood | Bare Steel | 1910 | 2375 | 35 |  | 1191 | 2375 | 0 | 2813 | 0 | 2751 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2196 | 19595002052210 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 5495 | 2842 | 2426 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2199 | 19595002052212 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 2065 | 1946 | 497 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2202 | 19573302052218 | Muncie | Muncie | Bare Steel / Plastic | 4140 | 4120 | 4145 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2203 | 18573302052224 | Muncie | Muncie | Bare Steel / Plastic | 5890 | 5758 | 29 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
2207 | 19595002052213 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 3455 | 3773 | 5022 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2210 | 18595002052213 | Terre Haute | Terre Haute | Bare Steel / Cast Iron | 4620 | 3620 | 53 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2211 | 19595002052214 | Terre Haute | Terre Haute | Bare Steel / Cast Iron / Plastic | 4335 | 3242 | 1649 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2213 | 16583302052219 | Greenfield | Knightstown | Bare Steel / Plastic | 3270 | 3660 | 48 |  | 3736 | 3660 | 57 | 2233 | 0 | 1973 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2221 | 18582102052212 | Anderson | Chesterfield | Bare Steel / Plastic | 5295 | 4770 |  |  | 5524 | 4770 | 0 | 3416 | 0 | 2526 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2230 | 18574102052218 | Marion | Gas City | Bare Steel / Plastic | 15096 | 5205 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2235 | 19573302052219 | Muncie | Albany | Bare Steel / Plastic | 3020 | 2897 | 1719 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2239 | 19573302052220 | Muncie | Gaston | Bare Steel / Plastic | 3040 | 3655 | 1765 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2260 | 18583302052212 | Greenfield | Greenfield | Bare Steel / Plastic | 6030 | 5022 | 49 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2262 | 19583502052210 | Franklin | Martinsville | Bare Steel / Plastic | 6210 | 5392 | 3450 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2263 | 19583502052212 | Franklin | Martinsville | Bare Steel / Plastic | 7570 | 5908 | 5005 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2275 | 17595002052218 | Greencastle | Terre Haute | Bare Steel / Plastic | 6865 | 6827 | 91 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2277 | 17582102052210 | Anderson | Pendleton | Bare Steel | 6250 | 6000 | 5 |  | 5881 | 5345 | 0 | 1320 | 0 | 897 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2278 | 17595302052214 | Danville | Danville | Bare Steel / Plastic | 10625 | 11476 | 151 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
2279 | 18595302052213 | Danville | Brownsburg | Bare Steel / Plastic | 5795 | 5038 | 3475 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2257 | 17595502052212 | Lafayette | Frankfort | Bare Steel / Cast Iron | 4305 | 1885 | 61 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2280 | 18595302052214 | Danville | Brownsburg | Bare Steel / Plastic | 5455 | 5735 | 34 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2281 | 18595302052215 | Danville | Brownsburg | Bare Steel / Plastic | 8760 | 8324 | 98 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2283 | 17595302052212 | Danville | Danville | Bare Steel | 610 | 600 | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2286 | 17592402052218 | Bloomington | Oolitic | Bare Steel / Plastic | 2955 | 2720 | 17 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2291 | 17583302052213 | Greenfield | Rushville | Bare Steel / Plastic | 8075 | 8045 | 5 |  | 8223 | 8080 | 2 | 169 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2300 | 19595002052215 | Terre Haute | Rockville | Bare Steel / Plastic | 6275 | 6784 | 5843 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2301 | 17595302052216 | Crawfordsville | Danville | Bare Steel / Plastic | 9860 | 9694 | 79 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2306 | 19595302052210 | Crawfordsville | Danville | Bare Steel / Plastic | 5920 | 5791 | 4109 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2307 | 19595302052212 | Crawfordsville | Danville | Bare Steel / Plastic | 10972 | 9608 | 6667 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2308 | 17595302052215 | Crawfordsville | Danville | Bare Steel / Plastic | 10815 | 8843 | 155 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2309 | 19595302052213 | Crawfordsville | Danville | Bare Steel / Plastic | 6765 | 7420 | 6336 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2318 | 18595502052213 | Lafayette | West Lafayette | Bare Steel / Plastic | 6075 | 6026 | 16 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2319 | 18595502052214 | Lafayette | Lafayette | Bare Steel / Plastic | 8840 | 8422 | 5445 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2320 | 18595502052215 | Lafayette | West Lafayette | Bare Steel / Plastic | 6230 | 4997 | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
2322 | 19592602052217 | Columbus | Columbus | Bare Steel / Plastic | 4025 | 2772 | 1765 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2324 | 19592602052218 | Columbus | Columbus | Bare Steel / Plastic | 11085 | 7466 | 10035 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2325 | 19592602052219 | Columbus | Columbus | Bare Steel / Plastic | 6645 | 5255 | 3295 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2328 | 18595502052216 | Lafayette | Lafayette | Bare Steel / Plastic | 1445 | 3071 | 2594 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2326 | 17592602052214 | Columbus | Columbus | Bare Steel / Plastic | 5630 | 5355 | 71 |  | 5789 | 5934 | 64 | 5380 | 0 | 6043 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2332 | 19595302052214 | Danville | Lebanon | Bare Steel / Plastic | 1720 | 912 | 1352 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2333 | 19595002052216 | Terre Haute | Greencastle | Bare Steel / Plastic | 3380 | 3090 | 1034 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2339 | 18595502052217 | Lafayette | Lafayette | Bare Steel / Plastic | 3545 | 3541 | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | in service | CSIA - COMPLIANCE
2357 | 18592602052212 | Columbus | Columbus | Bare Steel / Plastic | 6605 | 4765 | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2360 | 19592402052210 | Bloomington | Bedford | Bare Steel / Plastic | 10540 | 10684 | 4685 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2364 | 19592402052213 | Bloomington | Bedford | Bare Steel / Plastic | 5895 | 17537 | 4361 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2369 | 19592402052214 | Mitchell | Bloomington | Bare Steel / Plastic | 3440 | 3393 | 1545 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2370 | 19592402052215 | Mitchell | Bloomington | Bare Steel / Plastic | 14310 | 15366 | 2880 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2374 | 18592402052214 | Bloomington | Bloomington | Bare Steel / Plastic | 2810 | 2583 | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
2376 | 17583302052219 | Greenfield | Rushville | Bare Steel / Plastic | 2300 | 3121 | 28 |  | 3229 | 3113 | 1 | 1219 | 0 | 3141 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2379 | 17583302052220 | Greenfield | Rushville | Bare Steel / Plastic | 9390 | 8758 | 9 |  | 9362 | 9477 | 0 | 1456 | 0 | 1309 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2380 | 19583302052210 | Greenfield | Greenfield | Bare Steel / Plastic | 7535 | 6368 | 3875 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2381 | 19592402052217 | Harrodsburg | Bloomington | Bare Steel / Plastic | 5900 | 5756 | 5335 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2385 | 18592602052213 | Columbus | Greensburg | Bare Steel / Plastic | 405 | 283 | 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2389 | 19592602052220 | Columbus | Seymour | Bare Steel / Plastic | 1145 | 1600 | 190 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2391 | 19592002052210 | Clarksville | Madison | Bare Steel / Plastic | 1480 | 1871 | 475 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2392 | 19592002052212 | Clarksville | Madison | Bare Steel / Plastic | 2795 | 1549 | 1655 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2394 | 19592002052213 | Clarksville | Madison | Bare Steel / Plastic | 11630 | 10832 | 12445 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | initiated | Excluded from CSIA
2396 | 18592602052214 | Columbus | Columbus | Bare Steel / Plastic | 5170 | 5273 | 29 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
2400 | 17592602052218 | Columbus | Columbus | Bare Steel / Cast Iron | 3755 | 3183 | 58 |  | 4095 | 3180 | 6 | 3165 | 0 | 3443 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2401 | 17592602052219 | Columbus | Columbus | Bare Steel / Cast Iron | 4575 | 3605 | 3315 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
2413 | 19583002052210 | Noblesville | Noblesville | Bare Steel / Plastic | 3390 | 3833 | 2695 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2417 | 17574102052212 | Marion | Marion | Bare Steel / Plastic | 1790 | 1769 | 0 |  | 1320 | 1295 | 0 | 704 | 3 | 815 | [14 empty] | completed | CSIA - COMPLIANCE
2421 | 17582102052224 | Anderson | Anderson | Bare Steel / Cast Iron | 2840 | 5357 | 54 |  | 3095 | 5355 | 49 | 3206 | 3 | 3614 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2426 | 18575102052213 | Richmond | Richmond | Bare Steel / Plastic | 5515 | 10476 | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2432 | 17592602052221 | Columbus | Columbus | Bare Steel / Plastic | 1015 | 2107 | 8 |  | 935 | 1510 | 0 | 497 | 0 | 824 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2450 | 18592402052210 | Bloomington | Bloomington | Bare Steel / Plastic | 1650 | 1626 | 195 |  | 1240 | 1625 | 0 | 951 | 0 | 275 | [14 empty] | posted to CPR | CSIA - COMPLIANCE
2459 | 19582102052223 | Anderson | Anderson | Bare Steel / Plastic | 1345 | 1358 | 385 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2487 | 20574102052210 | Marion | Huntington | Bare Steel / Plastic | 3920 | 3266 | 2898 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2496 | 19595502052210 | Lafayette | Frankfort | Bare Steel / Plastic | 2870 | 2612 | 11 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | completed | CSIA - COMPLIANCE
2512 | 19595502052212 | Lafayette | Lafayette | Bare Steel / Plastic | 7230 | 2858 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | CSIA - COMPLIANCE
2531 | 20595002052212 | Terre Haute | Cloverdale | Bare Steel / Plastic | 12850 | 13935 | 1430 |  | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | open | Excluded from CSIA
2532 | 20595002052213 | Terre Haute | Greencastle | Bare Steel / Plastic | 12440 | 12775 | 650 |  | 0 | 0 | 0 | . | 0 | 0 | [14 empty] | open | Excluded from CSIA
|  |  |  | TOTALS | 3717261 | 3939587 | 310127 | 0
|  |  |  | TOTALS - COMPLETED / IN-SERVICE | 388790 | 374820 | 7579 | 0 | 2707790 | 2863211 | 41316 | 2111653 | 18656 | 2123401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[A] Represents only Investment Costs on Projects In Service prior to December 31, 2020, excludes Removal Costs. Negative activity represents corrections posted to the work order during the trailing charge period.
Charges extending beyond 2008 represents trailing charges (invoices not paid until a later date) or restoration costs after the asset is placed in service.
[B] "Open" - Project is currently active and receiving charges, not yet in-service or complete, and not yet depreciating or receiving Post In-Service AFUDC accounting treatment.
"Initiated" - Project is included in the current year plan and is currently awaiting approval.
"Suspended" - Project engineering and planning has been performed. Project status will change to "Open" when construction begins.
"In-Service" - Project is depreciating (deferred) and is receiving Post In-Service AFUDC. Project is not unitized as final as-built is pending; preliminary footage data has been provided (above), if available.
"Complete" - Project is depreciating (deferred) and is receiving Post In-Service AFUDC.
[C] Services Retired represents services retired and not replaced.
[D] Service line footage retired represents the feet of service retired due to a retired or replaced service line.
[E] Services replaced represents the number of services that remain active after the project has been completed. The total count represents the number of steel services replaced + the number of tie-ins of existing plastic services.
[F] This project was created to capture permit costs for group numbers: 1, 2, 3, 4, 7, 8, 9, 20, 30, 31, 32.
[G] Group 81 and 860 are retirement only work orders, which only included removal expenses; therefore, no costs are reflected above for these work orders.
[H] Main retirement footages may be higer or lower than installed footage. This is attributable to dual mains being replaced with single main, or single main replaced with dual mains, service tie-overs where high pressure mains existed, proximity of existing high pressure mains to customer base and reduced customer base in some areas.
[J] Project not identified as BS/CI until completed with the system. Originally set up as a Gas System Improvement.
[K] Work orders labeled "CSIA Recoverable" consist of bare steel cast iron replacement work orders that are now eligible for recovery via the CSIA order granted in 2014. CSIA eligible work orders are those that had a zero CWIP balance or had not broken ground on January 1, 2014. Work orders labeled "Excluded from CSIA" are not eligible and will continue to follow the BSCI replacement program.

## SAH-9 (Public)
CEI North
2022-2026 TDSIC Plan
Database Number | Maximo Work Order Number | Work Order Number SAP/Oracle | Project Category | Area | City or Storage Field | Description | Planned Year | Base Estimate 2022 $ | Estimate for Planned Year
N/A | 14929034 | 21583002G61220 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-PLEASANT ST RIVER RD TO 11TH PH 1-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 945' 2" PE, 1620' 4" PE, 200' 6" PE, 210' 8" PE MAINS AND 19 SERVICE LINES FOR ROAD RECONSTRUCTION PROJECT | 2022
N/A | 16299341 | 21592602G61215 | PUBLIC IMPROVEMENT - DIST | SE | COLUMBUS | IN-COLUMBUS-LOWELL RD RECONST US 31 SB TO 200 W ~~ Relocate/replace 1915' of 2" PE & 515' of 4” PE distribution mains and retire 1215' of 2" main and 1215' of 4" main for road improvement project | 2022
N/A | 16299366 | 21592602G61212 | PUBLIC IMPROVEMENT - DIST | SE | COLUMBUS | IN-COLUMBUS-LOWELL RD RECONST 325 W TO 200 W ~~ Relocate/replace 115' of 2" PE and 240' of 4” PE distribution mains and retire 355' of 4" PE main and replace one service for road improvement project | 2022
N/A | 16542367 | 19592402061219 | PUBLIC IMPROVEMENT - DIST | SE | MARTINSVILLE | IN-MARTINSVILLE-OHIO ST FROM POSTON RD TO MORGAN ST-RELOCATE/INSTALL 4250' OF 4" PE MAIN AND 68 SERVICES. RETIRE 1800' OF 4" PE MAIN AND 2450 OF 4" BARE STEEL MAIN AND 68 SERVICES. ROAD RECONSTRUCTION PROJECT | 2022
N/A | 16623863 | 21583502G61214 | PUBLIC IMPROVEMENT - DIST | SE | EDINBURGH | IN-EDINBURGH-SR 252, US 31 TO I65 ~~ Relocate/install 460' of 4" PE and 6505' of 2" PE distribution mains and 56 services. Retire 7065' of 4" steel main and 56 services for road improvement project | 2022
N/A | 16623868 | 21592402G61212 | PUBLIC IMPROVEMENT - DIST | SE | BLOOMINGTON | IN-BLOOMINGTON-SR 45 AND PETE ELLIS ROAD ~~ Relocate/install 980' of 2" PE and 1775' of 6" PE distribution mains and 5 services. Retire 1757' of 4"/ 6" mains and 5 services for road improvement project | 2022
N/A | 16623878 | 21592402G61213 | PUBLIC IMPROVEMENT - DIST | SE | BLOOMINGTON | IN-BLOOMINGTON-E 3RD (SR46) AT SMITH ROAD ~~ Relocate/install 1335' of 4" PE and 400' of 6” steel distribution mains and 12 services. Retire 1335' of 4" PE and 400' of steel mains and 12 services for road improvement project | 2022
N/A | 16881738 | 21592402G61219 | PUBLIC IMPROVEMENT - DIST | SE | BLOOMINGTON | IN-BLOOMINGTON-VERNAL PIKE CONNECTOR DES#1702957 & 1900 ~~ Relocate/install 800' of 4" steel main and 5 services. Retire 800' of 4" steel main and 5 services for road improvement project. | 2022
N/A | 17619497 | 20574102G61216 | PUBLIC IMPROVEMENT - DIST | NE | UPLAND | Des #1800168 SR 22 RR & Pavement Project-Upland-Grant Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 3700’ of 4" main and replace 28 services. This main appears to be in conflict with an INDOT road reconstruction project. | 2022
N/A | 17619503 | 20573302G61213 | PUBLIC IMPROVEMENT - DIST | NE | ALBANY | Des #1701336 SR 28 Bridge Replacement-Delaware Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 200’ of 4" main and replace 2 services. This main appears to be in conflict with an INDOT bridge replacement project. | 2022
N/A | 17619514 | 20575102G61213 | PUBLIC IMPROVEMENT - DIST | NE | RICHMOND | Des #1702769 Main St-Ft Wayne Ave & NE St Bike Project-Richmond - Final plans have yet to be published. Based off of the available information, we will relocate approximately 1176’ of 8" main and replace 11 services. This main appears to be in conflict with an INDOT bridge replacement project. | 2022
N/A | 17619523 | 20573302G61218 | PUBLIC IMPROVEMENT - DIST | NE | NEW CASTLE | Des #1600789 SR 103 Road Recon-Henry Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 4000’ of 2" main and replace 44 services. This main appears to be in conflict with an INDOT road reconstruction project. | 2022
N/A | 17619553 | 20573302G61219 | PUBLIC IMPROVEMENT - DIST | NE | MUNCIE | Muncie Sanitary District - CSO 023 Project-Various Streets - Final plans have yet to be published. Based off of the available information, we will relocate approximately 825’ of 2" main and replace 15 services. This main appears to be in conflict with a city sewer separation project. | 2022
N/A | 17619921 | 20583302G61214 | PUBLIC IMPROVEMENT - DIST | SE | KNIGHTSTOWN | Des #1702899-1702901 US 40-SR 103 Pavement Project-Henry Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 2500’ of 2” main and replace 31 services. This main appears to be in conflict with an INDOT road reconstruction project. | 2022
N/A | 17620008 | 20574102G61215 | PUBLIC IMPROVEMENT - DIST | NE | HUNTINGTON | Des #1902041 US 24 & SR 9 Project-Huntington Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 865’ of 6" main and replace 2 services. This main appears to be in conflict with an INDOT road project. | 2022
N/A | 17620009 | 20583302G61210 | PUBLIC IMPROVEMENT - DIST | SE | RUSHVILLE | Des #1702912 US 52 Bridge Project-Rush Co | 2022
N/A | 17620011 | 20583302G61213 | PUBLIC IMPROVEMENT - DIST | SE | KNIGHTSTOWN | Des #1701338 US 40 Bridge Project-Henry Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 800’ of 4” main and replace no services. This main appears to be in conflict with an INDOT bridge replacement project. | 2022
N/A | 17624038 | 21583502G61215 | PUBLIC IMPROVEMENT - DIST | SE | FRANKLIN | IN-FRANKLIN-YANDES & MADISON ST PROJECT-JOHNSON CO ~~ Relocate/install 1700' of 2” PE distribution mains and 7 services. Retire 1700' of 2" PE main and 7 services for road improvement project | 2022
N/A | 17624130 | 21592402G61214 | PUBLIC IMPROVEMENT - DIST | SE | BLOOMINGTON | IN-BLOOMINGTON-SR 45 WIDENING NEAR BUNGER RD ~~ Relocate/install 1500' of 4” PE distribution mains and 12 services. Retire 1500' of 4" mains and 12 services for road improvement project | 2022
N/A | 17624230 | 21583502G61213 | PUBLIC IMPROVEMENT - DIST | SE | FRANKLIN | IN-FRANKLIN-US 31 INTERSECTION PROJECTS ~~ Relocate/install 300' of 2” PE and 150' of 4" PE distribution mains. Retire 300' of 2" PE and 150' of 4" PE mains for road improvement project | 2022
N/A | 17624352 | 21583002G61214 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-SR 32 LAKEVIEW TO 19TH ST-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO ~70' 2" PE MAIN FOR ROAD RECONSTRUCTION | 2022
N/A | 17624542 | 21583002G61215 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-LITTLE CHICAGO-PATH PROJECT-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 300' 2" PE, 80' 4" STL, 1700' 6" STL MAIN FOR BRIDGE REPLACEMENT/NEW PATH CONSTRUCTION | 2022
N/A | 17624590 | 21583002G61216 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-SR 32/MILL CREEK ROB-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 1400' 4" PE MAIN AND 2 SERVICE LINES FOR INTERSECTION IMPROVEMENT | 2022
N/A | 17624639 | 21583002G61217 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-SR 38/OAKMONT DR ROB-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 330' 2" PE MAIN & 1100' 4" PE MAIN FOR INTERSECTION IMPROVEMENT | 2022
N/A | 17624645 | 21583002G61218 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-SR 38/LOGAN ST ROB-BASED OFF AVAILABLE INFORMATION WE WILL RELO 500' 6" STL MAIN AND 3 SERVICE LINES FOR INTERSECTION IMPROVEMENT | 2022
N/A | 17624653 | 21583002G61219 | PUBLIC IMPROVEMENT - DIST | NE | FISHERS | IN-FISHERS-106TH/HOOSIER RD ROB-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 750' 8" STL, 400' 6" PE, 200' 4" PE MAIN AND 10 SERVICE LINES FOR INTERSECTION IMPROVEMENT | 2022
N/A | 18101887 | 20592402061219 | PUBLIC IMPROVEMENT - DIST | SE | MARTINSVILLE | IN-MARTINSVILLE-SOUTH ST-INDOT-DES.NO.1702961-RELOCATE/INSTALL 1015' OF 4" PE MAIN AND 290' OF 2" PE MAIN AND 8 SERVICES. RETIRE 160' OF 2" PE MAIN, 115' OF 2" BARE STEEL MAIN, AND 1385 OF 4" BARE STEEL MAIN AND 8 SERVICES. ROAD RECONSTRUCTION PROJECT | 2022
N/A | 18471007 | 21583502G61216 | PUBLIC IMPROVEMENT - DIST | SE | SHELBYVILLE | IN-SHELBYVILLE-MCKAY RD & MILLER ST RAB ~~ Relocate/install 800' of 4” PE & 980' of 6" steel distribution mains. Retire 800' of 4" PE and 980' of 6" steel mains for road improvement project | 2022
N/A | 18471025 | 21592402G61215 | PUBLIC IMPROVEMENT - DIST | SE | BLOOMINGTON | IN-BLOOMINGTON-SR 45 INTER IMPR-MONROE CO ~~ Relocate/install 1200' of 4” PE distribution mains and 3 services. Retire 1200' of 4" PE main and 3 services for road improvement project | 2022
N/A | 18520457 | 21583302061210 | PUBLIC IMPROVEMENT - DIST | SE | GREENFIELD | IN-GREENFIELD-CR 600 W ~~ INDOT DES. NO. 1702756 SEGMENT B - Install 1,380’ of 6” Steel, 1,615’ of 6” PE, 645’ of 4” PE, 1,845’ of 2” PE, and 1 Regulator Station. Retire 1,675’ of 6” Steel, 1,035’ of 6” PE, 410’ of 4” PE, 2,150’ of 2” PE, and 1 Regulator Station. Replace 15 Services. Necessary for road reconstruction. | 2022
N/A | 18540600 | 21595302G61210 | PUBLIC IMPROVEMENT - DIST | NW | LEBANON | IN-LEBANON-GRANT ST-PHASE 1~~RELOCATE/INSTALL 150' OF 6" STEEL AND 300' OF 2" STEEL DISTRIBUTION MAINS, AND 3 SERVICES. RETIRE 150' OF 6" STEEL AND 300' OF 2" STEEL DISTRIBUTION MAINS, AND 3 SERVICES FOR ROAD IMPROVEMENT PROJECT. | 2022
N/A | 18540641 | 21595302G61212 | PUBLIC IMPROVEMENT - DIST | NW | LEBANON | IN-LEBANON-GRANT ST-PHASE 2~~RELOCATE/INSTALL 1400' OF 4" PE DISTRIBUTION MAIN AND 9 SERVICES. RETIRE 1400' OF 4" PE DISTRIBUTION MAIN AND 9 SERVICES FOR ROAD IMPROVEMENT PROJECT. | 2022
N/A | 18540826 | 21595502G61210 | PUBLIC IMPROVEMENT - DIST | NW | ROMNEY | IN-ROMNEY-US HWY 231-PASSING LANES~~RELOCATE/INSTALL 4400' OF 8" STEEL DISTRIBUTION MAIN AND 3 SERVICES. RETIRE 4400' OF 8" STEEL DISTRIBUTION MAIN AND 3 SERVICES FOR ROAD IMPROVEMENT PROJECT. | 2022
N/A | 18540904 | 21592602G61217 | PUBLIC IMPROVEMENT - DIST | SE | SEYMOUR | IN-SEYMOUR-O'BRIEN ST AT 4TH ST RAB ~~ Relocate/install 300' of 6" steel distribution mains and retire 300' of 6" steel mains to accommodate road improvement project | 2022
N/A | 18560008 | 21595002G61212 | PUBLIC IMPROVEMENT - DIST | NW | GREENCASTLE | IN-GREENCASTLE-US HWY 231-CULVERTS~~RELOCATE/INSTALL 1000' OF 4" STEEL DISTRIBUTION MAIN. RETIRE 1000' OF 4" STEEL DISTRIBUTIN MAIN FOR ROAD IMPROVEMENT PROJECT. | 2022
N/A | 18563084 | 21592002G61210 | PUBLIC IMPROVEMENT - DIST | SE | CLARKSVILLE | Clarksville-Blackiston Mill Rd Bridge No. 51-INSTALL 1 NEW SERVICE. RETIRE 110' OF 2" PE MAIN AND 1 SERVICE-BRIDGE/ROAD RECONSTRUCTION PROJECT | 2022
N/A | 18565148 | 21574102G61210 | PUBLIC IMPROVEMENT - DIST | NE | MARION | Des #2001581 SR 15 Bridge Culvert Project-Grant Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 800’ of 6” main and replace no services. This main appears to be in conflict with an INDOT culvert replacement project. | 2022
N/A | 18565173 | 21573302G61210 | PUBLIC IMPROVEMENT - DIST | NE | NEW CASTLE | Des #1593238 SR 38 Bridge over Big Blue River-Henry Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 800’ of 6” main and replace 2 services. This main appears to be in conflict with an INDOT bridge replacement project. | 2022
N/A | 18565178 | 21574102G61212 | PUBLIC IMPROVEMENT - DIST | NE | HUNTINGTON | City of Huntington - Long Term Sewer Project - Final plans have yet to be published. Based off of the available information, we will relocate approximately 8300’ of 4” main and replace 25 services. This main appears to be in conflict with a city sewer project. | 2022
N/A | 18565207 | 21573302G61212 | PUBLIC IMPROVEMENT - DIST | NE | ALBANY | Des #1600783 SR 28 Road Recon-Delaware Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 400’ of 2” main and replace 15 services. This main appears to be in conflict with an INDOT road reconstruction project. | 2022
N/A | 18565342 | 21573302G61213 | PUBLIC IMPROVEMENT - DIST | NE | HAGERSTOWN | Wayne Co - Bridge 194 South St-Hagerstown - Final plans have yet to be published. Based off of the available information, we will relocate approximately 600’ of 4” main and replace no services. This main appears to be in conflict with a county bridge replacement project. | 2022
N/A | 18565390 | 21582102G61215 | PUBLIC IMPROVEMENT - DIST | NE | PENDLETON | IN-PENDLETON-US 36/SR 9-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 1500' 2" PE, 1300' 4" PE, 150' 6" STL MAINS DUE TO ROAD RECONSTRUCTION | 2022
N/A | 18565407 | 21575102G61210 | PUBLIC IMPROVEMENT - DIST | NE | RICHMOND | Bridge #47 NW L Street - Richmond - Final plans have yet to be published. Based off of the available information, we will relocate approximately 600’ of 6” main and replace 2 services. This main appears to be in conflict with a county bridge replacement project. | 2022
N/A | 18775649 | 21592002G61214 | PUBLIC IMPROVEMENT - DIST | SE | NEW ALBANY | IN-NEW ALBANY-KAMER MILLER RD INT - Relocate 1,000’ of 6” PE, 915’ of 4” PE, 455’ of 2” PE, and 9 Services. Necessary for intersection reconstruction. | 2022
N/A | 18775655 | 21583502G61218 | PUBLIC IMPROVEMENT - DIST | SE | BARGERSVILLE | IN-BARGERSVILLE-SMOKEY ROW RD DRAINAGE~~ - Relocate 585’ of 4” PE and 2 Services. Necessary for drainage improvements. | 2022
N/A | 18775658 | 21592402G61217 | PUBLIC IMPROVEMENT - DIST | SE | MARTINSVILLE | IN-MARTINSVILLE-LAKE DETURK PRIM. SPILLWAY – Replace 195’ of 3” PE with 205’ of 4” PE. Necessary for the Spillway reconstruction. | 2022
N/A | 18781918 | 21595002G61220 | PUBLIC IMPROVEMENT - DIST | NW | CLINTON | IN-CLINTON-SR 163 OVER BROUILLETS CREEK-DES #1701589: relocate/install 500' of 6" plastic main & retire 500' of 6" plastic main for a bridge replacement project. | 2022
N/A | 18781971 | 21595002G61221 | PUBLIC IMPROVEMENT - DIST | NW | CLINTON | IN-CLINTON-9TH ST-DES #1800239: relocate/install 700' of 2" plastic main & 6 services & retire 700' of 2" plastic main & 6 services for road reconstruction and storm sewer improvement project. | 2022
N/A | 18782110 | 21595302G61216 | PUBLIC IMPROVEMENT - DIST | NW | AVON | IN-AVON-DAN JONES RD FROM MAIN RD TO CR 100 S-DES #1801463: relocate/install 2700' of 2" plastic main & 10 service & retire 2700' of 2" plastic main & 10 services for road reconstruction and storm sewer installation project. | 2022
N/A | 18782116 | 21595002G61222 | PUBLIC IMPROVEMENT - DIST | NW | CLOVERDALE | IN-CLOVERDALE-US 231-DES #1800151: relocate/install 500' of 4" steel main & retire 500' of steel main for bridge/culvert replacement project | 2022
N/A | 18782267 | 21595002G61223 | PUBLIC IMPROVEMENT - DIST | NW | TERRE HAUTE | IN-TERRE HAUTE-13TH & 8TH ST-DES #1801932: install 550' of 6" plastic main & 6 services. Retire 625' of 2" plastic main, 495' of 6" steel main, 380' of 4" steel main & 6 services for roundabout/bridge/road reconstruction & storm sewer improvement project. | 2022
N/A | 18782269 | 21595302G61222 | PUBLIC IMPROVEMENT - DIST | NW | BROWNSBURG | IN-BROWNSBURG-CR 700 FROM SR 267 TO CR 900 E- DES #1701590 - based on available information: relocate/install 5000' of 6" plastic main, 500' of 4" plastic main, 1000' of 2" plastic main & 15 services. Retire 5000' of 6" steel main, 500' of 4" plastic main, 1000' of 2" plastic main & 15 services for road reconstruction & storm sewer improvement project. | 2022
N/A | 18783818 | 21595302G61224 | PUBLIC IMPROVEMENT - DIST | NW | ZIONSVILLE | IN-ZIONSVILLE-CR 800 & OAK ST: based on available information - relocate/install 3000' of 6" plastic main, 100' of 2" plastic main, & 8 services. Retire 2500' of 6" plastic main, 400' of 2" plastic main, & 8 services for road reconstruction/roundabout/storm sewer installation project. | 2022
N/A | 15704575 | 18592002044210 | RURAL EXTENSION | SE | GEORGETOWN | IN-GEORGETOWN-SB560 OFFSITE EXPANSION ~~ | 2022
N/A | 16990862 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENWOOD | IN-GREENWOOD-WORTHSVILLE RD INTERCHANGE there are 2 inch bottlenecks and large subdivision on end of 1 way feed in area where growth is expected with new Worthsville Road interchange with I-65. Install 3,560' of 6" main. This is one way feed to 622 customers fed by 2" main. | 2022
N-XA-11505 | 10767877 | 17595502G51210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN-LAFAYETTE-KOSSUTH ST-UPRATE GAS MAIN, (LORI LEE) - Project area operating at 15psig and will be Uprated to 60psig MAOP. Area has 3,959' of main, and 754' of service lines with 119 services. The gas main was installed between 1965 and 1968 and 60 of the 119 services have no information on the service card. Uprate needed to retire station and to bolster pressure in area. Project has gone from an uprate to a total replacement per Operations because of existing location of mains and service lines and age of pipe. There are 112 steel services with no established MAOP with no established MAOP IN-LAFAYETTE-KOSSUTH ST-UPRATE GAS MAIN, (LORI LEE) - Project area operating at 15psig and will be Uprated to 60psig MAOP. Area has 3,959' of main, and 754' of service lines with 119 services. The gas main was installed between 1965 and 1968 and 60 of the 119 services have no information on the service card. Uprate needed to retire station and to bolster pressure in area. Project has gone from an uprate to a total replacement per Operations because of existing location of mains and service lines and age of pipe. There are 112 steel services with no established MAOP with no established MAOP | 2022
N-XA-11506 | 13807515 | 17595502G51212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | WEST LAFAYETTE | IN-WEST LAFAYETTE-KLONDIKE AREA 1- ELEVATE/RETEST IN-WEST LAFAYETTE-KLONDIKE AREA 1-ELEVATE/RETEST. Area is operating at 20PSIG and will be Uprated to 60PSIG MAOP. Uprate area has 27,734' of main and 19,908' of service line that feeds 419 services. 300' of 6" PE and 225' of 2" PE will be installed to create a tie. Uprate need to bolster pressure in area. There are 5 steel services and 3 plastic services with no established MAOP | 2022
N-XA-11514 | 15525323 | 18595302G51212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | PLAINFIELD | IN-PLAINFIELD-25 PSIG SYSTEM AREA . Uprate area fed from Regulator Stations #46000027 and #46000066 at 25 PSIG and will be uprated to 60psig MAOP. Uprate area includes 16.56 miles (87,287')of gas main & 41.67 miles (206,758') of service lines and 2,625 services. 35 services will need to be replaced or retested. Regulator Stations #46000027 and #46000066 will be retired. Uprate is needed to bolster pressure in area and to retire reg stations. There are 1,280 steel services and 41 plastic services with no established MAOP IN-PLAINFIELD-25 PSIG SYSTEM AREA . Uprate area fed from Regulator Stations #46000027 and #46000066 at 25 PSIG and will be uprated to 60psig MAOP. Uprate area includes 16.56 miles (87,287')of gas main & 41.67 miles (206,758') of service lines and 2,625 services. 35 services will need to be replaced or retested. Regulator Stations #46000027 and #46000066 will be retired. Uprate is needed to bolster pressure in area and to retire reg stations. There are 1,280 steel services and 41 plastic services with no established MAOP. | 2022
N-XA-11538 | 15497686 | 18595502G51210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | WEST LAFAYETTE | IN-WEST LAFAYETTE-KLONDIKE AREA 2 IN-WEST LAFAYETTE-KLONDIKE AREA 2 - Uprate 33.84 miles of gas main & 21.75 miles of service lines from 27 to 54 PSIG. Total services 1,513. 992' of 2" plastic main will be retested and 61 services will need to be replaced or retested. Lafayette system reliability improvement. | 2022
N-XA-11539 | 15497693 | 18595502G51212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | WEST LAFAYETTE | IN-WEST LAFAYETTE-KLONDIKE AREA 3-UPRATE GAS MAIN Uprate 20.53 miles of gas main & 17.98 miles of service lines from 18 to 54 PSIG. Total services 1,184. No main but 28 services will need to be replaced or retested. | 2022
N-XA-11722 | 14000066 | 19595702051212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | FRANKFORT | IN-FRANKFORT-SR 28-VALVE REPAIR SR 28 Valve Repair, 12" Valve feeding Frito Lay factory. Safety improvement. | 2022
N-XA-11723 | 10767853 | 16595502051210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | WEST LAFAYETTE | IN-WEST LAFAYETTE-BROWN ST-UPRATE GAS MAIN BROWN ST ~~UPRATE GAS MAIN to improve system reliability | 2022
N-XA-11725 | 17893394 | 20583002051222 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | FISHERS | IN-FISHERS-SOUTHEASTERN PKWY --- Install approximately 2,100' of 8" PE on Southeastern Parkway, from Olio Rd east to Jack Walker Ln to help overloaded 6" main on Olio Rd. No services included on project. INSTALL 8" MAIN | 2022
N-XA-11739 | 16812141 | 20573302051213 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | YORKTOWN | IN-YORKTOWN-7900 N COUNTY ROAD 925 W Encroachment project customer build a barn on existing 4" plastic distribution main in easement. Relocate 100' section of 4" main from building corner. | 2022
N-XA-11762 | 16055567 | 19595302051219 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | BROWNSBURG | IN - Brownsburg - Acre Lane Area - Uprate Brownsburg - Uprate Acre Lane Area, (MAOP) from 25 to 60 PSIG, Retire Regulator Station #46000016. Uprate area includes 17,509’ of gas main and 19,475’of service lines. There are also 197 services of which 26 will need to be retested/replaced due to insufficient pressure test or threaded fittings. There are 27 steel services and 2 plastic services with no established MAOP with no established MAOP, Project area is part of BSCI project N-2279 slated for 2021 Station to be retired | 2022
N-XA-11763 | 10767696 | 17595302G50210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | PLAINFIELD | IN- PLAINFIELD - MAXWELLTON - UPRATE PLAINFIELD-MAXWELLTON UPRATE currently , fed by regulator station 46000030, MAOP will be uprated from 20 PSIG TO 60 PSIG. Uprate area includes 16,230' of main which is made up off 2", 3" and 4" plastic and steel pipe. Also in uprate area are 7,632’of service lines that feed 179 services. Uprate needed to bolster pressure in area and to retire reg station. There are 36 steel services and 1 plastic services with no established MAOP. Install 2085' of 2" main and 37 services. | 2022
N-XA-11772 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | DANVILLE | IN - Danville - 100N - Virginia - Install main (100N - Virginia) Install ~ 2100' of 6" PE on CR 100N/10th St from east of Polley Dr to west of Virginia Dr 400' of 2"PE. Increases minimum pressure in 60-psig system to 29 psig from 21 psig, Help gas pressure drop from new growth on west side of Plainfield. (0 - Services) | 2022
N-XA-11803 | 17834732 | 20583002051220 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | CARMEL | IN-CARMEL-W 106TH ST -- INSTALL 8IN MAIN Tie together two 8" steel mains on 106th st just east of Torrey Pines Circle (creek crossing). Expected Improvement: Provides 2-4 psi increase in Carmel/Zionsville area and improves reliability of the system if we were to lose stations 12 or 62. | 2022
N-XA-11804 | 17830488 | 20573302051218 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | DALEVILLE | IN-DALEVILLE-S CR 800 W -- REPLACE MAIN Replace ~ 6500' of 4" with 6" PE on CR 800W from RS #1386 outlet south to existing 6" main. Expected Improvement: Increases minimum pressure in 60-psig system to 42.3 psig from 5.2 psig | 2022
N-XA-11805 | 17838700 | 20583002051221 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | CARMEL | IN-CARMEL-JEFFRIES PL-INSTALL 2IN PL MAIN Install ~ 150' of 2" PE on Jeffries Pl from E 126th south to existing 2" main. Expected Improvement: Increases pressure in neighborhood to 39 psig from 29 psig | 2022
N-XA-11806 | 17724841 | 20583002051218 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | FISHERS | IN-NOBLESVILLE-FISHERS SOUTHEASTERN PARKWAY / E 126TH ST Install approximately 4,100' of 6" PE on Southeastern Parkway, from Florida Rd north to E 126th St. Install approximately 650' of 4" PE on E 126th St, from Southeastern Parkway west to existing 4" plastic main. | 2022
N-XA-11807 | 17912407 | 20575102050217 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | RICHMOND | IN-RICHMOND-S J &23RD ST -- REPLACE MAIN & SERVICES MOD project set up for 2021, engineer to be done in 2020. ENE Engineering. 22 customer transferred from 2" S main (10#) to 6" main (54#). | 2022
TBD | 16921762 | 18592602G51210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | COLUMBUS | IN-COLUMBUS-COLUMBUS SOUTHSIDE HP LOOP install 2.75 miles of 6 inch steel HP main to loop HP system south of Columbus for increased system pressure and reliability | 2022
NWTDSIC01 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | IN-Wolcott Storage Field - Replace 2- 4" Valves, 2 - 6" Valves and 1- 16" Valve | 2022
NWTDSIC02 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | LEBANON LP | Replace final exterior station lighting with new poles and LED lights to increase safety, light quality and energy efficiency. | 2022
NWTDSIC03 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | LEBANON LP | Replace Lighting inside compressor building with LED Fixtures to increase safety, light quality and energy efficiency | 2022
SETDSIC01 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | JEFFERSON LP | Install Fire Pump and tank hose monitors - ensure plant safety for enhanced system reliability | 2022
SETDSIC02 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | JEFFERSON LP | Replace final exterior station lighting with new poles and LED lights to increase safety, light quality and energy efficiency | 2022
SETDSIC03 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | SELLERSBURG | Replace exterior station lighting with new poles and LED lights to increase safety, light quality and energy efficiency. | 2022
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | VEDIN | Multiple | TARGETED ECONOMIC DEVELOPMENT | 2022
N/A | 15162787 | 20573302G61222 | PUBLIC IMPROVEMENT - DIST | NE | MUNCIE | Des # 1700751 MUNCIE-ARTS & CULTURAL TRAIL - Final plans have yet to be published. Based off of the available information, we will relocate approximately 2600’ of 2” main and replace 56 services. This main appears to be in conflict with a city trail & road project. | 2023
N/A | 15277645 | 20583002G61210 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-146TH STREET AT ALLISONVILLE ROAD- BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 875' 2" PE, 875' 6" PE, 1050' 8" PE, 1300' 12" STL MAINS AND 7 SERVICE LINES DUE TO INTERSECTION IMPROVEMENT | 2023
N/A | 16723181 | 21583002G61210 | PUBLIC IMPROVEMENT - DIST | NE | FISHERS | IN-FISHERS-106TH/CUMBERLAND BRIDGE 187-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 1,000' 6" PE MAIN FOR BRIDGE REPLACEMENT PROJECT | 2023
N/A | 16903501 | 21595502G61213 | PUBLIC IMPROVEMENT - DIST | NW | WEST LAFAYETTE | IN-WEST LAFAYETTE-MOREHOUSE RD-ROAD RECONSTRUCTION~~RELOCATE/INSTALL 4500' OF 6" PE MAIN, AND 13 SERVICES. RETIRE 4000' OF 6" STEEL AND 500' OF 4" PE DISTRIBUTION MAINS, AND 13 SERVICES FOR ROAD IMPROVEMENT PROJECT. | 2023
N/A | 17177730 | 19592402061236 | PUBLIC IMPROVEMENT - DIST | SE | BLOOMINGTON | IN-BLOOMINGTON-W FULLERTON PIKE PH 3 ~~INDOT-DES.NO.1802977-RELOCATE/INSTALL 1675' OF 2" PE MAIN AND 16 SERVICES. RETIRE 2265 OF 2" PE MAIN AND 16 SERVICES. -ROAD RECONSTRUCTION PROJECT | 2023
N/A | 17619474 | 20575102G61210 | PUBLIC IMPROVEMENT - DIST | NE | RICHMOND | Wayne Co - Bridge No. 720 Rehab - Final plans have yet to be published. Based off of the available information, we will relocate approximately 500’ of 12” main and replace 1 services. This main appears to be in conflict with county bridge replacement project. | 2023
N/A | 17900173 | 20592402061218 | PUBLIC IMPROVEMENT - DIST | SE | MARTINSVILLE | IN-MARTINSVILLE-INDOT-DES.NO.1802868 & 1802869-RELOCATE/INSTALL 7300' OF 2" PE MAIN AND 72 SERVICES. RETIRE 7300' OF 2" PE MAIN AND 72 SERVICES. BIKE & PEDESTRIAN PATH PROJECT | 2023
N/A | 18560039 | 21595502G61216 | PUBLIC IMPROVEMENT - DIST | NW | LAFAYETTE | IN-LAFAYETTE-OLD US HWY 231-REPLACE BRIDGE~~RELOCATE/INSTALL 300' OF 8" STEEL DISTRIBUTION MAIN. RETIRE 300' OF 8" STEEL DISTRIBUTION MAIN. | 2023
N/A | 18560555 | 21582102G61210 | PUBLIC IMPROVEMENT - DIST | NE | PENDLETON | IN-PENDLETON-SR 13/CR 800S-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 425' 4" PE MAIN DUE TO ROAD RECONSTRUCTION | 2023
N/A | 18560565 | 21583002G61222 | PUBLIC IMPROVEMENT - DIST | NE | CARMEL | IN-CARMEL-96TH/COLLEGE-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 450' 4" STL, 500' 4" PE MAINS AND 5 SERVICE LINES DUE TO INTERSECTION IMPROVEMENT | 2023
N/A | 18563028 | 21583502G61210 | PUBLIC IMPROVEMENT - DIST | SE | GREENWOOD | IN-GREENWOOD-COUNTY LINE RD FROM SR 37 TO SR 135-RELOCATE/INSTALL 12100' OF 6" PE MAIN, 100' OF 4" PE MAIN, AND 43 SERVICES. RETIRE 500' OF 2" BARE STEEL MAIN, 100' OF 4" BARE STEEL MAIN, 12100' OF 6" PE MAIN, AND 43 SERVICES. ROAD WIDENING/RECONSTRUCTION PROJECT | 2023
N/A | 18565291 | 21583302G61210 | PUBLIC IMPROVEMENT - DIST | SE | CAMBRIDGE CITY | Des #1900190 SR 1 Structure Project-Wayne Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 400’ of 4” main and replace no services. This main appears to be in conflict with an INDOT culvert replacement project. | 2023
N/A | 18565343 | 21582102G61214 | PUBLIC IMPROVEMENT - DIST | NE | FRANKTON | Des #1900251 SR 128 Pavement Project-Madison Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 600’ of 2” main and replace 10 services. This main appears to be in conflict with an INDOT road reconstruction project. | 2023
N/A | 18565357 | 21573302G61214 | PUBLIC IMPROVEMENT - DIST | NE | EATON | Des #1702884 SR 3 Structure Project-Delaware Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 600’ of 4” main and replace no services. This main appears to be in conflict with an INDOT culvert replacement project. | 2023
N/A | 18565392 | 21574102G61213 | PUBLIC IMPROVEMENT - DIST | NE | HUNTINGTON | Des #1900239 SR 124 Structure Project-Huntington Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 600’ of 4” main and replace no services. This main appears to be in conflict with an INDOT culvert replacement project. | 2023
N/A | 18565405 | 21583002G61225 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-SR 37/191ST ST-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 550' 4" PE MAIN DUE TO INTERSECTION IMPROVEMENT | 2023
N/A | 18565636 | 21592602G61210 | PUBLIC IMPROVEMENT - DIST | SE | COLUMBUS | IN-COLUMBUS-SR 11 OVER DENOIS CREEK-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 700' 4" STL HP DISTR MAIN DUE TO BRIDGE REPLACEMENT | 2023
N/A | 18775552 | 21583502G61217 | PUBLIC IMPROVEMENT - DIST | SE | BARGERSVILLE | IN-BARGERSVILLE-S. SR 135 DES 1800033 - Install 7,095’ of 8” PE, 1,840’ of 6” PE, and 825’ of 2” PE. Retire 7,250’ of 8” Steel, 1,270’ of 8” PE, 1,850’ of 6” PE, 35’ of 4” PE, and 1,090’ of 2” PE. Replace 15 Services. Necessary for road reconstruction. | 2023
N/A | 18781708 | 21595002G61214 | PUBLIC IMPROVEMENT - DIST | NW | TERRE HAUTE | IN-TERRE HAUTE-I-70 OVER ROBINSON RD-DES #1900178-193: based on available information - relocate/install 300' of 4" steel main & retire 300' of 4" steel main for bridge replacement project. | 2023
N/A | 18781762 | 21595002G61216 | PUBLIC IMPROVEMENT - DIST | NW | TERRE HAUTE | IN-TERRE HAUTE-I-70 OVER CSX RR-DES #1900195-198: based on available information - relocate/install 300' of 2" plastic main & retire 300' of 2" plastic main for bridge replacement project. | 2023
N/A | 18781800 | 21595302G61215 | PUBLIC IMPROVEMENT - DIST | NW | NORTH SALEM | IN-NORTH SALEM-SR 75-DES #1801720: based on available information - relocate/install 1000' of 8" plastic main & retire 1000' of 8" plastic main for road drainage project. | 2023
N/A | 18782175 | 21595302G61217 | PUBLIC IMPROVEMENT - DIST | NW | AVON | IN-AVON-DAN JONES RD FROM CR 100 S TO CR 150 S-DES #1901763: relocate/install 3000' of 4" plastic main, 300' of 2" plastic main & 8 services. Retire 3000' of 4" plastic main, 300' of 2" plastic main & 8 services for road reconstruction, bridge replacement, & storm sewer installation project. | 2023
N/A | 18782266 | 21595302G61221 | PUBLIC IMPROVEMENT - DIST | NW | AVON | IN-AVON-DAN JONES RD FROM US 36 TO CR 100 N - based on available information: relocate/install 1000' of 8" plastic main, 700' of 6" plastic main, 3600' of 4" plastic main, 300' of 2" plastic main & 15 services. Retire 1000' of 8" plastic main, 700' of 6" plastic main, 3600' of 4" plastic main, 300' of 2" plastic main & 15 services for road reconstruction and storm sewer installation project. | 2023
N/A | 18783807 | 21595302G61223 | PUBLIC IMPROVEMENT - DIST | NW | ZIONSVILLE | IN-ZIONSVILLE-TEMPLIN RD-BRIDGE #217 OVER LITTLE EAGLE CREEK: relocate/install 585' of 2" plastic main & retire 515' of 2" plastic main for bridge replacement project. | 2023
SETDSIC12 | N/A | TBD | PUBLIC IMPROVEMENT - DIST | SE | CLARKSVILLE | IN-CLARKSVILLE-BLACKISTON MILL ROAD (PHASE 2) FROM KROGER DRIVE TO ALTRA DRIVE-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 2,700' OF 4" & 2" PE MAIN AND REPLACE 21 SERVICES DUE TO CONFLICTS WITH ROAD RECONSTRUCTION PROJECT. | 2023
N/A | N/A | TBD | RURAL EXTENSION | VEDIN | Multiple | RURAL EXTENSION | 2023
N-XA-12070 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY - TRANS | SE | GREENFIELD | IN-GREENFIELD-EAST INDY LATERAL PHASE 1 East Indy Lateral Phase 1: Replace or parallel existing ~1.5 miles of 6" HPS (Fortville lateral) with 20" HPS from the 18"/20" south to reg station #55-110. Phase 1 provides a large gain in capacity for the Noblesville and Fortville/Greenfield area, both experiencing extremely high growth rates. | 2023
N/A | 18520594 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | FRANKLIN | IN- Franklin-E King Dr. New feed into Franklin 60# system, dramatically increase pressures/capacities on eastside. Install new feed into 60# system from south of town by extending 6" HPS from the 8" MPS at E King Dr/SR44 (east of I-65) and head south to the 8" HPS at E Greensburg Rd. Set new 60# station at SR44. | 2023
N/A | 18520596 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | JEFFERSONVILLE | In-Jeffersonville-Port Rd. to Loop Rd. Overloaded mains, increase capacity of system feeding multiple large users at the Port. Extend 6"/8" HPS from Port Rd reg station south along Port Rd to Loop Rd. Install new regulator station. | 2023
N-X-15210 | 18581521 | N/A | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | NEW PALESTINE | IN-New Palestine-N-X-15210 Retire 1580’ of 2 inch ineffectively coated steel and 1 reg station by installing 1580 feet 2 inch plastic and 2500’ of 6” plastic and replace 15 services. Tie in will be to larger surrounding 60 MAOP system | 2023
N-XA- 11808 | 17509970 | 20583002051216 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-WATERSIDE DR -- INSTALL 2IN PL MAIN Install ~65' of 2" plastic main to create two way feed between a subdivision and apartment complex. | 2023
N-XA- 11809 | 17844055 | 20573302051219 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | NEW CASTLE | IN-NEW CASTLE-MAIN & JEFFRY ST -- TIE IN EXISTING MAINS Install ~ 100' of 4" PE on S. Main St at Jeffry St/Woodbrooke Ct intersection to connect 3 dead end mains. Expected Improvement: Increases minimum pressure in 18-psig system to 11.7 psig from 9.7 psig | 2023
N-XA- 11810 | 17848871 | 20573302051221 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | MUNCIE | IN-MUNCIE-W JACKSON ST -- Install ~5300' of 6" PE in R/W on W Jackson St west of Nebo Rd to 3" MPS at N CR 500 W. Expected Improvement: Increases the pressure in the 50-psig system in the residential area NW of here up from 18 psig to ~ 40 psig. | 2023
N-XA- 11811 | 17834814 | 20582102051213 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | ORESTES | IN-ORESTES-MICHIGAN ST -- INSTALL 2IN MAIN Install ~ 350' of 2" PE on Ontario St from Broadway St to Oak St, and ~ 400' of 2" PE on Erie St from E 1st St to Broadway. Expected Improvement: Increases minimum pressure in 20-psig system to 7.6 psig from 10.8 psig | 2023
N-XA- 11812 | 18439967 | 21583002051212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | INDIANAPOLIS | IN-INDIANAPOLIS-E 96TH ST -- INSTALL 4IN MAIN Install ~3000' of 4" PE on E 96th St between Meridian St and College Ave. Expected Improvement: Provide ~20 psig increase on 2" main that serves Drury Inn and Firebirds restaurant. This would also increase pressures throughout the area just N of SR 31. | 2023
N-XA- 11813 | 18439975 | 21583002051213 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-E 216TH ST -- INSTALL 8" MAIN Install ~4200 ft of 6-8" MP PE on E 216th St, between Stringtown Pike and South State Rd 19. There are also two small segments of 2" PE in the intersection of Stringtown Pike and E 216th that should be replaced. Expected Improvement: This will raise pressure in the Stringtown Pike area from 27 to 44 psig, and support future growth in the area around Morse Reservoir. | 2023
N-XA- 11814 | 18443362 | 21583002051217 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | FISHERS | IN-NOBLESVILLE-FISHERS CYNTHEANNE RD Install approximately 650' of 4" PE on E 126th St, from Southeastern Parkway west to existing 4" plastic main. | 2023
N-XA- 11815 | 18443423 | 21583002051218 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | FISHERS | IN-FISHERS-E 136TH ST -- Install approximately 11,000' of 8" PE on E 136th St, from Jack Walker Ln east to existing 8" plastic main at Stiles Dr. to increase pressure and reliability in high growth area | 2023
N-XA- 11816 | 18439982 | 21583002051214 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | ANDREWS | IN-ANDREWS-RIVERFORK RD -- DERATE MAIN Install approximately 800' of 6" HDPE from station south to W 200 N. Install approximately 450' of 2" HDPE to RS 72167001714. Down grade section of 6" steel transmission main (running to Andrews, IN) to 60psig MAOP and retire RS 72147001716, 72166001715, 72166001717 and 726267001714. Also removes approx. 30 high pressure services. | 2023
N-XA- 11817 | 18442799 | 21573302051212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | DALEVILLE | IN-DALEVILLE-S 800 W -- UPGRADE MAIN Upgrade system to 60psig MAOP and remove regulator station on mostly newer plastic system. Cut and Retest approximately 933' of 2" steel, and upgrade 8,185' of 4" and 2" plastic (upgrade from 26psig MAOP to 60 psig MAOP). Replace approximately 5 of 25 services. Retire regulator station 56344001369 | 2023
N-XA- 11818 | 18443183 | 21583002051216 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | FISHERS | IN-FISHERS-116TH ST-INSTALL 6IN PL MAIN Install ~2200' of 6" PE on 116th from Eller Rd to Wilderness Trail. Expected Improvement: ~ 5 psig increase in area on east side of main install. This also adds to the reliability by providing another feed from the west. | 2023
N-XA- 11819 | 18443013 | 21582102051212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | ANDERSON | IN-ANDERSON-N MADISON AVE-REPLACE 2IN MAIN Replace ~2000' of 2" PE/Steel with 4" PE on N Madison Ave (Monticello Dr to Greenway Dr), or install ~ 1200' of 4" PE (Hazlett St to Riverview Dr) across White River. Expected Improvement: When replaced, we could lose RS 1002 on a 50HDD day and still keep all residential customers on line. In late 2016 there was an outage in this residential area since RS 1002 failed. ~ 850 customers in the area. | 2023
N-XA- 11820 | 18442806 | 21583002051215 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | SHERIDAN | IN-SHERIDAN-S CALIFORNIA ST -- INSTALL 2IN MAIN Install ~ 750' of 2" PE on W 5th St and S California St from Elm Ave to alley south of W 3rd St (may be opportunity to install shorter section of main instead in easement from W 4th to W 3rd). Expected Improvement: Increases minimum pressure in 30-psig system to 16.1 psig from 9.5 psig | 2023
N-XA- 11821 | 18442804 | 21582102051210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | INGALLS | IN-INGALLS-REFORMATORY RD -- INSTALL 6IN MAIN Install ~ 9500' of 6" PE on Reformatory Rd to add a second feed to a one way feed system, from 4" plastic main at S 650 W east to 8" steel coming out of RS 55410000114. Will also significantly help pressure issue in area of Maple Trails Subdivision for future section and additional subdivisions in high growth area. No services included on project. | 2023
N-XA-11517 | 10768266 | 17595502G51214 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN-LAFAYETTE-DAVIS DR-UPGRADE GAS MAIN, Replace 38,131' of 2" PE Main, Replace 477 Services. Project area is 1950's steel prone to leaks. IN-LAFAYETTE-DAVIS DR-UPGRADE GAS MAIN, Replace 38,131' of 2" PE Main, Replace 477 Services. Project area is 1950's steel prone to leaks. | 2023
N-XA-11766 | 18531747 | 19595402051214 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | THORNTOWN | IN-THORNTOWN-SR 47-OLD TBS RETIREMENT SR 47 ~~OLD TBS RETIREMENT,RETIRE OLD TBS FOR THORNTOWN. RETIRE ALL VALVES AND PIPING STILL ACTIVE WITHIN STATION. REMOVE ALL FENCE, GRAVEL AND PIPING SO LAND CAN BE RETURNED TO OWNER. Safety and reliability. | 2023
N-XA-11767 | 10768176 | 19595502051212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN-LAFAYETTE-BECK LN-UPRATE GAS MAIN BECK LN ~~UPGRADE GAS MAIN, UPRATE (East) SYSTEM SERVED BY BECK Station #59000091 and CAYUGA #59000090 Station FROM 15 PSIG TO 60 PSIG. RETIRE REGULATOR STATION. Replace 16,770' of main and 407 meters | 2023
N-XA-11768 | 10768204 | 16595502051213 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN-LAFAYETTE-CAYUGA CT-UPRATE GAS MAIN CAYUGA CT ~~~~UPGRADE GAS MAIN, UPRATE (West) SYSTEM SERVED BY BECK Station #59000091 and CAYUGA #59000090 Station FROM 15 PSIG TO 60 PSIG. RETIRE REGULATOR STATION. Retire and replace 13,758' of main, and 240 services. | 2023
N-XA-11802 | 18733967 | 21574102051210 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | UPLAND | IN-UPLAND-S 8TH ST -- DERATE MAIN Down grade HPD 8" steel main to be able to retire of one or two Upland stations and remove approximately 27 high pressure services. Safety and reliability. May require RS 66284000513 to be rebuilt | 2023
N-XA-12033 | 16990419 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | MOORESVILLE | IN-MOORESVILLE-BARGERSVILLE-SECOND MP FEED GSP RECOMMENDATION Provide second MP feed from the south on Bargersville 600# system Town of Mooresville is a large single feed town, with pressure issues noted from the past cold winters. This will provide reliability and help add future capacity | 2023
N-XA-12068 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENWOOD | IN-GREENWOOD-MP SYSTEM IMPROVEMENT TIE INS MP System Improvement Tie Ins. Extensive development in Greenwood Area - Amazon, etc. -2 miles 8 HDPE along Whiteland Rd -10,870' 6 hdpe along Honey Creek -1770' 4 HDPE along Cutsinger | 2023
N-XA-12071 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-GREENFIELD-REGULATOR STATION-INSTALL Install small double cut regulator station on CR W 1000 S at intersection with 6" transmission line to feed into both the 18# and 60# systems here. Location: 39.959362, -85.841086. Brings 20# system above recommended minimums, additional feed into 60# system. | 2023
NWTDSIC04 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | Install new Station inlet water knockout vessel designed for inlet slug capacity of 700 gallons. Improved withdrawal capability from field in support of Lafayette growth. | 2023
NWTDSIC05 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-046 F. Ponto#03 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC06 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-051 Bahler#01 -Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC07 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-023 F. Ponto#01 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system. | 2023
NWTDSIC08 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-025 F. Ponto#02 -Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC09 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-018 M. Ponto#04 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system. | 2023
NWTDSIC10 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-020 P. Mathew#02 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC11 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-022 P. Mathew#03 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system. | 2023
NWTDSIC12 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-043 P.Mathew#04 -Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system. | 2023
NWTDSIC13 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-034 Sheets#2 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC14 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-050 A. Mathew#02 -Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system. | 2023
NWTDSIC15 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-042 O. Mathew#02 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC16 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-041 V. Mathew#03 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC17 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-017 M. Ponto#03 - Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC18 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-036 IGC#06 Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC19 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-031 IGC#03 Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC20 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-060 Sanford#02 Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC21 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-047 Goss#11 Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
NWTDSIC22 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | WOT-049 Goss#12 Install 2-3/8" tubing and packer and 3/8" stainless capillary unit. Work includes wellhouse and separator system for additional storage field withdrawals to ensure Lafayette system reliability | 2023
SETDSIC04 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | DOLAN | Install compression at Dolan Station Current Pipe Capacity Option 1 - Backup existing Large Compressor | 2023
SETDSIC05 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | JEFFERSON LP | Install Backup Generator - ensure plant operation for enhanced system reliability during power outage event | 2023
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | VEDIN | Multiple | TARGETED ECONOMIC DEVELOPMENT | 2023
N/A | 16143367 | 21583302G61212 | PUBLIC IMPROVEMENT - DIST | SE | GREENFIELD | IN-GREENFIELD-5TH ST CULVERT REPLACE-RELO 100' 2" PE Relocate 2" PE distribution main & 1 SERVICE LINE for culvert replacement | 2024
N/A | 17619462 | 20582102G61210 | PUBLIC IMPROVEMENT - DIST | NE | ALEXANDRIA | Des #1800242-1800243-1800244 Washington St-Alexandria - Final plans have yet to be published. Based off of the available information, we will relocate approximately 1250’ of 2” main and replace 15 services. This main appears to be in conflict with an INDOT road reconstruction project. | 2024
N/A | 17619838 | 20573302G61221 | PUBLIC IMPROVEMENT - DIST | NE | MUNCIE | Muncie Sanitary District - CSO 027 Project-Various Streets - Final plans have yet to be published. Based off of the available information, we will relocate approximately 1600’ of 2” main and replace 58 services. This main appears to be in conflict with a city sewer separation project. | 2024
N/A | 17621894 | 20575102G61215 | PUBLIC IMPROVEMENT - DIST | NE | RICHMOND | City of Richmond - Peacock Rd Recon from 11th to 18th - Final plans have yet to be published. Based off of the available information, we will relocate approximately 1688’ of 12” main and replace 23 services. This main appears to be in conflict with a city road reconstruction project. | 2024
N/A | 18560452 | 21583002G61212 | PUBLIC IMPROVEMENT - DIST | NE | CARMEL | IN-CARMEL-111TH/MONON CENTER RAB-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 300' 4" PE MAIN DUE TO INTERSECTION IMPROVEMENT | 2024
N/A | 18560464 | 21583002G61213 | PUBLIC IMPROVEMENT - DIST | NE | FISHERS | IN-FISHERS-CONNOR PRAIRIE N & S-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO ~1,800' 6" PE, 200' 2" PE, AND 3 SERVICE LINES DUE TO COUNTY DRAINAGE PROJECT | 2024
N/A | 18565001 | 21583002G61223 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-CUMBERLAND RD 150TH TO CUMBERLAND PT-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 3200' 6" PE, 100' 2" PE, AND 2 SERVICE LINES DUE TO ROAD RECONSTRUCTION | 2024
N/A | 18565011 | 21583002G61224 | PUBLIC IMPROVEMENT - DIST | NE | CARMEL | IN-CARMEL-146TH/CAREY RD RAB-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 500' 2"PE, 1200' 4" PE, 4400' 8" STL, AND 7 SERVICE LINES DUE TO INTERSECTION IMPROVEMENT | 2024
N/A | 18565403 | 21573302G61215 | PUBLIC IMPROVEMENT - DIST | NE | NEW CASTLE | Des #1593230 SR 3 Reconstruction-Henry Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 600’ of 8” main and replace no services. This main appears to be in conflict with an INDOT road reconstruction project. | 2024
N/A | 18565418 | 21583002G61226 | PUBLIC IMPROVEMENT - DIST | NE | WESTFIELD | IN-WESTFIELD-161ST/MONON PEDESTRIAN UNDERPASS-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 100' 2" PE, 800' 4" PE MAINS DUE TO PEDESTRIAN UNDERPASS CONSTRUCTION FOR MONON TRAIL | 2024
N/A | 18565530 | 21583502G61212 | PUBLIC IMPROVEMENT - DIST | SE | SHELBYVILLE | IN-SHELBYVILLE-SR 44/I-74 LIFT STATION/FM INSTALL-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 50' 4" PE, 1250' 6" PE, AND 2 SERVICE LINES FOR PROPOSED LIFT STATION AND FORCE MAIN | 2024
N/A | 18565553 | 21583302G61213 | PUBLIC IMPROVEMENT - DIST | SE | FORTVILLE | IN-FORTVILLE-CR 200W/FORTVILLE PIKE-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 1600' 4" PE AND 10 SERVICE LINES FOR PROPOSED WALK PATH | 2024
N/A | 18565808 | 21583302G61214 | PUBLIC IMPROVEMENT - DIST | SE | NEW PALESTINE | IN-NEW PALESTINE-CR 600W/US 52 TO DOE CREEK-BASED OFF OF THE AVAILABLE INFORMATION WE WILL RELO 2800' 2" PE, 6800' 4" PE, 1200' 8" PE AND 45 SERVICE LINES FOR ROAD RECONSTRUCTION | 2024
N/A | 18775543 | 21592402G61216 | PUBLIC IMPROVEMENT - DIST | SE | BEDFORD | IN-BEDFORD-JOHN A WILLIAMS BLVD ~~ RAB DES 1902792 - Relocate 350’ of 6” PE and 2 Services. Necessary for the construction of a Round-a-bout. | 2024
N/A | 18775546 | 21592002G61212 | PUBLIC IMPROVEMENT - DIST | SE | JEFFERSONVILLE | IN-JEFFERSONVILLE-CHARLESTOWN PIKE ~~ - Relocate 3,000’ of 4” PE and 5 Services. Necessary for road reconstruction. | 2024
N/A | 18782263 | 21595302G61219 | PUBLIC IMPROVEMENT - DIST | NW | ZIONSVILLE | IN-ZIONSVILLE-I-465/I-865 INTERCHANGE-DES #1600854: based on available information - relocate/install 1200' of 4" plastic main & retire 1200' of 4" plastic main for the highway interchange modification project. | 2024
N/A | 18870483 | 21583002G61227 | PUBLIC IMPROVEMENT - DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-PLEASANT ST-11TH TO 19TH PH 2-BASED OFF OF AVAILABLE INFORMATION WE WILL RELO 600' 2" PE, 2900' 4" PE, 750' 8" PE, AND 30 SERVICE LINES FOR ROAD RECONSTRUCTION PROJECT | 2024
N/A | N/A | TBD | RURAL EXTENSION | VEDIN | Multiple | RURAL EXTENSION | 2024
N-XA-12032 | 16990681 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY - TRANS | SE | CRANE | IN-CRANE-REPLACE WITH 8IN HP MAIN GSP RECOMMENDATION Replace 4" 400# main with 8", starting at Crane PP outlet. Existing system at capacity, any new growth will require the 4" to be upsized. | 2024
N/A | 13370610 | 16592602051215 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | SEYMOUR | IN-SEYMOUR-BURKHART BLVD AT E 4TH STREET GSP RECOMMENDATION INSTALL 5.18 MILES OH 8 INCH HDPE FOR MP FEED TO FREEMAN FIELD INDUSTRIAL PARK Existing system gets down to ~20 psig on cold days. Area has multiple light industrial company's and continues to grow. Route would parallel 4.63 mile route of new bypass around south-east side of Seymour to the Industrial Park. | 2024
N-X-4810 | 18124767 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | YORKTOWN | IN-YORKTOWN- UPRATE THE TOWN OF YORKTOWN FROM 18# TO 54# TO COMPLETE THE SYSTEM TO SAME PRESSURES. System safety and reliability improvement. | 2024
N-XA- 11822 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-SR 19-INSTALL 12IN STL MAIN Install ~9000' of 12" steel on SR 19 from PEPL Noblesville PP outlet to the N side of 196th St. Expected Improvement: The pressure drop in this line is well over 10 psig. Upsizing would improve the pressure in the area to the N/NE of Noblesville by up to 12 psig, bringing the low point up to 32 psig. Note that this area also drops to 20 psig on a 50HDD seasonal due to large asphalt plant fed off of the 8" on Pendleton Ave. | 2024
N-XA- 11823 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | NEW CASTLE | IN-NEW CASTLE-N RAINTREE DR -- INSTALL 2IN MAIN two way feed provides reliability improvement - outage experienced previously. | 2024
N-XA- 11824 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | FISHERS | IN-NOBLESVILLE-FISHERS Florida Rd Install approximately 4,500' of 6" PE on Florida Rd, from E 113th St north to existing 6" plastic main. Increased pressure and reliability to high growth area. | 2024
N-XA- 11825 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | FISHERS | IN-NOBLESVILLE-FISHERS Southeastern Parkway Install approximately 5,300' of 6" PE on Southeastern Parkway, from Cyntheanne Rd south to E 113th St | 2024
N-XA-11769 | 14000335 | 19595402051212 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LEBANON | IN-LEBANON-SR 39-DERATE SR 39 De-Rate - LEBANON - DERATE 6" AND MOVE 55 SERVICES (Farm Taps) OFF 8" FOR FUTURE IM,NORTH ALONG SR 39. (55 - Services) | 2024
N-XA-11770 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | PLAINFIELD | IN - Plainfield - 750E - Hadley - Install main (750E - Hadley) -Install ~ 1600' of 6" PE on CR 750E from RS #46-040 outlet to Hadley Rd; rebuild RS #46-040 for higher capacity because of new grow on west side of Plainfield. Alternative could be to retire existing station and build a new appropriately sized station at Hadley Rd. ( 0 - Services) | 2024
N-XA-11771 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | PLAINFIELD | IN - Plainfield - 750E - Bucbas - Install main and new regulator station (750E - Bucbas) Install ~ 12,300' of 6" steel HP on the north side of I-70 from CR 750E to Bucbas Rd; install new regulator station; install ~ 2000' of 8" PE on Bucbas from station outlet to Reeves Rd. Increases pressure in south side of Plainfield | 2024
N-XA-11773 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | DANVILLE | IN - Danville - 100N - Whiperwood - Install main (100N - Whiperwood) Install ~ 1100' of 6" PE on CR 200E from Whisperwood to CR 100N, will tie in new areas of growth that are feed by 2" one way feeds. (0 - Services) | 2024
N-XA-11774 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN - LAFAYETTE - CAT 1 on McCarty - Derate the HP main Derate the HP main west from CAT 1 on McCarty to 60# MAOP or install 8" PE west in order to tie in to the 6" PE on Creasy Lane. (0 - Services). System reliability improvement. | 2024
N-XA-11775 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | CRAWFORDSVILLE | IN- Crawfordsville - Derate 325-psig system Derate 325-psig system to 60-psig (convert RS # 52-245B); retire RS # 52-446; maintain RS # 52-882 from 16" main as backup feed; install ~ 4500' of 6" PE on CR 150S from Mt Tabor PP to Ladoga Rd (0 - Services) | 2024
N-XA-11776 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | BRAZIL | IN -Brazil - 1100N - 100E - (1100N - 100E) Install ~ 5300' of 6" PE on CR 1100N from CR 100E to CR 200E. Project will bolster system pressure on east side of Brazil growth area. (0 - Services) | 2024
N-XA-11777 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | TERRE HAUTE | IN - TERRE HAUTE - Woodsmall Dr - Southridge Rd - Replace ~ 3300' of 2" with 4" PE on Woodsmall Dr from US 41 to Southridge Rd. Project will bolster system pressure of neighborhood south side of Terre Haute. (0 - Services) | 2024
N-XA-11778 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | COVINGTON | IN - Covington - Liberty St - Replace ~ 200' of 3/4" with 6" PE Liberty St from RS # 51-288 outlet west to main split. Project will increase gas flow from north to south of town to help with low gas pressure issues. (0 - Services) | 2024
N-XA-11784 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN - LAFAYETTE - Mayfair Station #108 - Upgrade main/retire station. Area that has 1960’s steel that has been prone to leaks, Replace 1,580’ of 2” steel and 20 services on small reg station to be retired. | 2024
N-XA-11785 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | FRANKFORT | IN - Frankfort - TBS 60000033 - Repair leak IN. Station has 8” valves that need replaced, Temp station may need to be installed to supply demand. | 2024
N-XA-12069 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-GREENFIELD-REGULATOR STATION-UPRATE -Continue 125psig to 275psig uprate from Regulator Station 48001170A down 600 W -Using Uprate/Upgrade continue the 275psig system down to Regulator Station 48001168 -This involves an unknown number of services to be checked -We do have most, if not all, work order records for this segment of main -Will involve investigating the following Regulator Stations – 48001551, 48001560, 48001488, 48001487, 48001565, 48001557, and 48001177 Required for industrial and commercial loads proposed in this area. Greatly reduces flow on 6” 275# system McKenzie Rd and Meridian Rd (currently overloaded). | 2024
NWTDSIC23 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | Install compression at Wolcott Station 425 PSI Discharge. Required to ensure deliverability from the field during peak demand. Enhanced reliability for Lafayette system in conjunction with Trunkline lateral. | 2024
NWTDSIC24 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | HENDRICKS COUNTY JUNCTION | Install Backup Generator - ensure plant operation for enhanced system reliability during power outage event | 2024
NWTDSIC25 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | HENDRICKS COUNTY JUNCTION | Replace Compressor building lights to increase safety, light quality and energy efficiency | 2024
SETDSIC06 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | UNIONVILLE | UND-007 Ealy #01 needs to be deepened 20'+ and acidized for additional storage capacity | 2024
SETDSIC07 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | UNIONVILLE | UND-057 F. Skirvin #03 needs to be deepened 10'+ and acidized for additional storage capacity | 2024
SETDSIC08 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | SELLERSBURG | Install Backup Generator and station power disconnect - ensure plant operation for enhanced system reliability during power outage event | 2024
NWTDSIC26 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- TRANS | NW | LAFAYETTE | IN- LAFAYETTE- Construct interconnection with Trunkline and 20" x 29-mile pipeline to NW Lafayette. Pressure improvement, increased capacity, and enhanced Wolcott operation. | 2024
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | VEDIN | Multiple | TARGETED ECONOMIC DEVELOPMENT | 2024
N/A | 18540685 | 21595502G61214 | PUBLIC IMPROVEMENT - DIST | NW | LAFAYETTE | IN-LAFAYETTE-S 9TH ST-ROAD RECONSTRUCTION~~RELOCATE/INSTALL 5400' OF 8" STEEL DISTRIBUTION MAIN, AND 22 SERVICES. RETIRE 5400' OF 8" STEEL DISTRIBUTION MAIN, AND 22 SERVICES FOR ROAD IMPROVEMENT PROJECT. | 2025
N/A | 18565142 | 21582102G61212 | PUBLIC IMPROVEMENT - DIST | NE | ANDERSON | Des #1592299 67th St Road Extension Project-Madison Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 800’ of 4” main and replace no services. This main appears to be in conflict with an INDOT road construction project. | 2025
N/A | 18565190 | 21582102G61213 | PUBLIC IMPROVEMENT - DIST | NE | ANDERSON | Des #1902803 Bridge 107 Deck Project-Madison Co - Final plans have yet to be published. Based off of the available information, we will relocate approximately 800’ of 4” main and replace no services. This main appears to be in conflict with an INDOT bridge replacement project. | 2025
N/A | 18775562 | 21592002G61213 | PUBLIC IMPROVEMENT - DIST | SE | SELLERSBURG | IN-SELLERSBURG-SR 60 INTERSECTION DES 1900373 - Relocate 340’ of 4” PE. Necessary for intersection reconstruction. | 2025
N/A | 18775610 | 21592602G61218 | PUBLIC IMPROVEMENT - DIST | SE | JONESVILLE | IN-JONESVILLE-SR 11 CURVE CORRECTION DES 2000239 - Relocate 3 Services. Necessary for road reconstruction. | 2025
N/A | 15634137 | 18592002G61213 | PUBLIC IMPROVEMENT - DIST | SE | NEW ALBANY | IN-NEW ALBANY-MT TABOR ROAD (PHASE 2) FROM KLERNER LANE TO CHARLESTOWN ROAD-BASED ON AVAILABLE INFORMATION WE WILL RELOCATE APPROXIMATELY 3,900' OF 8", 4", & 2" PE MAIN AND REPLACE APPROXIMATELY 26 SERVICES DUE TO ROAD RECONSTRUCTION PROJECT. | 2025
SETDSIC09 | N/A | TBD | PUBLIC IMPROVEMENT - DIST | SE | CLARKSVILLE | IN-CLARKSVILLE-BLACKISTON MILL ROAD (PHASE 3) FROM ALTRA DRIVE TO GUTFORD ROAD-BASED ON AVAILABLE INFORMATION WE WILL NEED TO RELOCATE APPROXIMATELY 3,500' OF 4" & 2" PE MAIN AND REPLACE 20 SERVICES DUE TO ROAD RECONSTRUCTION PROJECT. | 2025
N/A | N/A | TBD | RURAL EXTENSION | VEDIN | Multiple | RURAL EXTENSION | 2025
N-XA-12052 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY - TRANS | SE | GREENWOOD | In-Greenwood-W Smith Valley Rd. install ~5 miles of 8" HP main on west side of Greenwood | 2025
N-XA-12072 | N-XA-12072 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY - TRANS | SE | GREENFIELD | IN-GREENFIELD-EAST INDY LATERAL PHASE 2 East Indy Lateral Phase 2: Install ~13.5 miles of 16" - 20" HPS from the 18"/20" (or reg station #55-110, depending on route) south to the 8" Greenfield to Mount Comfort lateral. Large increase in capacity for Mount Comfort/Greenfield area. Phase 2 of project to connect the 18/20 to the 16" 600# line in Shelbyville | 2025
N-XA- 11827 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | TIPTON | IN-TIPTON-E STATE RD 28-REPLACE MAIN/SERVICE FEEDING CARGILL Replace ~1670 ft of 4" main/service feeding Cargill on E State Rd 28 (east of Tipton) with 6" MPP, from the 6" on SR28 to the Cargill meter set. Expected Improvement: 23# MEUP to serve a 20# delivery. Cannot always meet 20psig delivery with current system. | 2025
N-XA- 11828 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | RICHMOND | IN-RICHMOND-CHESTER BLVD -- INSTALL SECTIONS OF 6IN MAIN Replace section of 2" plastic with 6" plastic main totaling 1225' to provide two way feed to hospital/north side of town. Reliability and safety improvement. | 2025
N-XA- 11830 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | HUNTINGTON | IN-HUNTINGTON-MERIDIAN ST-INSTALL 6IN PL MAIN Install ~ 14,825' of 6" PE on Meridian St from Markle Rd to US 24. Expected Improvement: Increases minimum pressure in 60-psig system to 37.9 psig from 35.1 psig | 2025
N-XA- 11831 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | RICHMOND | IN-RICHMOND-W INDUSTRIES RD-INSTALL 6IN PL MAIN Install ~ 2170' of 6" PE on W. Industries Rd from 6" main at Flatley Rd to 6" or 8" main at Williamsburg Pike. Expected Improvement: Provide more substantial 3rd feed into Richmond 54-psig | 2025
N-XA- 11832 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | SPICELAND | IN-SPICELAND-SR 3-INSTALL 6IN PL MAIN Install ~ 5640' of 6" PE on SR 3 (Fair Oaks to CR 125W and extension on south end); new regulator station on SR 3. Expected Improvement: Increases minimum pressure in 35-psig system to 21.9 psig from 16.7 psig and provides 2nd feed into the Spiceland system | 2025
N-XA-11786 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN-LAFAYETTE- Park E Blvd to South St - Install new 5,500' of 8" PE to replace the existing 4" PE located on Park E Blvd to South St. Upgrade Main | 2025
N-XA-11787 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | ZIONSVILLE | IN - Zionsville - CR 400S-700E-425S-500S (650E - Brocks Meadows) Install ~ 11,000' of 6" PE on CRs 400S/700E/425S/500S (CR 650E to Brocks Meadows) to provide for growth and bolster the pressure in the growing Zionsville area. | 2025
N-XA-11788 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN - LAFAYETTE - CR 550E - Replace ~ 2650' of 2" with 6" PE on CR 550E from SR 26 to CR 50N Increases minimum pressure in 60-psig system in vicinity of CR 100N to 30 psig from 20 psig | 2025
N-XA-11789 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN - LAFAYETTE - McCarty Ln to SR 26 (I-65 crossing) Install ~ 5400' of 6" or 8" PE on CR 500E (replace 3400' of 2") from McCarty Ln to SR 26 (I-65 crossing) | 2025
N-XA-11790 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN - LAFAYETTE - Wagon Wheel Trail - Install new regulator station & ~ 5300' of 8" PE on CR 100E from south of CR 510S to existing 8" main south of Wagon Wheel Trail (creek crossing). Install regulator station & main | 2025
N-XA-11791 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN - LAFAYETTE - Canal Rd - Fannon Dr - Install ~ 300' of 6" PE from Canal Rd to Fannon Dr north of Heath St (major RR crossing) | 2025
N-XA-11792 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | TERRE HAUTE | IN - TERRE HAUTE - Chamberlain Rd - Install ~ 100' of 4" PE on N Chamberlain Rd & new 30-psig regulator station | 2025
N-XA-11793 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | BLOOMINGDALE | IN - Bloomingdale - Broadway St - Install ~ 500' of 2" PE on Broadway St from end of 1.5" mains (2) to connect systems fed by RS # 38-285 and RS # 38-459. Reliability improvement. | 2025
N-XA-11794 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | HILLSBORO | IN - Hillsboro - Hershey Ln-Bogg St - Install ~ 1500' of 2" PE on Hershey Ln/Bogg St From SR 341/CR 600E to Hobson St | 2025
N-XA-11795 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | VEEDERSBURG | IN - Veedersburg - Perry St-Washington - Install ~ 450' of 2" PE on Perry St/Washington from W 2nd St south to end of 1.5" main & ~ 50' of 2" PE on College at W 2nd. Reliability improvement. | 2025
N-XA-11796 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | PLAINFIELD | IN- PLAINFIELD - Moon Rd reg station - Replace ~7000 ft of 6" and 8" HPS with 10" or 12" HPS from the end of the 12" outlet of Moon Rd reg station #46-73 to the inlet of stations 46-27 and 46-59. Rebuild Moon Rd station for higher capacity. | 2025
N-XA-11829 | N-XA 11829 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | HUNTINGTON | IN-HUNTINGTON-US 24-INSTALL 6IN PL MAIN Install ~ 3740' of 6" PE on US 24 from north of Park Dr to south of Flaxmill Rd. Expected Improvement: Increases minimum pressure in 60-psig system to 39.5 psig from 35.1 psig | 2025
N-XA-12036 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | BLOOMINGTON | IN-Bloomington-High Street New large line to downtown Bloomington. Replace 4" and 6" MPS with 8" MPP on S High St, from outlet of regulator station #29-107, north to intersection with Moores Pike/ Hillside. Tie three 4" mains leaving intersection to new 8" MPP. Rebuild station 29-107 for higher capacity | 2025
N-XA-12037 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | BLOOMINGTON | IN-Bloomington-Station #29-13 Undersized station. Rebuild station # 29-13 for additional capacity and to maintain outlet pressure . | 2025
N-XA-12038 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | BLOOMINGTON | In-Bloomington-E Rogers Rd. Increase capacity to this area. Install ~1200 ft of 4" MPP on E Rogers Rd, from existing 6" MPS on S High, east to The Stands / Winding Brook. | 2025
N-XA-12039 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | BROOKLYN | IN- Brooklyn-Mooney Regulators Upgrade Existing Mooney diaphragms get stuck to throttle plate due to being closed all year and only needing to be used on the coldest of days. Regulators do not open at set point and allow system to heavily droop before kicking in.Replace 4" Mooney regulators with a regulator more suited to conditions experienced here. | 2025
N-XA-12043 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | COLUMBUS | Replace existing 4" MPS with 8" MPP on 22nd St Overloaded main, increased capacity , from the 8" MPS on Midway St to the 6" MPP heading south on Beam Rd. Tie the 4" and 6" to the 8". | 2025
N-XA-12044 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | COLUMBUS | IN-Columbus- Station 31-156 Replace existing system downstream of station 31-156 and retire station. Reliability improvement for two systems. | 2025
N-XA-12045 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | TAYLORSVILLE | IN-Taylorsville- Fiesbeck Dr. Large grain dryer installed east of intersection overloaded existing 2" mains. Adds second feed to system. Install new reg station on Fiesbeck Dr / CR W 550 N at intersection with HWY 31. | 2025
N-XA-12046 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | SEYMOUR | IN-Seymore-W 10th St. Parallel existing 6" MPS on N CR 760 E, from reg station # outlet south to W 10th St. Development/load growth in Seymour area. | 2025
N-XA-12049 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | SHELBYVILLE | IN-Shelbyville- Michigan Rd. Eliminate bottleneck near station outlet, increase capacity of industrial park south of here. Replace ~1800 ft of 4" MPP with 6" MPP on Michigan Rd near Bassett from existing 6" MPP at 39.568118, -85.799604 to existing 6" MPP at 39.565448, -85.794681 | 2025
N-XA-12053 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | FORTVILLE | In-Fortville- CR W 1000 Brings 20# system above recommended minimums, additional feed into 60# system. Install small double cut regulator station on CR W 1000 S at intersection with 6" transmission line to feed into both the 18# and 60# systems here. Location: 39.959362, -85.841086 | 2025
N-XA-12054 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-Greenfield-Station 48-1071 Capacity, reduce station count. Replace small system downstream of station 48-1071 and retire station (8 psi system) | 2025
N-XA-12055 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-Greenfield-Station 48-1082 Capacity, reduce station count. Replace any remaining pipe downstream of stations 48-1082 and 48-1083 and retire stations (8 psi system). Increases pressure and reliability on Greenfield rapid development area. | 2025
N-XA-12056 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-Greenfields-Wood St. Eliminate bottleneck in primary mains into town, improve pressure/capacity. Extend 4" MPP from existing 4" MPS on E Main St at Howard St to the 4" MPP at Baldwin St. Then replace 2" MPP from 4" MPP from Wood St to the 4" MPP heading south on S Swope St. Last, replace the 2" MPP on E South St, from the 4" MPP east of Spring St west to where the 2" heads south and ties to the 6" MPS in the alley south of South St. | 2025
N-XA-12057 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-Greenfield-S State St. Loop multiple parts of the system together with large artery mains, improves pressure/capacity. Replace existing mains/install 6" MPP from the existing 6" MPP from S State St and E Steele Ford, north to the 4" MPS on Davis Rd. | 2025
N-XA-12058 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | In-Greenfield-N Blue Rd. Area growing and existing station outlets feeding this area are overloaded. Install new 275# -> 50# station at N Blue Rd and E McKenzie Rd | 2025
N-XA-12059 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | KNIGHTSTOWN | In-Knoghttown-Main St. Increased capacity and less pressure drop due to 4" line undersized at regulator outlet. Replace 4" MPS from outlet of station 49-294 with 8" MPP to the intersection of Main St and Front St where the 4" splits and continues north and south. | 2025
N-XA-12060 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | RUSHVILLE | IN-Rushville-Station-43-299 Capacity, reduce station count. Replace 2" MPS with 4" MPP at outlet of station 43-299 to the end of the system if not covered under BSCI (GIS says bare, but no boundary) | 2025
NWTDSIC27 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | WOLCOTT | Install Backup Dehydrator at Wolcott to support increased deliverability from field | 2025
NWTDSIC28 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | NW | TERRE HAUTE LP | Install Backup Generator - ensure plant operation for enhanced system reliability during power outage event | 2025
SETDSIC10 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | SELLERSBURG | SEK-018 Couch#08 recompletion related work, then convert from observation to injection/withdrawal to increase field inventory for reliability | 2025
SETDSIC11 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- STORAGE | SE | HINDUSTAN | Install Backup Generator - ensure plant operation for enhanced system reliability during power outage event | 2025
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | VEDIN | Multiple | TARGETED ECONOMIC DEVELOPMENT | 2025
N/A | 18540697 | 21595502G61215 | PUBLIC IMPROVEMENT - DIST | NW | WEST LAFAYETTE | IN-WEST LAFAYETTE-SOUTH ST-PLAZA PROJECT~~RELOCATE/INSTALL 200' OF 2" PE DISTRIBUTION MAIN, AND 5 SERVICES. RETIRE 200' OF 2" PE DISTRIBUTION MAIN, AND 5 SERVICES FOR ROAD IMPROVEMENT PROJECT. | 2026
N/A | 18540795 | 21595502G61212 | PUBLIC IMPROVEMENT - DIST | NW | WEST LAFAYETTE | IN-WEST LAFAYETTE-STATE ST-PURDUE MEM UNION SEWER PROJECT~~RELOCATE/INSTALL 1400' OF 2" PE DISTRIBUTION MAIN, AND 6 SERVICES. RETIRE 1400' OF 2" PE DISTRIBUTION MAIN, AND 6 SERVICES FOR ROAD IMPROVEMENT PROJECT. | 2026
N/A | 18541011 | 215955002G1210 | PUBLIC IMPROVEMENT - DIST | NW | TERRE HAUTE | IN-TERRE HAUTE-CLINTON ST-CORRIDOR INTERCHANGE~~RELOCATE/INSTALL 15000' OF 4" STEEL DISTRIBUTION MAIN. RETIRE 15000' OF 4" STEEL DISTRIBUTION MAIN FOR ROAD IMPROVEMENT PROJECT. | 2026
N/A | N/A | TBD | RURAL EXTENSION | VEDIN | Multiple | RURAL EXTENSION | 2026
N-XA-12076 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY - TRANS | SE | JEFFERSONVILLE | IN-Jeffersonville-Prosser TBS Install 2 miles of 12" transmission main from Prosser TBS to Mt Tabor Rd at New Albany-Floyd County Industrial Park and regulator station. | 2026
N-XA- 11826 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NE | NOBLESVILLE | IN-NOBLESVILLE-E 160TH STREET Install 2.25 miles of 6-inch PE on E 160th Street, Cherry Tree Road, and E 161st Street from Hazeldell Road to River Avenue. Expected Improvement: This improvement will support load growth along the route and also provide another feed to the asphalt plants on River Rd. | 2026
N-XA-11797 | 14000435 | 19595402051213 | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LEBANON | IN-LEBANON-SR 39 MECHANICSBURG SYSTEM SR 39 ~~MECHANICSBURG SYSTEM Project is tied to 2024 project derating of 6” line and removing high pressure services. Project will consolidation stations with uprate of 10psig and 15psig systems. Tie station areas together with 2”PE. Retire stations 53000018, 53000001, & 53000002. Install & 4,320’ of 2”PE, Replace 93 services on derated 6”lines. Mitigates risks with high pressure services and improves system reliability. | 2026
N-XA-11798 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | THORNTOWN | IN - Thorntown - SR 47 - I-65 - Replace ~ 6600' of 4" with 6" PE on SR 47 from RS #53-004 outlet west to I-65 (or install new regulator station off the 12" 720-psig main). Project will Increase minimum pressure in 60-psig system to 26 psig from 19 psig. (0 - Services) | 2026
N-XA-11799 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | TERRE HAUTE | IN - TERRE HAUTE -Margaret Dr - 20th St - Install ~ 1350' of 2" PE on E Margaret Dr from end of main east to S 20th St. Project Increases minimum pressure in south end of main 30-psig system to 21.7 psig from 18.5 psig. (0 - Services) | 2026
N-XA-11800 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | MOORESVILLE | IN - Mooresville - E CR 750 - Enterprise Dr - Install ~14'750 of 6" MPP along E CR 750, S CR 975 E, E CR 800 S, HWY 67, and Enterprise Dr. Start point is at 6" MPP located at 39.653262, -86.355645. End point is 4" MPP located at 39.642983, -86.332124. Project will provide a 3rd feed to Mooresville. Pressure improvement where growth is located. (0 - Services) | 2026
N-XA-11801 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | NW | LAFAYETTE | IN - LAFAYETTE - South Lea - South Lea, Retire stations 59000052 & 59000063 and replace 1960's steel in neighborhood stations feed. Replace (24,250 of old steel main), and (477 services). Increase system MAOP with new main. Area is prone to leaks and main is located in back yards with fences and high vegetation, hard to access. | 2026
N-XA-12062 | 16990410 | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | BLOOMINGTON | IN-BLOOMINGTON-CURRY PIKE/SR 48-8IN HP PL MAIN Install 6000' of 8" HP main from Curry Pike to SR 48 & Profile Pkwy and regulator station Support load growth on west side MP system. Parallel existing 6" MPP on N Curry Pike with 8" MPS (pressure tested for future 600# MAOP), from outlet of station # 29-168, south to intersection at Profile Parkway. Tie both 6" mains to new 8". | 2026
N-XA-12063 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | COLUMBUS | IN-COLUMBUS-WESTPORT-REPLACEMENT Columbus Westport Replace all 1” steel mains in the system. This would complete the Original 1985 plan to replace all mains non standard and steel mains to increase system reliability. | 2026
N-XA-12075 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | SELLERSBURG | INSELLERSBURG-HWY 111/GRANT LINE RD Install ~2 miles of 8" MPP on HWY 111 / Grant Line Rd, from existing 8" MPS at Payne Rd, north to existing 8" MPP at Glenwood Way. Tie large MP systems together | 2026
N-XA-12078 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | CLARKSVILLE | IN-Clarksville-River Ridge Install ~2 miles of 656# MAOP main into the River Ridge area and set new 60# reg station increase capacity for growing River Ridge area, and also provide a second feed to the area for reliability. | 2026
N-XA-12079 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | SHELBYVILLE | IN-Shelbyville-Michigan St. Replace ~1800 ft of 4" MPP with 6" MPP on Michigan St from existing 6" MPP at 39.568118, -85.799604 to existing 6" MPP at 39.565448, -85.794681. Eliminate bottleneck near station outlet, increase capacity of industrial park south of station | 2026
N-XA-12080 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-GREENFIELD-REGULATOR STATION-UPRATE -Regulator Station 48001071 – Center St – Between Osage and Pierson - 8psig System to 50psig System -Isolate and retest approx. 2500’ of 2” Steel Main and 15 Services to 60psig MAOP -Retire Regulator Station and tie over to the existing 50psig system -Approx. 500’ of 2” Plastic main has test records for 60psig MAOP on Work Order 12583302061220 | 2026
N-XA-12081 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-GREENFIELD-REGULATOR STATION-UPRATE Regulator Station 48001364 – East 40 Mobile Home Park – 15psig System to 60psig System - Isolate and retest approx. 1100’ of 2” Steel main and approx. 28 services -If retest is successful, install approx. 1100’ of 4” Plastic main along the south side of US 40 to tie in to retested system. -Retire Regulator Station 48001364 | 2026
N-XA-12082 | N/A | TBD | SYSTEM IMPROVEMENT - SAFETY AND RELIABILITY- DIST | SE | GREENFIELD | IN-GREENFIELD-REGULATOR STATION-UPRATE Regulator Station 48001181 – Lantern Woods – 20psig System to 60psig System -Using inlet pressure, test downstream system to 90psig to establish 60psig MAOP for system -Work Order 34841 for 170’ of 2” Plastic main, but it is Vintage Adyl-A. The rest of the main is M/W Steel. Replace the whole subdivision with new Plastic Main -15 services total. Have test records for 7 services, however 3 are vintage Adyl-A. The other services are M/W Steel of 1966 vintage and should be replaced entirely | 2026
N/A | N/A | TBD | TARGETED ECONOMIC DEVELOPMENT | VEDIN | Multiple | TARGETED ECONOMIC DEVELOPMENT | 2026